## PLI
Washington State Department of Transportation
Desgin-Build Professional Liability:
Assessment of Project Risk Level
Project Title: | [8 empty] | Date:
CN Cost Est: | [8 empty] | WIN:
PIN
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
<Insert Text>
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [8 empty] | NA | 0 |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [8 empty] | NA | 0 |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [8 empty] | NA | 0 |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [9 empty] | 0 |  |  | 0
3 | Do the materials/components/tools/equipment pose any challenges? | [9 empty] | 0 |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [9 empty] | 0 |  |  | 0
4b | Greater than 1 construction Season | [9 empty] | 0 |  |  | 0
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? | [9 empty] | 0 | 0 | 0 | 0
5b | Bridge Over Railroad Track? | [9 empty] | 0 | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? | [9 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? | [9 empty] | 0 | 0 | 0 | 0
5e | Burried Structure? | [9 empty] | 0 | 0 | 0 | 0
5f | Floating Bridge? | [9 empty] | 0 | 0 | 0 | 0
5g | Are there any structural issues not otherwise | [9 empty] | 0 | 0 | 0 | 0
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [9 empty] | 0 |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  | 0
6c | Does the project include flow bypass work? | [9 empty] | 0 |  |  | 0
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [9 empty] | 0 |  |  | 0
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [9 empty] | 0 |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [9 empty] | 0 |  |  | 0
If yes, explain:
<Insert Text>
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [9 empty] | 0 |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [9 empty] | 0 |  |  | 0
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [9 empty] | 0 |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [9 empty] | 0 |  |  | 0
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [9 empty] | 0 |  |  | 0
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [9 empty] | 0 |  |  | 0
10b | Does the project utilize trenchless construction? | [9 empty] | 0 |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [9 empty] | 0 |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [9 empty] | 0 |  |  | 0
12b | Does the proejct incorporate one or more deep foundation? | [9 empty] | 0 |  |  | 0
12c | Is the project constructing any wall(s) that are not standard plan? | [9 empty] | 0 |  |  | 0
12d | Does the project have a high water table? | [9 empty] | 0 |  |  | 0
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [9 empty] | 0 |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [9 empty] | 0 |  |  | 0
13 | Are there any known environmental issues not otherwise addressed by another question? | [9 empty] | 0 |  |  | 0
14 | Does the number of stakeholders exceed 5? | [9 empty] | 0 |  |  | 0
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [9 empty] | 0 |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 0
| Final Project Risk Level Concurrence | [6 empty] | Project Risk Level
[8 empty] | Score |  | Level
| PDE/EM |  | Signature: |  |  |  |  | 0 to 30 |  | Low
[8 empty] | 31 to 60 |  | Medium
| ASDE |  | Signature: |  |  |  |  | 61 to 100 |  | High
[8 empty] | 101 or greater |  | Very High
| ASCE |  | Signature:
Note: * - See "Impact" tab for more information.

## Impact
Washington State Department of Transportation
Assessment of Impact
Project Title: |  | 0
CN Cost Est: |  | 0
Date: | 0
WIN: | 0
Overview: | The assessment of “impact(s)” for any given question is intended to assess the magnitude of costs associated with a negative outcome relative to the project’s total engineer’s estimate (i.e. how much will it cost to correct the issue relative to the project’s engineer’s estimate). These potential costs include any collateral project impacts and associated cost’s (e.g. schedule delay, office overhead, repairs to new and existing facilities including local agency and third party etc.). For any given risk, a negative outcome could result in a range of possible impacts (e.g. an impact could result in between $10,000 to $100,000 in additional costs). When assigned the how “impactful” any given question or risk is, identify the most likely approximate cost.
Assessment of Impact
|  | Magnitude of Impact | Description | Cost relative to Total Eng. Est. | Project Specific Range
|  | Very Low | Very minor impacts with very limited or no collateral contract issues that may result in very minor cost to correct | $ ≤ 0.5% |  | $ ≤ | 0
|  | Low | Minor impacts with some collateral contract issues that results in minor costs to correct. | 0.5% < $ ≤ 2% | 0 | < $ ≤ | 0
|  | Medium | Moderate impacts with collateral contract issues that results in costs to correct. | 2% < $ ≤ 5% | 0 | < $ ≤ | 0
|  | High | Notable impacts with collateral contract issues that results in sizable costs to correct. | 5% < $ ≤ 10% | 0 | < $ ≤ | 0
|  | Very High | Significant impacts with extensive collateral contract issues that result in substantial costs to correct. | $ > 10% |  | $ > | 0

## Ex#01 - $6M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | Region Chip Seal | [6 empty] | Date:
CN Cost Est: |  | 6257000 | [6 empty] | WIN:
PIN
SR | 2 | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
Chip seal will rehabilitate existing bituminous pavement to preserve and maintain pavement structure. These sections will receive bituminous surface treatment, fog seal and rumble strips. Three additional sections of nearby highway will receive shouldering. In these sections, the existing surface beyond the paved shoulder has compacted, settled or eroded and has created a drop off from the paved shoulder to the shoulder rock. Crushed surfacing will be added outside the paved shoulder to bring rock up to the level of the existing pavemen
Considerations
[9 empty] | Yes/No | Impact | Score
1 | Are there any known environmental senstive issues? | [7 empty] | No |  | 0 |  |  | 0
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  | 2
2b | Is the project on an interstate corridor? | [7 empty] | No | NA | 0 |  |  | 2
2c | Is the project on a highway with high ADT (i.e. >25,000)? | [7 empty] | No | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction? | [7 empty] | No |  | 0 |  |  | 0
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | Yes | Low | 2 |  |  | 2
4b | Greater than 1 construction Season | [7 empty] | No |  | 0 |  |  | 0
5 | Type and number of structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? | [9 empty] | 0 | 0 | 0 | 0
5b | Bridge Over Railroad Track? | [9 empty] | 0 | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? | [9 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? | [9 empty] | 0 | 0 | 0 | 0
5e | Burried Structure | [9 empty] | 0 | 0 | 0 | 0
5f | Floating Bridge? | [9 empty] | 0 | 0 | 0 | 0
6 | Bodies of water and/or building in close proximity
6a | Does the project include in-water work? | [7 empty] | No |  | 0 |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  | 0
6c | Are their private structures in close proximity to major work elements? | [9 empty] | 0 |  |  | 0
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | No |  | 0 |  |  | 0
If yes, explain:
<Insert Text>
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | No |  | 0 |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [9 empty] | 0 |  |  | 0
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [9 empty] | 0 |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | No |  | 0 |  |  | 0
9b | Is the project's new draingage element tie into existing drainage system(s)? | [9 empty] | 0 |  |  | 0
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Low | 2 |  |  | 2
10b | Does the project utilize trenchless construction? | [9 empty] | 0 |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads (excluding 5a)? | [7 empty] | Yes | Low | 2 |  |  | 2
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | No |  | 0 |  |  | 0
12b | Does the proejct incorporate deep foundations | [7 empty] | No |  | 0 |  |  | 0
12c | Is the project constructing walls greater than or equal to 35ft in height | [7 empty] | No |  | 0 |  |  | 0
12d | Does the project have a high water table? | [7 empty] | No |  | 0 |  |  | 0
12e | If 12d is yes, will dewatering impact WSDOT or private facilities? | [7 empty] | No |  | 0 |  |  | 0
12f | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  | 0
12g | Are there any significant excavations requiring shoring next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  | 0
13 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  | 5
14 | Does the number of stakeholders exceed 5? | [9 empty] | 0 |  |  | 0
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [9 empty] | 0 |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 6
Project Risk Level
|  |  | Score |  | Level
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#02 - $11M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | Shared Use Path | [6 empty] | Date: | 2020-10-20
CN Cost Est: |  | 11583891 | [6 empty] | WIN:
PIN
SR | 395 | Begin MP | 159.04 | End MP | 161.16 | Length: | 2.12 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
This project will build a 12 foot wide paved, multi-use path between Carlisle Avenue and the current southern termination of the trail near Columbia Avenue in Hillyard; this Work includes the construction three pedestrian bridges, one each at: Wellesley Avenue, Garland Avenue, and Euclid Avenue. This project will also construct reinforced concrete retaining walls, fencing and various safety systems, and other amenities determined in conjunction with Eastern Washington University and community outreach.
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | Yes | NA | 2 |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | No | NA | 0 |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [7 empty] | No | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Low | 2 |  |  | 2
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | Yes | Medium | 3 |  |  | 3
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | Low | 4 |  |  | 2
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5b | Bridge Over Railroad Track? |  |  |  | Yes |  | No |  | 1 | Medium | 6 | 3 | 3 | 3
5c | Pedestrian Bridge Over Roadway? |  |  |  | Yes |  | Yes |  | 2 | Low | 4 | 4 | 0 | 2
5d | Bridge Over Water? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5e | Burried Structure? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | No |  | 0 |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  | 0
6c | Does the project include flow bypass work? | [7 empty] | No |  | 0 |  |  | 0
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [7 empty] | No |  | 0 |  |  | 0
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | No |  | 0 |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | No |  | 0 |  |  | 0
If yes, explain:
<Insert Text>
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | No |  | 0 |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [9 empty] | 0 |  |  | 0
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | No |  | 0 |  |  | 0
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | No |  | 0 |  |  | 0
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | No |  | 0 |  |  | 0
10b | Does the project utilize trenchless construction? | [7 empty] | No |  | 0 |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | No |  | 0 |  |  | 0
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | No |  | 0 |  |  | 0
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | Yes | Low | 2 |  |  | 2
12d | Does the project have a high water table? | [7 empty] | No |  | 0 |  |  | 0
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  | 0
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | No |  | 0 |  |  | 0
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Medium | 3 |  |  | 3
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | Yes | High | 4 |  |  | 4
If yes, explain:
The possible impact that the community will have on approving the proposal put forth to them, as well as the continued interactions with stakeholders, in the confines of a very aethetically driven project, poses significant challenges, conceivably ones never-before-seen in prior WSDOT projects.
[10 empty] | Total Score = | 30
| Final Project Risk Level Concurrence | [6 empty] | Project Risk Level
[8 empty] | Score |  | Level
| PDE/EM |  | Signature: |  |  |  |  | 0 to 30 |  | Low
[8 empty] | 31 to 60 |  | Medium
| ASDE |  | Signature: |  |  |  |  | 61 to 100 |  | High
[8 empty] | 101 or greater |  | Very High
| ASCE |  | Signature:
Note: * - See "Impact" tab for more information.

## Ex#03 - $16M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | Fishpassage | [6 empty] | Date:
CN Cost Est: |  | 16000000 | [6 empty] | WIN:
PIN
SR | 530 | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
This Project will remove two fish barriers and reconstruct the sites with fish passable structures.
Considerations
[9 empty] | Yes/No | Impact | Score
1 | Are there any known environmental senstive issues? | [7 empty] | Yes | Low | 2 |  |  | 2
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  | 2
2b | Is the project on an interstate corridor? | [7 empty] | No | NA | 0 |  |  | 2
2c | Is the project on a highway with high ADT (i.e. >25,000)? | [7 empty] | No | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction? | [7 empty] | No |  | 0 |  |  | 0
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | Yes |  | 0 |  |  | 0
4b | Greater than 1 construction Season | [9 empty] | 0 |  |  | 0
5 | Type and Number of Structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5e | Burried Structure |  |  |  | Yes |  | Yes |  | 2 | Medium | 6 | 6 | 0 | 3
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
6 | Bodies of water and/or building in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | Low | 2 |  |  | 2
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | No |  | 0 |  |  | 0
6c | Are their private structures in close proximity to major work elements? | [7 empty] | Yes | Medium | 3 |  |  | 3
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | No |  | 0 |  |  | 0
If yes, explain:
<Insert Text>
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | No |  | 0 |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [9 empty] | 0 |  |  | 0
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | Yes | Low | 2 |  |  | 2
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | No |  | 0 |  |  | 0
9b | Is the project's new draingage element tie into existing drainage system(s)? | [7 empty] | No |  | 0 |  |  | 0
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | No |  | 0 |  |  | 0
10b | Does the project utilize trenchless construction? | [7 empty] | No |  | 0 |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads (excluding 5a)? | [7 empty] | No |  | 0 |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | No |  | 0 |  |  | 0
12b | Does the proejct incorporate deep foundations | [7 empty] | No |  | 0 |  |  | 0
12c | Is the project constructing walls greater than or equal to 35ft in height | [7 empty] | Yes | Low | 2 |  |  | 2
12d | Does the project have a high water table? | [7 empty] | No |  | 0 |  |  | 0
12e | If 12d is yes, will dewatering impact WSDOT or private facilities? | [9 empty] | 0 |  |  | 0
12f | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | Yes | Medium | 3 |  |  | 3
12g | Are there any significant excavations requiring shoring next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  | 0
13 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  | 5
14 | Does the number of stakeholders exceed 5? | [7 empty] | No |  | 0 |  |  | 0
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | Yes | Low | 2 |  |  | 2
If yes, explain:
Design and functionallity of the fish passage channel.
[10 empty] | Total Score = | 22
Project Risk Level
|  |  | Score |  | Level
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#04 - $35M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | Remove Fish Barriers | [6 empty] | Date: | 2020-10-20
CN Cost Est: |  | 35565937.78 | [6 empty] | WIN:
PIN
SR | 3 | Begin MP | 40.71 | End MP | 41.3 | Length: | 0.59 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
This project is a design-build project that will address a total of 4 fish barrier water crossing structures. The conceptual plan for this project will remove one structure on Chico Creek and replace with two bridges, and remove the 3 additional fish barrier structures on the and replace with 3 culverts with < 20' span.
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | No | NA | 0 |  |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [7 empty] | Yes | NA | 2 |  |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Very Low | 1 | There will be impact to a county road and the potential for use of county roads for detours |  |  | 1
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | High | 8 | 3 CN seasons |  |  | 4
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 1 | High | 4 |  | 4 | 0 | 4
5e | Burried Structure? |  |  |  | Yes |  | Yes |  | 3 | Low | 6 |  | 6 | 0 | 2
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
6c | Does the project include flow bypass work? | [7 empty] | Yes | Low | 2 |  |  |  | 2
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [7 empty] | Yes | Low | 2 |  |  |  | 2
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | No |  | 0 |  |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | No |  | 0 |  |  |  | 0
If yes, explain:
<Insert Text>
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | Low | 2 | Conceptual WZTC would require multiple stages for construction. |  |  | 2
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Very Low | 1 | SR 3 is multi-lane high speed cooridor at this location. |  |  | 1
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | Yes | Low | 2 | WZTC concept requires both NB and SB of SR 3 to be shifted to facilitate separate bridge construction |  |  | 2
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | No |  | 0 |  |  |  | 0
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
10b | Does the project utilize trenchless construction? | [7 empty] | No |  | 0 |  |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | No |  | 0 |  |  |  | 0
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | No |  | 0 |  |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | Yes | Medium | 3 | Wetlands that will be impacted and may require mitigation. |  |  | 3
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | Yes | High | 4 |  |  |  | 4
If yes, explain:
Pre-NEPA fish passage DB project
[10 empty] | Total Score = | 57
Project Risk Level
|  |  | Score |  | Level |  |  | Note: * - See "Impact" tab for more information.
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#05 - $36M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | I-5/Pavement Repair & More Project | [6 empty] | Date: | 2017-05-09
CN Cost Est: |  | 36000000 | [6 empty] | WIN:
PIN
SR | I-5 | Begin MP | 157.44 | End MP | 170.28 | Length: | 12.84 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
Repairing & replacing the deteriorating concrete pavement, replacing bridge expansion joints, approach slabs, remove existing traffic island and extending existing mainline right shoulder as identified in the RFP. Road improvements shall include, but are not limited to rehabilitating the existing pavement to maintain structural integrity and extending the service life of the concrete pavement.
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | Yes | NA | 2 |  |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Low | 2 |  |  |  | 2
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | Yes | High | 4 |  |  |  | 4
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | Medium | 6 |  |  |  | 3
5 | Constructing New Bridge(s) and/or Structure(s) | [10 empty] | No new bridges or new structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? | [9 empty] | 0 |  | 0 | 0 | 0
5b | Bridge Over Railroad Track? | [9 empty] | 0 |  | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? | [9 empty] | 0 |  | 0 | 0 | 0
5d | Bridge Over Water? | [9 empty] | 0 |  | 0 | 0 | 0
5e | Burried Structure? | [9 empty] | 0 |  | 0 | 0 | 0
5f | Floating Bridge? | [9 empty] | 0 |  | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | Yes |  | No |  | 1 | High | 8 | Replace 27 existing expansion joints. | 4 | 4 | 4
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | No |  | 0 |  |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  |  | 0
6c | Does the project include flow bypass work? | [9 empty] | 0 |  |  |  | 0
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [9 empty] | 0 |  |  |  | 0
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [9 empty] | 0 |  |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | High | 4 |  |  |  | 4
If yes, explain:
Lead paint found on many/all existing expansion joints that were replaced.
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | Very High | 5 |  |  |  | 5
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Very High | 5 |  |  |  | 5
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | No |  | 0 |  |  |  | 0
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | High | 4 |  |  |  | 4
10b | Does the project utilize trenchless construction? | [7 empty] | No |  | 0 |  |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | High | 4 |  |  |  | 4
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | No |  | 0 |  |  |  | 0
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | No |  | 0 |  |  |  | 0
12d | Does the project have a high water table? | [7 empty] | No |  | 0 |  |  |  | 0
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  |  | 0
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | No |  | 0 |  |  |  | 0
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | High | 4 |  |  |  | 4
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | No |  | 0 |  |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 53
Note: * - See "Impact" tab for more information.

## EX#06a - $60M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | I-5/ Corridor & Interchange Improvements | [6 empty] | Date:
CN Cost Est: |  | $50M - $60M | [6 empty] | WIN:
PIN
SR | I-5 | Begin MP | 193.07 | End MP | 198.5 | Length: | 5.43 | miles
SR | 529 | Begin MP | 5.61 | End MP | 6.26 | Length: | 0.65 | miles |  |  |  | Note: Same project as 6b; however, evaluation for 6a conducted by Construction Manager
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
The project will construct a new on-ramp from on to southbound interstate freeway, construct a new off-ramp from northbound interstate freeway, and add a permanent fourth lane, designated for high-occupancy vehicles (HOV).
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  | Yes and No. from north edge of Everett to south edge of Marysville, across the Snohomish River delta. |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | Medium | 6 |  |  |  |  | 3
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | Yes |  | No |  | 2 | Medium | 12 |  |  | 6 | 6 | 3
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5e | Burried Structure? |  |  |  | Yes |  | No |  | 1 | Low | 4 |  |  | 2 | 2 | 2
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | Yes |  | No |  | 3 | Low | 12 |  | Minor widening of existing bridges | 6 | 6 | 2
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | No |  | 0 |  |  |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  |  |  | 0
6c | Does the project include flow bypass work? | [7 empty] | No |  | 0 |  |  |  |  | 0
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [7 empty] | No |  | 0 |  |  |  |  | 0
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | No |  | 0 |  |  |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | High | 4 |  |  |  |  | 4
If yes, explain:
known contaminated soils, but extent is unknown
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | No | Low | 0 |  |  |  |  | 2
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | No |  | 0 |  |  |  |  | 0
10b | Does the project utilize trenchless construction? | [7 empty] | No |  | 0 |  | Not known at this time - DB project |  |  | 0
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | High | 4 |  | Not known at this time - DB project |  |  | 4
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | Yes | High | 4 |  | Not known at this time - DB project |  |  | 4
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | No |  | 0 |  | Not known at this time - DB project |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | No |  | 0 |  |  |  |  | 0
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | No |  | 0 |  |  |  |  | 0
If yes, explain:
Settlement of the flood plain soils with the high, tidal water table, supporting new bridge structures and a substantial amount of new fill material adjacent to I-5 is the biggest risk on the project. This risk is well defined, but the solution is not fully known as this is a D-B project.
[10 empty] | Total Score = | 67
Project Risk Level
|  |  | Score |  | Level |  |  | Note: * - See "Impact" tab for more information.
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#06b - $60M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | I-5 / Improvements | [6 empty] | Date: | 2020-09-22
CN Cost Est: |  | 60000000 | [6 empty] | WIN:
PIN
SR | 5 | Begin MP | 190 | End MP | 199 | Length: | 9 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles |  |  |  | Note: Same project as 6a; however, evaluation for 6b conducted by design PE
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
The project will construct a new on-ramp on to southbound (SB) I-5, construct a new off-ramp from northbound (NB) I-5, and add a permanent fourth lane, designated for high-occupancy vehicles (HOV), to NB I-5 in Everett.
Considerations
[9 empty] | Yes/No | Impact | Score
1 | Are there any known environmental senstive issues? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | Yes | NA | 2 |  |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | High | 8 |  |  |  | 4
5 | Type and Number of Structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | Yes |  | Yes |  | 2 | High | 8 |  | 8 | 0 | 4
5b | Bridge Over Railroad Track? |  |  |  | Yes |  | Yes |  | 1 | Very Low | 1 |  | 1 | 0 | 1
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 3 | Low | 6 |  | 6 | 0 | 2
5e | Burried Structure? |  |  |  | Yes |  | Yes |  | 1 | Very Low | 1 |  | 1 | 0 | 1
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 |  | 0 | 0 | 0
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | Yes | High | 4 |  |  |  | 4
6c | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | Yes | Very High | 5 |  |  |  | 5
major work elements (e.g. settlement, drainage)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
If yes, explain:
Superfund site adjacent to the project. Soil and groundwater has high arecenic and lead content.
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | No |  | 0 |  |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Low | 2 |  |  |  | 2
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | Yes | Low | 2 |  |  |  | 2
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
10b | Does the project utilize trenchless construction? | [7 empty] | Yes | Low | 2 |  |  |  | 2
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | Yes | Very Low | 1 |  |  |  | 1
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | High | 4 |  |  |  | 4
12b | Does the proejct incorporate deep foundations? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
12c | Is the project constructing walls greater than or equal to 35ft in height? | [7 empty] | No |  | 0 |  |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
12e | If 12d is yes, will dewatering impact WSDOT or private facilities? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
12f | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  |  | 0
12g | Are there any significant excavations requiring shoring next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  |  | 0
13 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | No | NA | 0 |  |  |  | 5
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Medium | 3 |  |  |  | 3
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | No |  | 0 |  |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 72
Project Risk Level
|  |  | Score |  | Level
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#07 - $109M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | US 12/ Build New Highway | [6 empty] | Date: | 2020-10-14
CN Cost Est: |  | 109000000 | [6 empty] | WIN:
PIN
SR | 12 | Begin MP | 317.16 |  | 328.16 | Length: | 11 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
Increased traffic has resulted in a rise in fatal and disabling crashes within the project limits. Economic development is also hindered without a four-lane connection to the interstate system. This project will construct the next section of a four-lane, limited access divided highway to reduce the risk of collisions and improve economic vitality.
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | Yes | NA | 5 |  |  |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | No | NA | 0 |  |  |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [7 empty] | No | NA | 0 |  |  |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | Low | 4 |  |  |  |  | 2
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | Yes |  | Yes |  | 12 | Low | 24 |  |  | 24 | 0 | 2
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 2 | Very High | 10 |  | Large floodway/floodplain requires very large 1000ft bridge (10% of project cost) | 10 | 0 | 5
5e | Buried Structure? |  |  |  | Yes |  | Yes |  | 4 | Very Low | 4 |  | Large culvert quantities unknown at this time. Estimated 4. | 4 | 0 | 1
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | No | [5 empty] | 0 |  |  | 0 | 0 | 0
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | No |  | 0 |  |  |  |  | 0
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [9 empty] | 0 |  |  |  |  | 0
6c | Does the project include flow bypass work? | [7 empty] | No |  | 0 |  |  |  |  | 0
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [7 empty] | No |  | 0 |  |  |  |  | 0
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [9 empty] | 0 |  |  |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | Very Low | 1 |  |  |  |  | 1
If yes, explain:
Old farmhouse with asbestos to be demolished.
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | No |  | 0 | New US 12 alignment built off-line of existing US 12. |  |  |  | 0
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [9 empty] | 0 |  |  |  |  | 0
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | No |  | 0 |  |  |  |  | 0
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
10b | Does the project utilize trenchless construction? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | Medium | 3 | Farm land |  |  |  | 3
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | Yes | Medium | 3 | Foundation design unknown at this time (Design-Builder design). Possible risk of deep foundations. |  |  |  | 3
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | No |  | 0 |  |  |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | Yes | High | 4 | liquefiable soils risk |  |  |  | 4
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | Yes | Low | 2 |  |  |  |  | 2
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | Yes | Medium | 3 | Animal crossing corridor: WDFW minimum height requirements under structures adjacent to rivers/known migratory paths |  |  |  | 3
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | Yes | Medium | 3 |  |  |  |  | 3
If yes, explain:
ROW acquisition delays / additional ROW purchase delays/ condemnation proceedings Unknown utility impacts / utility relocation coordination Historic flooding area / seasonal work due to muddy conditions
[10 empty] | Total Score = | 81
Project Risk Level
|  |  | Score |  | Level |  |  | Note: * - See "Impact" tab for more information.
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#08 - $110M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | I-90 / Interchange Improvments & Widening | [6 empty] | Date: | 2020-09-23
CN Cost Est: |  | 110000000 | [6 empty] | WIN: | A09070F
[9 empty] | PIN | 109070F
SR | 90 | Begin MP | 25.03 | End MP | 27.8 | Length: | 2.77 | miles
SR | 18 | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
This project will improve the existing interchange using a diverging diamond Interchange (DDI) design. The project will also widen approximately two and half miles of interesecting highway (from its existing 2-lane to 4-lane configuration). This project will also correct 14 fish impassable crossings within the project limits.
Considerations
[9 empty] | Yes/No | Impact | Score
1 | Are there any known environmental senstive issues? | [7 empty] | Yes | Medium | 3 |  |  | 3
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | No |  | 0 |  |  | 0
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [9 empty] | 0 |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | High | 8 |  |  | 4
5 | Type and Number of Structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 3 | High | 12 | 12 | 0 | 4
5e | Burried Structure? |  |  |  | Yes |  | No |  | 2 | High | 16 | 8 | 8 | 4
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | Medium | 3 |  |  | 3
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | Yes | High | 4 |  |  | 4
6c | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | No |  | 0 |  |  | 0
major work elements (e.g. settlement, drainage)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | Low | 2 |  |  | 2
If yes, explain:
Asbestos in small building
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | High | 4 |  |  | 4
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Medium | 3 |  |  | 3
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | No |  | 0 |  |  | 0
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Medium | 3 |  |  | 3
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | Yes | Very Low | 1 |  |  | 1
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Medium | 3 |  |  | 3
10b | Does the project utilize trenchless construction? | [7 empty] | Yes | Very Low | 1 |  |  | 1
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | No |  | 0 |  |  | 0
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | Very Low | 1 |  |  | 1
12b | Does the proejct incorporate deep foundations? | [7 empty] | Yes | Medium | 3 |  |  | 3
12c | Is the project constructing walls greater than or equal to 35ft in height? | [7 empty] | No |  | 0 |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | High | 4 |  |  | 4
12e | If 12d is yes, will dewatering impact WSDOT or private facilities? | [7 empty] | No |  | 0 |  |  | 0
12f | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | Yes | Low | 2 |  |  | 2
12g | Are there any significant excavations requiring shoring next to WSDOT or other facilities? | [7 empty] | Yes | Very High | 5 |  |  | 5
13 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | Yes | NA | 5 |  |  | 5
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | High | 4 |  |  | 4
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | No |  | 0 |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 89
Project Risk Level
|  |  | Score |  | Level
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## Ex#09 - $155M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | I-5 / Interchange and Highway Improvements | [6 empty] | Date:
CN Cost Est: |  | 155000000 | [6 empty] | WIN:
PIN
SR | 5 | Begin MP | 81 | End MP | 84 | Length: | 3 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
Theproject improves safety and mobility on and near I-5 in Chehalis and Centralia. The $155 million project improves two interchanges, adds collector-distributor lanes, straightens a curve on I-5, and connects local roadways to provide alternative route to interstate corridor. The project will construction 5 bridges (1 over I-5, 2 over water, and 2 over RR).
Considerations
[9 empty] | Yes/No | Impact | Score
1 | Are there any known environmental senstive issues? | [7 empty] | Yes | Low | 2 |  |  | 2
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | No | NA | 0 |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  | 2
2c | Is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction? | [7 empty] | No |  | 0 |  |  | 0
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | No |  | 0 |  |  | 0
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | Low | 4 |  |  | 2
5 | Type and number of structures
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | Yes |  | Yes |  | 1 | Medium | 3 | 3 | 0 | 3
5b | Bridge Over Railroad Track? |  |  |  | Yes |  | Yes |  | 2 | Medium | 6 | 6 | 0 | 3
5c | Pedestrian Bridge Over Roadway? | [9 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 2 | Medium | 6 | 6 | 0 | 3
5e | Burried Structure | [9 empty] | 0 | 0 | 0 | 0
5f | Floating Bridge? | [9 empty] | 0 | 0 | 0 | 0
6 | Bodies of water and/or building in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | Low | 2 |  |  | 2
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | Yes | Low | 2 |  |  | 2
6c | Are their private structures in close proximity to major work elements? | [7 empty] | Yes | Very Low | 1 |  |  | 1
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | Very Low | 1 |  |  | 1
If yes, explain:
Asbestos was identified in one of the bridge structures being removed.
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | Low | 2 |  |  | 2
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Low | 2 |  |  | 2
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | Yes | Very Low | 1 |  |  | 1
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Low | 2 |  |  | 2
9b | Is the project's new draingage element tie into existing drainage system(s)? | [7 empty] | Yes | Low | 2 |  |  | 2
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Low | 2 |  |  | 2
10b | Does the project utilize trenchless construction? | [7 empty] | Yes | Very Low | 1 |  |  | 1
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads (excluding 5a)? | [7 empty] | Yes | Medium | 3 |  |  | 3
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | Medium | 3 |  |  | 3
12b | Does the proejct incorporate deep foundations | [7 empty] | Yes | Medium | 3 |  |  | 3
12c | Is the project constructing walls greater than or equal to 35ft in height | [7 empty] | Yes | Low | 2 |  |  | 2
12d | Does the project have a high water table? | [7 empty] | Yes | Low | 2 |  |  | 2
12e | If 12d is yes, will dewatering impact WSDOT or private facilities? | [7 empty] | No |  | 0 |  |  | 0
12f | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  | 0
12g | Are there any significant excavations requiring shoring next to WSDOT or other facilities? | [7 empty] | No |  | 0 |  |  | 0
13 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | Yes | NA | 5 |  |  | 5
0
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Very Low | 1 |  |  | 1
0
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | No |  | 0 |  |  | 0
If yes, explain:
<Insert Text>
[10 empty] | Total Score = | 60
Project Risk Level
|  |  | Score |  | Level
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High

## EX#10 - $330M
Washington State Department of Transportation
Determination of Professional Liability
Project Title: |  | SR 167/ New Expressway | [6 empty] | Date: | 2020-10-20
CN Cost Est: |  | $330M | [6 empty] | WIN:
PIN
SR | 509 | Begin MP | 2.6 | End MP |  | Length: | -2.6 | miles
SR | 167 | Begin MP |  | End MP | 1.93 | Length: | 1.93 | miles
SR |  | Begin MP |  | End MP |  | Length: | 0 | miles
Brief Project Description:
This contract will construct approximately two miles of new highway with an interchange at four locations. There will be a shared-use path along the entire project length. The Project will demolish the an existing crossing over I-5. Other major work includes utility relocations, earthwork grading, bridge construction, retaining walls, wetland mitigation, landscaping, stormwater management facilities, HMA paving, illumination, ITS, Tolling, and signage.
Considerations
[9 empty] | Yes/No | Impact* | Score
1 | Is the Engineer's Estimate greater than or equal to $100 million? | [7 empty] | Yes | NA | 5 |  |  | 5
2 | Project Location
2a | Is the project in an urban area? | [7 empty] | Yes | NA | 2 |  |  | 2
2b | Is the project on an interstate corridor? If yes, skip 2c. | [7 empty] | Yes | NA | 2 |  |  | 2
2c | If 2b is no, is the project on a highway with high ADT (i.e. >25,000)? | [8 empty] | NA | 0 |  |  | 2
2d | Within Local agency jurisdiction and require a City Permit, Detour and/or Turnback Agreement? | [7 empty] | Yes | Low | 2 |  |  | 2
3 | Do the materials/components/tools/equipment pose any challenges? | [7 empty] | Yes | Medium | 3 |  |  | 3
4 | Duration of project (i.e. number of construction seasons, etc)?
4a | Less than or Equal to 1 construction Season | [7 empty] | No |  | 0 |  |  | 0
4b | Greater than 1 construction Season | [7 empty] | Yes | High | 8 |  |  | 4
5 | Constructing New Bridge(s) and/or Structure(s)
[5 empty] | Type of Structure |  | Previously included |  | Number of
[7 empty] | in WSDOT project? |  | Structures
[5 empty] | (Yes/No) |  | (Yes/No) |  | (Number)
5a | Bridges Over a Roadway? |  |  |  | Yes |  | No |  | 7 | Medium | 42 | 21 | 21 | 3
5b | Bridge Over Railroad Track? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5c | Pedestrian Bridge Over Roadway? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5d | Bridge Over Water? |  |  |  | Yes |  | Yes |  | 9 | Low | 18 | 18 | 0 | 2
5e | Burried Structure? |  |  |  | Yes |  | No |  | 1 | Very Low | 2 | 1 | 1 | 1
5f | Floating Bridge? |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
5g | Are there any structural issues not otherwise |  |  |  | No | [5 empty] | 0 | 0 | 0 | 0
addressed by another question?
6 | Bodies of water and/or buildings in close proximity
6a | Does the project include in-water work? | [7 empty] | Yes | High | 4 |  |  | 4
6b | If 6a is yes, is there concern regarding the allocated in-water work window? | [7 empty] | Yes | Low | 2 |  |  | 2
6c | Does the project include flow bypass work? | [7 empty] | Yes | Low | 2 |  |  | 2
6d | Does the project include dewatering to facilitate in-water work (e.g. dewatering portion of stream)? | [7 empty] | Yes | Medium | 3 |  |  | 3
6e | Are their private structures (e.g. homes, building) in close proximity affect by | [7 empty] | No |  | 0 |  |  | 0
dewatering elements (e.g. dewatering causes settlement)?
7 | Any hazardous substance issues (Contaminated soils, underground storage tanks, etc.)? | [7 empty] | Yes | Low | 2 |  |  | 2
If yes, explain:
We have cleaned up a few leaking underground storage tanks to date and there is possibility that others could be found. There is also known contaminated soil & groundwater on a property adjacent to Hylebos Creek between SR 99 and I-5. There is contaminated shallow ground water adjacent to the B&L Landfill.
8 | Traffic control Issues
8a | Is the traffic control complex, and/or involves multiple statges? | [7 empty] | Yes | Medium | 3 |  |  | 3
8b | If so, is this on interstate freeway or multi-lane, high speed corridor? | [7 empty] | Yes | Medium | 3 |  |  | 3
8c | Does traffic control require temporary alignments outside of existing highway footprint? | [7 empty] | Yes | High | 4 |  |  | 4
9 | Drainage Issues
9a | Does the project include more than $250K of drainage work? | [7 empty] | Yes | Low | 2 |  |  | 2
9b | Is the project's new draingage element(s) tieing into existing drainage system(s)? | [7 empty] | Yes | Low | 2 |  |  | 2
10 | Utilities Issues
10a | Is there an elevated risk or concern assocaited with potential conflicts with utilities? | [7 empty] | Yes | Medium | 3 |  |  | 3
10b | Does the project utilize trenchless construction? | [7 empty] | Yes | Low | 2 |  |  | 2
11 | Railroads
11a | Does the project include coordination, design or construction with any railroads not included in 5b? | [7 empty] | Yes | Very Low | 1 |  |  | 1
12 | Geotechnical
12a | Does the project have compressible soils? | [7 empty] | Yes | Medium | 3 |  |  | 3
12b | Does the proejct incorporate one or more deep foundation? | [7 empty] | Yes | High | 4 |  |  | 4
12c | Is the project constructing any wall(s) that are not standard plan? | [7 empty] | No |  | 0 |  |  | 0
12d | Does the project have a high water table? | [7 empty] | Yes | Medium | 3 |  |  | 3
12e | Are there any other high risk geotechnical considerations (historic slides, etc.)? | [7 empty] | No |  | 0 |  |  | 0
12f | Are there any excavations requiring shoring or walls next to WSDOT or other facilities? | [7 empty] | Yes | Low | 2 |  |  | 2
13 | Are there any known environmental issues not otherwise addressed by another question? | [7 empty] | No |  | 0 |  |  | 0
14 | Does the number of stakeholders exceed 5? | [7 empty] | Yes | Low | 2 |  |  | 2
15 | Are there any other potential problems (What do YOU see as risks related to this project). | [7 empty] | Yes | Medium | 3 |  |  | 3
If yes, explain:
There is a large number of plants that are needed for the wetland mitigation sites and the riparian restoration work along the streams and the quantity of plants exceed the ability of landscaping contractors to supply and they do not have enough property to grow the plants.
[10 empty] | Total Score = | 134
Project Risk Level
|  |  | Score |  | Level |  |  | Note: * - See "Impact" tab for more information.
|  |  | 0 to 30 |  | Low
|  |  | 31 to 60 |  | Medium
|  |  | 61 to 100 |  | High
|  |  | 101 or greater |  | Very High