## PM
Code | Title | Description | work op | level | level description
PM | Project Management | See Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | 1 | Process
PM.01 | Project Management Plan Development & Maintenance | The Project Management Plan describes both the Project Performance Baseline for the project deliverables and the schedule and budget/cost plans for delivering them, and the Project Management Methods that will be used by the Project Team during their delivery. This item is for such work as is charged to the PE/RW/CN phases. See Project Management Guide (PMG) for details. http://www.wsdot.wa.gov/Projects/ProjectMgmt/ | 0101/0106, 0201/0206, 0301/0306 | 2 | Group
PM.01.10 | Work Order Authorized | This marks the start of the project process. It is usually considered accomplished when the PE Work Order is authorized by Region Program Management. It can be used for any Work Order Phase PE/RW/CN. Can align with the Begin Preliminary Engineering CPDM milestone. |  | 3 | Milestone
PM.01.20 | Project Kick Off | The purpose of the kickoff meeting is to formally notify all team members and stakeholders that the project has begun and make sure everyone has a common understanding of the project and their roles. Like all formal meetings, there should be an agenda, a preparation packet, and a team charter. Deliverable is called Pre-Construction meeting in the CN Phase. |  | 3 | Deliverable
PM.01.30 | WSDOT Project Management Plan (PMP) | The Project Management Plan describes both the Project Performance Baseline for the project deliverables and the schedule and budget/cost plans for delivering them, and the Project Management Methods that will be used by the Project Team during their delivery. See Project Management Guide (PMG) for details. http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | 3 | Deliverable
PM.01.35 | DBE/WBE Goal requirements determined | During development of the Project Management Plan identify I the project schedule when DBE/WBE goal requirements will be determined. |  | 3 | Milestone
PM.01.40 | Internal Scope Of Work Agreement | Scope of Work, Cost Estimate, and Schedule – The Specialty group works with the Project Office to develop an Internal Scope of Work Agreement that defines the scope of the services for a project, estimates costs for services, and provides P6 Schedule Information. This process applies to the development of preconstruction and construction internal scope of work agreements between the Project Team and Specialty Groups within WSDOT. This process is a complement to the Internal Scope of Work Agreement Development Process Map. Reference PMRS Procedure documents Internal SOW Agreement Development, Internal SOW Agreement Management, Internal SOW Agreement Change Management. |  | 3 | Deliverable
PM.01.50 | FHWA Project Management Plan | The 2005 surface transportation act, the "Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users" (SAFETEA-LU) (Pub.L. 109-59, 119 Stat. 1144) increased requirements for Project Management Plans and Annual Financial Plans on major projects. The general requirements are contained in section 1904(a) of SAFETEA-LU, while the guidance and standards from the FHWA are at this web site: http://www.fhwa.dot.gov/programadmin/mega/ Any project with an estimated total cost of $500 million or more shall complete a project management plan. The PMP shall document "the procedures and processes that are in effect to provide timely information to the project decision makers to effectively manage the scope, costs, schedules, and quality of, and the Federal requirements applicable to, the project; and "the role of the agency leadership and management team in the delivery of the project." |  | 3 | Deliverable
PM.01.60 | FHWA Finance Plan | The 2005 surface transportation act, the "Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users" (SAFETEA-LU) (Pub.L. 109-59, 119 Stat. 1144) increased requirements for Project Management Plans and Annual Financial Plans on major projects. The general requirements are contained in section 1904(a) of SAFETEA-LU, while the guidance and standards from the FHWA are at this web site: http://www.fhwa.dot.gov/programadmin/mega/ The SAFETEA-LU changed the criteria for classification as a Major Project to an estimated total cost of $500 million or greater. and requires recipients of funds for a project with an estimated total cost from $100 million to $500 million to prepare an annual financial plan. A Financial Plan shall “be based on detailed estimates of the cost to complete the project and provide for the annual submission of updates to the Secretary that are based on reasonable assumptions, as determined by the Secretary, of future increases in the cost to complete the project. | 0170 | 3 | Deliverable
PM.02 | Consultant Administration | The process concerning the authorization, selection, management, and oversight of consultants for Personal Service and Architect & Engineering (A&E) agreements and/or supplements. Includes all work involved in the general management of Consultant Agreements related to construction services, including negotiations, agreement and supplement requests, invoice processing, Dispute Review Board agreement management, meetings with consultants, submittal reviews, compliance reviews and other services offered to the consultants and to the state as related to consultants. Including Vessel Construction Engineering and Design Build. See Consultant Services Procedures Manual M27-50. | 0107/0208/0361/0362 | 2 | Group
PM.02.05 | 2020 Contract Freeze Exception | Complete and submit 2020 Contract/Task Order Freeze Exception request, DOT Form 761-019; Revised 04/2020 |  | 3 | Deliverable
PM.02.10 | Consultant RFP | Request for Proposal (RFP): A legal notice for solicitation of consulting services. Please see the Consultant Services Procedures Manual M 27-50, Chapter 1 for procedures. |  | 3 | Deliverable
PM.20.20 | Consultant Signed Contract | A legally binding contract between WSDOT and a Consultant for services rendered. Please see the Consultant Services Procedures Manual M 27-50, Chapters 5, 6, and 7 for procedures. |  | 3 | Deliverable
PM.03 | Community Engagement & Public Involvement | All work involved in the preparation and implementation of the public involvement plan; including work with the Communications Office and preparation and participation at public meetings. Does not include design or access hearings. See WSDOT Communication Manual M3030, as well as EM chapter 400 (EV.40.30 Early Coordination). | 0110/0111 | 2 | Group
PM.03.10 | Community Engagement Plan/ Public Involvement Plan | The public involvement plan includes methods that will elicit the best participation from the community, including traditionally underrepresented groups. Developing an effective public involvement plan is a strategic effort. WSDOT must identify audiences, messages, strategies, and techniques that will meet the unique needs of a proposed transportation project, as well as the needs of the public. The ultimate goal of the public involvement plan is to allow members of the public opportunities throughout the process to: --Learn about the project --Provide information and options --Collaborate --Provide input intended to influence WSDOT decisions --All Agreements and Memorandums of Understanding (MOUs) complete |  | 3 | Deliverable
PM.03.20 | Media & Public Outreach Activities | Community engagement Outreach to public such as stakeholder interviews, mailers, press releases, folios, open houses, booths at local events, traveling displays, briefings, presentations, meetings & other outreach activities; preparation of all media & public involvement communication materials; distribution of materials; on-going written, email & phone communications with media & public; establish & maintain project web page. --Media Relations Plan --Public Meetings --Open Houses --Community Engagement activities |  | 3 | Deliverable
PM.04 | Cost Risk Estimating & Management | Cost Risk Estimating and Management (CREM) involves developing the project cost and schedule estimates and assessing project risk. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ | 0166 | 2 | Group
PM.04.10 | CEVP® | Cost Estimate Validation Process (CEVP®) is required for any project with an estimated cost of $100 million or more. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.04.20 | CRA Workshop | Cost Risk Assessment (CRA) is required for all projects with an estimated cost of $25 million +. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.04.30 | Cost Risk Analysis | Cost Risk Analysis is required for all projects of $10 million or more. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.04.40 | Qualitative Risk Assessment | A qualitative risk assessment is required for all projects. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.04.50 | Combined Value Engineering and Risk Analysis (VERA) | On occasion it may be possible to combine value engineering with a project risk assessment. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.04.60 | Risk Management Plan | A document prepared by Regional managers that includes specific responses for each of the risk identified. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | 3 | Deliverable
PM.05 | Value Engineering | A systematic process of project review and analysis, during concept and design phases, by a multidisciplinary team to provide recommendations for: providing needed functions safely, reliably, efficiently, and at the lowest overall cost; improving the value and quality of the project; and reducing the time to complete the project. Simply stated, VE is an organized application of common sense and technical to find and eliminate unnecessary costs in a project. | 0165 | 2 | Group
PM.05.10 | VE Study | See Design Manual Chapter 310 for details. All projects with a total estimated cost (construction, right of way, preliminary engineering, utilities, etc.) over $25 million and any bridge project over $20 million will need to have a VE Study. |  | 3 | Deliverable
PM.05.20 | VE Final Report | The VE study Final Report and Workbook should include a narrative description of project input information, background and history, constraints and drivers, VE team focus areas, and a discussion of the team speculation, evaluation, and recommendations. All of other team's evaluation documentation including sketches, calculations, analysis, and rationale for recommendations must be included in the Workbook as part of the Final Report. |  | 3 | Deliverable
PM.05.30 | VE Recommendations implementation | Project decision makers act to ensure a fair and serious consideration of the proposed recommendations. The information is share within the agency as recommendations are implemented and associated savings are realized. The completed VE Recommendations Approval Form documents project team decisions with respect to VE recommendations. The completed form is sent to the HQ VE Program Manager. |  | 3 | Deliverable
PM.06 | Project Estimate Reviews (cost & schedule) | Project estimating and estimating reviews begin when design begins. As major portions of the project are designed the associated costs are determined. Each estimate must include a Basis Of Estimate. Formal project estimate reviews are scheduled to coincide with major review milestones that occur at 30%, 60%, and 90% design completion; interim reviews occur as appropriate. | 0167 | 2 | Group
PM.06.10 | 30% estimate review | Geometric design review typically occurs when design is about 30% complete. Design criteria, design decisions, design approval, and the Basis Of Design are complete. See Design Manual Chapter 300. |  | 3 | Deliverable
PM.06.20 | 60% estimate review | Constructability review formally occurs when design is about 60% complete; however constructability is evaluated and considered as soon as design begins. By this milestone major design elements should be completed, underground & overhead conflicts identified and resolved. 3D modeling is complete. |  | 3 | Deliverable
PM.06.30 | 90% estimate review | Pre-contract or Pre-ad review occurs when design is nearly complete, about 90%. Design deliverables are substantially complete. |  | 3 | Deliverable
PM.07 | Quality Management Major Review Milestones | Quality is achieved through systematic planning, scoping, communications coordination, supervision, and technical direction; by providing adequate time in the schedule for thorough reviews. There must be proper definition of job requirements and procedures. Skilled personnel control quality by performing work functions with a level of care that corresponds to the quality goal. PS&E quality processes are defined in two phases: Design Quality (ensuring accuracy of the underlying engineering) and Contract Plans Quality (ensuring that the various design elements are fully integrated and contractual expectations are clear and enforceable). Both are critical in delivery of quality transportation projects. WSDOT Quality Management Guide | 0167 | 2 | Group
PM.07.10 | 30% quality review | 30% Project Development Quality Review Considerations The 30% quality review should be considered for all bridge replacement, fish passage projects, and widening and improvement projects over $5 million in construction. In order for the 30% quality review to be successful, the design team should consider including the following review team members and must complete the following deliverables prior to performing the review (consider including in the initial scopes of work at the start of the project). Design Quality Review Members  Required - Engineer of Record (EOR), Project Development Engineer (PDE), Region Construction Engineer (RCE) or Engineering Manager (EM), Construction PE, Design Team Lead, Designer(s), Hydraulics designer, Traffic (WZTC, illumination and/or signal designer).  Optional (As needed) – Program Management representative, Environmental permits coordinator, Maintenance representative, Geotechnical Engineer or designee, Bridge Design representative, Utilities Engineer or Designee, Plans Engineer/Engineering Services Manager or designee, Landscape Architect, Asst. State Design Engineer (ASDE), Asst. State Construction Engineer (ASCE). WSDOT Quality Management Guide, Appendix A. |  | 3 | Deliverable
PM.07.20 | 60% quality review | 60% Project Development Quality Review Considerations In order for the 60% quality review to be successful, the design team should consider identifying the critical review team member and must complete the deliverables listed in this section prior to performing the review: Design Quality Review Members  Required - Engineer of Record (EOR), Project Development Engineer (PDE), Region Construction Engineer (RCE) or Engineering Manager (EM), Construction PE, Design Team Lead, Designer(s), Plans Engineer or Designee, Hydraulics designer, Traffic Engineer (WZTC, illumination and/or signal designer), Plans Engineer/Engineering Services Manager or designee,  Optional and as needed –Environmental permits coordinator, Maintenance representative, Geotechnical Engineer, Bridge Design Engineer, Utilities Engineer or Designee, Landscape Architect, Asst. State Design Engineer (ASDE), Asst. State Construction Engineer (ASCE), Program Management representative. WSDOT Quality Management Guide, Appendix A. |  | 3 | Deliverable
PM.07.30 | 90% quality review | 90% Project Development Quality Review Considerations The following items should be complete prior to the review. Design Quality Review Members  Required - Engineer of Record (EOR), Project Development Engineer (PDE), Region Construction Engineer (RCE) or Engineering Manager (EM), Construction PE, Design Team Lead, Designer(s), Plans Engineer or Designee, Hydraulics designer, Traffic Engineer (WZTC, illumination and/or signal designer), Plans Engineer/Engineering Services Manager or designee,  Optional and as needed –Environmental permits coordinator, Maintenance representative, Geotechnical Engineer, Bridge Design Engineer, Utilities Engineer or Designee, Landscape Architect, Asst. State Design Engineer (ASDE), Asst. State Construction Engineer (ASCE), Program Management representative. WSDOT Quality Management Guide, Appendix A. |  | 3 | Deliverable
PM.08 | Constructability | CONSTRUCTABILITY Goals of Constructability • Maximize ease with which a project is constructed while maintaining quality, complying standards, and meeting expectations. • Integrate construction expertise into the design to optimize efficiency during construction. • Ensure design is environmentally and socially responsible and continues during construction. | 0167 | 2 | Group
PM.08.10 | Integrate Constructability | Develop a design workplan that includes considerations of constructability integrated through the design process. Interim Constructability reviews at appropriate points of design. |  | 3 | Deliverable
PM.08.20 | 60% formal constructability review | Formal constructability review |  | 3 | Deliverable
PM.08.30 | Pre-ad constructability review | Final constructability review prior to Ad |  | 3 | Deliverable

## SC
Code | Title | Description | work op | level | level description
SC | Project Scoping | Some capital projects have the project scoping included as a specific part of the project. Some projects include work to plan further projects to be subsequently developed and constructed. |  | 1 | Process
SC.10 | Preliminary Estimates & Schedules for Scoping | Estimates and schedules developed for programming. | 01A0, 01AC, 01AP, 01AR | 2 | Group
SC.10.10 | PE Estimate | The estimated cost and schedule to complete the design phase of a project. Developed for programming the project. Contact Specialty groups to obtain an estimate for their services. |  | 3 | Deliverable
SC.10.20 | RW Estimate | The estimated cost and schedule to complete the right of way phase of a project. Includes all resource costs. Developed for programming the project. |  | 3 | Deliverable
SC.10.30 | CN Estimate | The estimated cost and schedule to complete the construction phase of a project. Developed for programming the project. |  | 3 | Deliverable
SC.20 | Agency & Tribal Coordination for Planning Studies | Outreach to public agencies & tribes | 115 | 2 | Group
SC.20.10 | Agency Outreach | Outreach to public agencies including initial interviews of partner agencies; briefings, presentations and meetings with technical staff and elected officials; written, email and phone communications |  | 3 | Deliverable
SC.20.20 | Tribal Outreach | Outreach to tribes including initial contact letter; briefings, presentations, meetings and consultations with tribal staff and members; written, email and phone communications. |  | 3 | Deliverable
SC.20.30 | Corridor Working Group | Establish Corridor Working Group (CWG); conduct CWG meetings; prepare CWG meeting materials; on-going communications with CWG members. |  | 3 | Deliverable
SC.20.40 | Agency & Tribal Coordination Summary | Document summarizing communications and coordination with public agencies & tribes |  | 3 | Deliverable
SC.30 | Existing Conditions Inventory & Analysis for Planning Studies and Scoping | For a planning or corridor study, inventory and analysis of existing facility, study area and travel conditions; identification of existing & future no-build deficiencies in accordance with Design Manual Chapter 300 | 125 | 2 | Group
SC.30.10 | Existing Facility & Study Area Conditions | Inventory & description of roadway classifications, function and characteristics; vicinity & study area map; inventory & description of facility including geometrics, structures, traffic signals & control devices, terrain & roadside characteristics; inventory & description of study area transportation network (all modes) and land use/zoning conditions |  | 3 | Deliverable
SC.30.20 | Environmental Inventory & Overview | Inventory & description of natural and built environment; inventory & description of archeological, historical and cultural resources; identify potential environmental justice issues and potential mitigation requirements of proposed improvements |  | 3 | Deliverable
SC.30.30 | Travel Conditions Analysis & Deficiencies Identification | Inventory of existing and historical traffic data & collisions; collect additional counts/data if needed; select & validate model; model existing and future no-build traffic conditions; analysis of data and forecasts; identify existing & future no-build access, safety, mobility and modal needs and deficiencies |  | 3 | Deliverable
SC.30.40 | Existing Conditions Summary | Document summarizing existing conditions & identified deficiencies | 126 | 3 | Deliverable
SC.40 | Improvement Options Development & Assessment for Planning Studies | For a planning or corridor study, development & assessment of options to address identified deficiencies | 0125/0126 | 2 | Group
SC.40.10 | Improvement Options | Identify & develop concept-level short & long-term improvements for all modes & TSM/TDM |  | 3 | Deliverable
SC.40.20 | Screening Criteria & Analysis | Establish screening criteria, methodology & process; select & validate model; model future build (improvement options) traffic conditions; analyze forecasts; screen proposed options |  | 3 | Deliverable
SC.40.30 | Short & Long-Term Recommendations | Establish prioritization process; select and prioritize screened improvement options into short-and long-term list of recommended improvement projects |  | 3 | Deliverable
SC.40.40 | Funding Program & Financial Resources | Identify funding program and financial resources available to implement RDP recommendations & next steps within the decision process to implement the RDP |  | 3 | Deliverable
SC.50 | Planning Report | Planning Report documenting project work and recommendations | 127 | 2 | Group
SC.50.10 | Draft Planning Report | Draft report documenting project inventory and analysis work, outreach activities, and improvement recommendations; circulate draft report to CWG, partner agencies & WSDOT for review & comment |  | 3 | Deliverable
SC.50.20 | Final Planning Report | Revise & finalize report in response to comments; distribute report |  | 3 | Deliverable
SC.60 | Project Profile (Project Summary) | A document which comprises the Project Definition, Design Decisions and the Environmental Review Summary for a project | 169 | 2 | Group
SC.60.10 | Project Definition | The official document that states the purpose and need for the project and the solution of the deficiency. This is a formal document that must have Region and HQ concurrence. |  | 3 | Deliverable
SC.60.20 | Basis Of Design, Design Parameter Sheets, Alternative Comparison Table (Design Decisions Summary) | A document which is part of the Project Summary which illustrates design considerations and details about design aspects of the project. |  | 3 | Deliverable
SC.60.25 | Pre-Design Phase | Per Project Delivery Memo #19-03 December 17, 2019 Basis of Design, BOD and Pre-Design Implementation This implemented a pre-design phase for certain projects to revise or validate scope, schedule and budget via a scalable Multi Modal (M2) and Multi Modal + Multijurisdiction (M3) process. Project Summary and Basis of Design (BOD) is required to complete the Pre-Design Phase. At the end of the pre-design phase, the Region will submit the Project Summary which will include an endorsed BOD or an exemption in accordance with Design Manual Chapter 1100.10(1)(a) and any other documentation produced during the pre-design phase. Projects that require the pre-design phase will follow the process documented at: http://wwwi.wsdot.wa.gov/publications/fulltext/cpdm/Scoping-Proritization/PreDesignProtocol.pdf. For projects with a PE phase start of July 2020 or later, utilize a pre-design phase to refine or validate project scope, schedule and budget for projects identified to have, or are likely to have, design element changes. Exemptions to using a pre-design phase in cases where design elements are expected to change requires ASDE concurrence. Decision-making and analysis is to be documented in the Project Summary and/or BOD in accordance with applicable Design Manual guidance and policy. The pre-design phase is not expected to change the overall design phase costs. About 15% of the project will require a pre-design phase, could be more or less in your region, coordinate with your ASDE on requirements for your specific project. |  | 3 | Deliverable
SC.60.30 | Environmental Review Summary | A document which illustrates environmental permit needs and addresses the level of environmental approval and classification of the project. |  | 3 | Deliverable
SC.60.40 | Project Definition Complete (Region) | PERFORMANCE REPORTING MAJOR Milestone- The official document that states the purpose and need for the project and the solution of the deficiency is a formal document called Project Summary. For reporting purposes, the Project Definition Milestone is considered complete on the date the Regional Administrator (RA) or the RA designee signs the Project Summary document. |  | 3 | Milestone
SC.60.50 | Project Definition Complete (HQ) | Milestone- The Project Definition is formally approved when Project Summary has received Headquarters signature. (formally the Project Summary which includes the Project Definition, ERS, DDS) |  | 3 | Milestone

## DES
Code | Title | Description | work op | level | level description
DES | Design | Planning and scoping typically have separate budgets but are encompassed under Design or Preliminary Engineering (PE). The terms “Design” or “Design Phase” are sometimes used interchangeably with DES. Also see SC.60.25 Pre-Design Phase |  | 1 | Process
DES.10 | Project Delivery Method Selection | A systematic process based on a balance of the anticipated benefits and allocated risks used in the selection of the project delivery method for a project. | 0113 | 2 | Group
DES.10.10 | Project Delivery Method Selection Document | Document of the final decision to proceed contracting via the selected project delivery method. |  | 3 | Deliverable
DES.10.20 | Project Need Statement | A project need statement (or statement of need) provides clear, accurate plain talk description of the root needs that will facilitate the development of efficient, focused project alternatives. DM 1101.05
DES.10.30 | Define Project Concept | Technical analysis |  | 3 | Deliverable
DES.10.40 | Solution Alternatives & Selection | This involves generating alternatives, evaluating alternatives, checking costs and --Generate Alternatives --Evaluate Alternatives --Alternative Reviews --Solution Selection --Appraise R/W Costs --Preliminary Project Development |  | 3 | Deliverable
DES.20 | Project Data, Survey Data, and Base Map | All work to collect background, project, survey, and field data and background data, and develop the base map. | Multiple | 2 | Group
DES.20.10 | Project Data | All work to collect field data and background date, except ground collection of survey data. Background Data, Aerial Photographs, Data Collection - Aerial Photography, Clear Zone Inventory, As-Built Data Verified, ADA Accessibility Feature Inventory | 0116 (For ADA use 0151) | 3 | Deliverable
DES.20.20 | Surveying Data | All work to collect, measure, and record ground topography necessary to build a base map for the project, including the work to prepare structural site data. This includes all work to establish project control, traversing, installing bench marks, etc. Contact GeoMetrix Office/ HQ Survey and Mapping Branch as needed. Establish Geodetic Survey Control Establish Project Geometric Framework Geodetic Survey Monument Location Geodetic Survey Monument Re-establishment Monitor Slope and Structure Movement Utility Location Data Collection -Survey Data Collection - 3D Terrestrial LiDAR (Laser Scanning) Data Collection - Hydrographic Survey Data Collection - Field Topography Data Collection – Borehole Survey (SPS Easting, SPS Northing, Station, Offset, and Elevation) | 0117 | 3 | Deliverable
DES.20.30 | Site Data for Geotech | Site information provided to the Geotechnical Office (GO) and/or Region Materials Office (RMO) by the project design office (specific to the type of project) to initiate geotechnical work on a project during the design and PS&E phases. See Design Manual Chapter 610. Typically this includes: • A plan view showing: R/W, alignments, wetlands, 100 yr. and 500yr high water elevations, utilities, contours, and existing features; with the proposed new project elements overlaid. • Elevation view • Cross-sections • CAD DTM | 0116/0117 | 3 | Deliverable
DES.20.40 | Base Map | Development of the project base map for Preliminary Engineering. This Work Op does not include Base Map work for Right of Way Plans, use Work Op 0119. Contact GeoMetrix Office/HQ Survey and Mapping Branch as needed. Data Processing Photogrammetry and Point Cloud. | 0118 | 3 | Deliverable
DES.20.50 | Maintenance and Design Collaboration | An onsite review of the project with maintenance to look at existing situations and any concerns about the proposed design. | 0116 | 3 | Deliverable
DES.20.60 | Design Visualization | Still Image or Visualization using 3D CAD modeling to effectively explain complicated design options and/or practical design decisions. Contact GeoMetrix Office / Visual Engineering Resource Group (VERG) as needed. | 0123 | 3 | Deliverable
DES.30 | Interchange Justification | Evaluate when new or reconstructed access on limited access facilities will be affected. See Design Manual Chapter 550. |  | 2 | Group
DES.30.10 | Interchange Justification Report (IJR) | An IJR is required for new/reconstruction of accesses on limited access facilities. It is required to be submitted to the Assistant State Design Engineer. FHWA approval is required for all interstate highways. See Design Manual Chapter 550. |  | 3 | Deliverable
DES.40 | Access Control | Evaluation of limited access and managed access components on WSDOT facilities. See Design Manual Chapters 520, 530 and 540. | 0120 | 2 | Group
DES.40.10 | Managed Access Permit | All new access connections and alterations/improvements to existing access connections to state highways require an access connection permit. See Design Manual Chapter 520 and 540. |  | 3 | Deliverable
DES.40.20 | Hearings | Certain capital transportation projects require a public hearing by state and federal statutes. See Design Manual Chapter 210 |  | 3 | Deliverable
DES.40.30 | Limited Access Hearing | An L/A hearing is required by law (per RCW 47.52) whenever limited access is established or revised on new or existing highways. (See Design Manual Chapter 210) |  | 3 | Deliverable
DES.40.40 | Limited Access Report & Plans | The access report and plans notifies the local agency how the limited access will impact their transportation system. The access report and plans are submitted to the HQ Access and Hearings Unit for approval. The Local Agency(ies) must concur with the Access Report. See Design Manual Chapter 210 & 530 and the Plans Preparation Manual Section 100.05. |  | 3 | Deliverable
DES.40.50 | Limited Access Hearing Packet | The prehearing packet (including legal notices, news releases, and exhibits) is prepared and submitted to HQ Access Office at least 45 days prior to the hearing. This packet will be sent to abutting owners. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.40.60 | Formal Access Hearing | Milestone- A formal hearing that gives local public officials, owners of abutting property, and other interested citizens an opportunity to be heard concerning any plan that proposes the limitation of access to the highway system. See Design Manual Chapter 210. |  | 3 | Milestone
DES.40.70 | Limited Access Findings & Order | A document containing the findings and conclusions of a limited access hearing that is approved by the Environmental and Engineering Programs Director. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.40.80 | Adoption of Limited Access Findings & Order | Milestone- The date of formal adoption of the Findings and Order for limited Access. See Design Manual Chapter 210. |  | 3 | Milestone
DES.40.90 | Design Hearing Packet | When it is determined that a hearing is to be held, the region prepares a pre-hearing packet. See Design manual Chapter 210 for details. |  | 3 | Deliverable
DES.40.100 | Design Hearing | A Design Hearing is required when there are social, economic, or environmental impacts. This hearing is held after a route is established, but before final design is complete and ensures the public has an opportunity to present views on design alternatives. This hearing may be formal or informal. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.40.110 | Adoption of Design Hearing Summary | A document containing the Design Hearing Summary and responses to all questions as a result of the hearing. State Design Engineer approves the summary for state routes, and FHWA approves the summary for interstate projects. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.40.120 | Corridor Hearing | A Corridor hearing is required if there is a proposed route on new location, or a significant change in layout of connecting roads. See Design Manual Chapter 210 |  | 3 | Deliverable
DES.40.130 | Adoption of Corridor Hearing Summary | A document containing the Corridor Hearing Summary and responses to all questions as a result of the hearing. The Director of Environmental and Engineering Programs approves the summary for state routes. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.40.140 | Environmental Documentation Hearing | Normally held for projects requiring an EIS, the hearing is timed to fall within the comment period for the Draft EIS. |  | 3 | Deliverable
DES.40.150 | Adoption of Environmental Hearing Summary | A document containing the Environmental Hearing Summary and responses to all questions as a result of the hearing. The Director of Environmental and Engineering Programs approves the summary for state routes. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | 3 | Deliverable
DES.50 | Materials (Roadway) | Development of soils, surfacing, and materials reports for project. | 01G6 | 2 | Group
DES.50.10 | Pavement Determination | Preliminary recommendations for surfacing materials. See WSDOT pavement interactive guide at http://wwwi.wsdot.wa.gov/MaintOps/mats/pavementguide.htm |  | 3 | Deliverable
DES.50.20 | Surfacing/Resurfacing Report | A report that lists the recommendations for type, size, & depth of surfacing for each roadway and recommendations for rehabilitation of existing roadways |  | 3 | Deliverable
DES.50.30 | Materials Source Report | A report on a specific WSDOT material source that verifies the quality and quantity of the material requested. |  | 3 | Deliverable
DES.50.40 | Native Soil Exploration | See Chapter 610 Investigation of Soils, Rock, and Surfacing Materials. The designer contacts and meets with the Regional Materials Engineer (RME) (and the HQ Geotechnical Office as needed) at the project site to conduct a field review to help identify the geotechnical issues for the project. A brief conceptual-level report that summarizes the results of the investigation is provided to the designer. The information from this report will be used to prepare the contract as well as by the Construction Office to evaluate Value Engineering Change Proposals (VECP). For example a contractor may want to use native soil instead of the specified import in the contract to save money. |  | 3 | Deliverable
DES.60 | Geotechnical | Development of Geotechnical reports for project. | 01G1/01G6 | 2 | Group
DES.60.10 | Soil Boring Notice of Intent | All drilling activities, including Geotech soil borings, monitoring/resource protection wells, and developing or decommissioning water wells. See Geotechnical Design Manual M46-03, Appendix 1-A. |  | 3 | Deliverable
DES.60.20 | Geotechnical Recommendations - RMO | Region Materials Office (RMO) The RMO provides geotechnical recommendations to the Project Office or other Specialty Offices, which they then incorporate into the project, see Chapter 1 of the Geotechnical Design Manual M 46-03. Project elements usually addressed by the RMO include: sign, signal, luminaire, and camera foundations, retaining walls less than 10 ft. in height, noise wall foundations, cuts and fills less than 10 ft. in height, culverts less than 30-inches, infiltration rates, and material sources. There can be several deliverables that are provided depending upon what the project contains. • Geotechnical Memorandums – Geotechnical memorandums are usually prepared for smaller projects, projects where the stakeholders are all WSDOT offices, to address one or two project specific elements, or to provide recommendations that are conceptual or preliminary. • Boring Logs – Borings logs are usually included in the Geotechnical Memorandum, and the Project Office includes them in the Contract Provisions. • Geotechnical Reference Information – The RMO will prepare a package of project related geotechnical references and provide that to Contract Ad and Award office who will post that information on their website for contractor use. | 01G6 | 3 | Deliverable
DES.60.30 | Geotechnical Recommendations - GO | Construction Division – Geotechnical Office (GO) The GO provides geotechnical recommendations to the Project Office or other Specialty Offices, which they then incorporate into the project, see Chapter 1 of the Geotechnical Design Manual M 46-03. There can be several deliverables that are provided depending upon what the project contains and the delivery method; Design-Build (DB) or Design-Bid-Build (DBB). Not all of the deliverables listed below are required. Typical DBB Deliverables • Geotechnical Reports – Geotechnical reports are prepared for larger projects or for projects that have external stakeholders. They typically address more than one project element. • Geotechnical Memorandums – Geotechnical memorandums are usually prepared for smaller projects, projects where the stakeholders are all WSDOT offices, to address one or two project specific elements, to provide early final recommendations to team members to keep work moving forward, or to provide recommendations that are conceptual or preliminary. • Boring Logs – Borings logs are usually included in the Geotechnical Report or Geotechnical Memorandum, and the Project Office includes them in the Contract Provisions. • Geotechnical Reference Information – The GO will prepare a package of project related geotechnical references and provide that to Contract Ad and Award office who will post that information on their website for contractor use. Typical DB Deliverables • Geotechnical Memorandums – Geotechnical recommendations may be prepared for project elements in the basic configuration. They are not intended to provide enough information to complete final design. The have just enough content to help assess feasibility, costs and risks. • Request for Proposal (RFP) Section 2.6 – Section 2.6 of the RFP is Geotechnical. The Project Office is responsible to deliver the entire RFP, but project specific technical requirements will be added into the 2.6 section template by the GO. • Geotechnical Data Report (GDR) – The GO will prepare the GDR and any supplements. • Geotechnical Reference Information - The GO will assemble a package of reference information which the Project Office will make available to the Design Builder along with the RFP. • Geotechnical Baseline Report (GBR) - The GO will prepare the GBR. • Request for Qualifications (RFQ) – The Project Office will prepare the RFQ, but the GO may prepare a portion of the document and should review it. • Instructions to Proposers (ITP) - The Project Office will prepare the ITP, but the GO may prepare a portion of the document. | 01G1 | 3 | Deliverable
DES.70 | Bridge and Structures | Preliminary work, design, and PS&E for bridges and structures. See Bridge Design Manual: http://www.wsdot.wa.gov/Publications/Manuals/M23-50.htm | Multiple | 2 | Group
DES.70.10 | Bridge Site Data | Structure Site Data to be sent to HQ Bridge for design and PS&E. See Design Manual Chapter 710. | 0144 | 3 | Deliverable
DES.70.20 | Wall Site Data | Structure Site Data to be sent to HQ Bridge, HQ Geotechnical, or Region Materials for design and PS&E. See Design Manual Chapter 730. | 0144 | 3 | Deliverable
DES.70.30 | Noise Wall Site Data | Plan and profile along centerline of the wall. Data to be sent to HQ Geotechnical or Region Materials for design. See Design Manual Chapter 740. | 0144 | 3 | Deliverable
DES.70.40 | Noise Barrier Height & Verification Analysis | This deliverable uses more detailed design data to optimize barrier height and verify that feasibility and requirements are met. | 0144 | 3 | Deliverable
DES.70.50 | Bridge Condition Report | Produced by the Bridge Office - describes condition of deck and general information about the structure. | 01SA | 3 | Deliverable
DES.70.60 | Preliminary Bridge Plan | Preliminary plan showing location, length, type of structure (TS&L) and estimate. | 01SB | 3 | Deliverable
DES.70.70 | Sign Structure Design & Plans | All work to design, review and finalize the sign structure plans. | 01SC | 3 | Deliverable
DES.70.80 | Noise Wall Design | Document/design noise walls that are non-standard or are part of a retaining wall. | 01SD | 3 | Deliverable
DES.70.90 | Retaining Wall Design | Document/design non standard retaining walls & soldier pile walls | 01SE | 3 | Deliverable
DES.70.100 | Bridge Rails/Expansion Joints Design | Document/design rehabilitation of bridge rails, expansion joints and bridge decks | 01SF | 3 | Deliverable
DES.70.110 | Other Structure Design | Document/design approach slabs, tunnel, emergency repairs and other structural design. | 01SG | 3 | Deliverable
DES.70.120 | Consultant Structural Plans Review | Performed by HQ Bridge & Structure office on preliminary or structural design layouts prepared by non-WSDOT personnel. Includes plans and specifications review and revisions. This work op is only for use by the HQ Bridge & Structures Office. | 01SH | 3 | Deliverable
DES.70.130 | Bridge Architect | Work to prepare preliminary designs and design concepts; review and finalize the architectural features for bridge, retaining walls, noise walls, and other structures. | 01SJ | 3 | Deliverable
DES.70.140 | Bridge Design | All work to design, review and finalize the bridge plans, including 90% Plans turn-in to the regions 4 weeks prior to 100% turn-in | 01SK | 3 | Deliverable
DES.70.150 | Bridge Specials and Estimates | All work to prepare Bridge & Structures contract provisions including Std. Spec. Amendments, GSP’s, Special Provisions, Appendices and estimates. | 01SN | 3 | Deliverable
DES.80 | Roadway Geometrics and Plans | Development of earthwork design and channelization design. Also includes minor safety design and documentation. | 0174 | 2 | Group
DES.80.10 | Roadway Design | Finalization of the horizontal and vertical alignments for each roadway in the project, see Design Manual Chapters 1210 & 1220 |  | 3 | Deliverable
DES.80.20 | Alignment Plan | Horizontal and vertical alignment plans for each roadway in the project, see Design Manual Chapters 1210 & 1220 |  | 3 | Deliverable
DES.80.30 | Intersection Plan for Approval | A plan that address the intersection design considerations in accordance with Design Manual Chapter 1310 |  | 3 | Deliverable
DES.80.40 | Interchange Plan for Approval | A plan that address the interchange design considerations in accordance with Design Manual Chapter 1360 |  | 3 | Deliverable
DES.80.50 | Channelization Plan | A plan that address the channelization design considerations in accordance with Design Manual Chapter 1310 |  | 3 | Deliverable
DES.80.60 | Project footprint & Earthwork Quantities | The Project Footprint & Earthwork Quantities are calculations that determine the cut/fill lines and project footprint, and the earthwork cut/fill quantities that specialty groups such as Environmental and Real Estate need to start their processes. These lines and quantities help identify if the project extends beyond WSDOT R/W, which determine the need for Right of Way acquisition. They also define the limits of the Area of Potential Effect map, which must be developed prior to the Section 106 cultural investigation and other Environmental documentation. The project footprint and earthwork quantities are critical for the NEPA/SEPA process, and Environmental permits such as the NPDES. See Design Manual Chapter 1600 |  | 3 | Deliverable
DES.80.70 | Roadway Sections | Geometric roadway cross section from the subgrade to finish grade |  | 3 | Deliverable
DES.80.80 | Roadside Safety Analysis | Address items on the Clear Zone Inventory and any other safety items that have been discovered including documenting a decision to fix or not. Design Manual Chapter 1600 |  | 3 | Deliverable
DES.80.90 | Minor Safety Documentation | Paving projects (P1) have opportunities to improve minor deficiencies as part of the preservation work. See Design Manual Chapter 1120 | 0176 | 3 | Deliverable
DES.80.100 | Corridor or Project Analysis | If completed - a corridor or project analysis in accordance with Design Manual Chapter 300 |  | 3 | Deliverable
DES.90 | Hydraulics/Drainage | The Hydraulic Report is intended to serve as a complete documented record containing the engineering justification for all drainage modifications that occur as a result of the project. See Hydraulics Manual. See Highway Run Off Manual M31-16. See Design Manual Chapter 301 Design Maintenance Coordination. | 0146/0147/0148 | 2 | Group
DES.90.10 | Type A Hydraulic Report | Type A Hydraulic Reports contain documentation of design for major hydraulic work. See the Hydraulics Manual. |  | 3 | Deliverable
DES.90.20 | Type B Hydraulic Report | Type B Hydraulics Reports contain documentation of design for hydraulics. See the Hydraulics Manual. |  | 3 | Deliverable
DES.90.30 | Hydraulic Summary | At the Region's discretion, smaller projects may replace a Type B report with a Hydraulic Summary, see the Hydraulics Manual and Region Hydraulics Engineer for more information. |  | 3 | Deliverable
DES.90.40 | Specialized Hydraulics Design and Analyses | Specialized hydraulic design and analyses are stream designs, floodplain analyses, bridge backwater analyses, scour analyses, fish passage designs, and other HQ Hydraulics roles and responsibilities. See Hydraulics Manual Section 1-2. |  | 3 | Deliverable
DES.90.50 | Stormwater BMP Maintenance Plan | It is the responsibility of the Project Design office to prepare Stormwater Best Management Practice Maintenance Plans for hand off to Construction Office for construction of the BMP and field survey verification testing of the constructed facility. See Highway Runoff Manual M31-16, Chapter 3 & 5. Construction Office then provides as-built feedback to the Author of the BMP plan, which will be finalized into the a WSDOT Owner's Manual for the Stormwater facility. Governed by the National Pollution Discharge Elimination System (NPDES) stormwater permit and the Clean Water Act, WSDOT constructs facilities to control and remove pollutants from stormwater discharged to surface waters. The NPDES permit requires that these best management practice (BMP) facilities be maintained for long-term performance. Stormwater BMPs are the physical, structural, and managerial practices that, when used singly or in combination, prevent or reduce the detrimental impacts of stormwater, such as the pollution of water, degradation of channels, damage to structures, and flooding. |  | 3 | Deliverable
DES.90.60 | Hydraulic Report Approved | Milestone- Hydraulics Report Approved for project. |  | 3 | Milestone
DES.100 | Partnerships | A contract entered into by two or more groups. | 0109 | 2 | Group
DES.100.10 | Local Agencies Agreements/MOU's | A contract between the Washington State Department of Transportation and a local governmental agency that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | 3 | Deliverable
DES.100.20 | Other Agencies Agreements/MOU's | A contract between the Washington State Department of Transportation and other governmental agencies or non-governmental agencies that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | 3 | Deliverable
DES.100.30 | Tribal Agreements/MOU's | A contract between the Washington State Department of Transportation and a tribal government that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | 3 | Deliverable
DES.100.40 | Developer Agreements/MOU's | A contract between the Washington State Department of Transportation and a private developer that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | 3 | Deliverable
DES.110 | Railroad | Communication and tasks related to Railroads. Contact the Region Utilities Office, Railroad and Agreements Office. | 0158 | 2 | Group
DES.110.10 | Railroad Facility Plan | A plan showing the location of known railroad facilities. This plan should include all additional data acquired to insure the accuracy needed for the project. --Preliminary Relocation Plan --Existing Railroad Facilities Located --Updated Railroad Facility Location Plan --Railroad Facilities Relocation Plan |  | 3 | Deliverable
DES.110.20 | Railroad Agreements | A contract between the Department and a railroad for work by either party where the department will receive or pay funds. |  | 3 | Deliverable
DES.120 | Facilities Plans | The design of facilities and buildings, including architectural, structural, mechanical, electrical, and landscape architecture aspects. These buildings and facilities include highway safety rest areas, ferry terminals, and other facilities. | Multiple | 2 | Group
DES.120.10 | Site Design (Facility) | All work to develop, review and finalize design criteria, plans and specifications for all site grading, stormwater, utilities, roadways, parking lots, and other landscape architecture or civil engineering tasks associated with new or alterations to existing buildings, structures or facilities. | 01F1 | 3 | Deliverable
DES.120.20 | Architectural Design | All work to develop, review and finalize design criteria, plans and specifications for all site layout, building design (floor plans, elevations) and other architectural tasks associated with new or alterations to existing buildings, structures or facilities. | 01F2 | 3 | Deliverable
DES.120.30 | Facilities Structural | All work to develop, review and finalize design criteria, plans and specifications for all structural design of buildings and other structural tasks associated with new or alterations to existing buildings, structures or facilities. | 01F3 | 3 | Deliverable
DES.120.40 | Facility Mechanical | All work to develop, review and finalize design criteria, plans and specifications for all plumbing, HVAC, steam lines, and other facility mechanical tasks associated with new or alterations to existing buildings, structures or facilities. | 01F4 | 3 | Deliverable
DES.120.50 | Facility Electrical | All work to develop, review and finalize design criteria, plans and specifications for all electrical design and other facility electrical tasks associated with new or alterations to existing buildings, structures or facilities. | 01F5 | 3 | Deliverable
DES.120.60 | Site Restoration | All work to develop, review and finalize design criteria, plans and specifications for all finish grading, plantings and irrigation and other landscape architecture tasks associated with new or alterations to existing buildings, structures or facilities. | 01F6 | 3 | Deliverable
DES.130 | Roadside Restoration and Site Development | Work to meet landscaping and roadside policies. Meet regulatory requirements. The funding type determines the limits of roadside restoration, and the character classification determines the appropriate treatment. | 162 | 2 | Group
DES.130.10 | Roadside Master Plan | Work required to meet agency policy and regulatory requirements. The Roadside Policy Manual describes restoration requirements. Impact area/location, roadside character and context determines the appropriate treatment. See Region Landscape Architect or HQ Roadside Development Manager. |  | 3 | Deliverable
DES.130.20 | Restoration Estimate Worksheet | Region Landscape Architects or the HQ Roadside and Site Development Section prepares a restoration estimate which includes all costs to restore and establish a sustainable plant community per the Roadside Policy Manual, and the Roadside Manual Chapter 810. |  | 3 | Deliverable
DES.130.30 | Roadside Restoration Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications related to roadside restoration associated with new or alterations to existing roadway projects. See the Roadside Policy Manual and Roadside Manual Chapter 800. |  | 3 | Deliverable
DES.130.40 | Irrigation Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans and specifications relating to irrigation, including Irrigation Structure notes and details. See Plans Preparation Manual (PPM) 400.06 | 163 | 3 | Deliverable
DES.130.50 | Aesthetics Treatment Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications related to architectural treatment and visual aspects of projects associated with new or alterations to existing roadway projects. See Design Manual Chapter 950; Environmental Manual Chapter 459 and Visual Discipline reports for the project. The Aesthetics Treatment Plan is a deliverable performed by a landscape architect for EV.30.160 Visual Impacts Discipline Report. | 0161 | 3 | Deliverable
DES.130.60 | Mitigation Design and Plan Sheets | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications associated with permit requirements for mitigation and environmental restoration. | 0139 | 3 | Deliverable
DES.130.70 | Plant Establishment Implementation Plan | All landscape architecture work to develop, review and finalize criteria during design including reports, plans, and specifications related to plant establishment requirements associated with roadside or mitigation design. | 0164 | 3 | Deliverable
DES.140 | Traffic Analysis | The determination of whether or not the proposed improvement(s) will satisfy future capacity needs and/or establishment of the requirements necessary for the facility to operate at an acceptable level of service through the design year. Refer to Design Manual 320. | 0150 | 2 | Group
DES.140.10 | Collision Data | Validate accident data. Update / supplement if necessary |  | 3 | Deliverable
DES.140.20 | Preliminary Traffic Analysis Report | A report that identifies safety and/or capacity deficiencies and provides recommendations including geometric configurations, intersection control, and appropriate traffic control devices. |  | 3 | Deliverable
DES.140.30 | Traffic Volumes & Movements | Validate traffic counts. Update / supplement if necessary |  | 3 | Deliverable
DES.140.40 | Traffic Model | Validate traffic model. Update/supplement if necessary |  | 3 | Deliverable
DES.140.50 | Traffic Analysis Report | Review the operational needs of a study area with consideration of multimodal factors. |  | 3 | Deliverable
DES.140.60 | Bus Stop Inventory | Design decisions . Approval, denial, or variance per engineering and traffic considerations. |  | 3 | Deliverable
DES.140.70 | Intersection Control Alternatives Analysis (ICA) | An objective of the ICA are to: provide a consistent framework to determine the most compatible intersection control type for the location, context, economics, and balance of performance needs. See DM 1300 for further details. |  | 3 | Deliverable
DES.140.80 | Collision Analysis Report | Review safety aspects of the project study area. |  | 3 | Deliverable
DES.150 | Traffic Design & Plans | Gathering of traffic data and development of Traffic reports, studies, designs, and plans. | 01T0 | 2 | Group
DES.150.10 | Signing Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Develop plan sheets in accordance with Plans Preparation Manual (PPM) 400.06. Includes sign specification sheets and details. See also Design Manual Chapter 1020. | 01TA | 3 | Deliverable
DES.150.20 | Illumination Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Develop plans that show street lighting, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1040 | 01TB | 3 | Deliverable
DES.150.30 | Signal Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, traffic volume and turning movements counts, Speed Study, utility service agreement. Plans developed by the Region or HQ Traffic Office, including details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1330 | 01TC | 3 | Deliverable
DES.150.40 | Traffic Signal Permit | State statutes (RCWs) require Department of Transportation approval for the design and location of all conventional traffic signals, ramp meters and some types of beacons located on city streets forming parts of state highways. Approval by the Department of Transportation for the design, location, installation, and operation of all other traffic control signals installed on state highways is required by department policy. The Traffic Signal Permit (DOT Form 242-014 EF) is the formal record of the department’s approval of the installation and type of signal. The permit is completed by the responsible agency and submitted to the Regional Administrator for approval. | 01TC | 3 | Deliverable
DES.150.50 | ITS Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Plans normally developed by the Region Traffic Office that show how to construct Intelligent Transportation Systems, including details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1050 | 01TD | 3 | Deliverable
DES.160 | Utilities | The Utility Accommodation Team evaluates and authorizes the installation of utilities and other facilities or activities within the state highway right of way. This Team will also coordinate any necessary relocations. | 0160 | 2 | Group
DES.160.10 | Existing Utilities Located | Locate existing utilities in the field to level of accuracy required. Can vary from quality level D (most basic) to quality level A (Subsurface Utility Engineering (SUE)). See Utilities Manual. Determine the best method to use and the level of detail needed. |  | 3 | Deliverable
DES.160.20 | Existing Utility Plan | A plan showing the location of known aerial and underground utility facilities. This plan should include all additional data acquired to insure the accuracy needed for the project. |  | 3 | Deliverable
DES.160.30 | Utility Relocation Plan | A plan showing utility relocations/adjustments. |  | 3 | Deliverable
DES.160.40 | Utility Agreements | A contract between the Department and a utility for work by either party where the department will receive or pay funds. |  | 3 | Deliverable
DES.170 | Work Zone Traffic Control (WZTC) - Design & Plans | The planning, design, and preparation of the Transportation Management Plan and contract documents for the modification of traffic patterns during construction is known as work zone traffic control. See Design Manual Chapter 1010. | 0154 | 2 | Group
DES.170.10 | Work Zone Traffic Control Meeting | A meeting with the Work Zone Traffic Control (WZTC) design team, construction office, and other stakeholders to discuss various traffic control strategies for the project. See Design Manual Chapter 1010. |  | 3 | Deliverable
DES.170.20 | Transportation Management Plan (TMP) | Includes the plans and actions to address the work zone safety and mobility impacts of the project. A TMP document is required for significant projects. See Design Manual Chapter 1010. |  | 3 | Deliverable
DES.170.30 | Staging Design | Development of a construction sequence/staging strategy that is efficient, cost effective, and safe. See Design Manual Chapter 1010. |  | 3 | Deliverable
DES.170.40 | Traffic Control Plans | Temporary Traffic Control strategies developed into site specific, project specific or typical traffic control plans. see Plans Preparation Manual (PPM) Chapter 460 and Design Manual Chapter 1010. |  | 3 | Deliverable
DES.170.50 | Detour Plan | Plans that show the route to be used as a detour while the project is being constructed. See Plans Preparation Manual (PPM) 400.06 |  | 3 | Deliverable
DES.180 | Design Documentation | Design documentation is prepared to record the evaluations by the various disciplines that result in design recommendations. See Design Manual Chapter 300 | 0172 | 2 | Group
DES.180.10 | Design Approval | Milestone- (May be delayed/combined with Project Development Approval) Design approval includes: a memo that describes the project, Project Summary Documents, Design Criteria, Design Variances, known deviations, applicable Channelization plans, Intersection plans, Interchange plans, or Alignment plans and a current cost estimate. See Design Manual Chapter 300 |  | 3 | Milestone
DES.180.20 | Design Documentation Package | A compilation of assumptions, decisions, justifications, and approvals that support the ultimate design of the project, to include review of the package. This file is designated for long term storage in accordance with WSDOT's document retention policies. See Design Manual Chapter 300. Basis Of Design, Scope Validation, Deliverables for the Project, Schedule, Cost Estimate, Risk management plan, Change management plan, Quality Management Plan, Human Resources Plan Project Profile - comprised of Project Definition, Environmental Review Summary, and Basis Of Design for a project |  | 3 | Deliverable
DES.180.30 | ADA Accessibility Design Documentation (MEF Maximum Extent Feasible) | ADA Accessibility of existing Pedestrian Facilities to the Maximum Extend Feasible Documentation . See Design Manual Chapter 1510 | 0151 | 3 | Deliverable
DES.180.40 | Design Analysis | A documented decision granting approval at project specific locations to differ from the design level specified in the Design Manual. DM Chapters 300 and 1100. |  | 3 | Deliverable
DES.180.50 | Project Development Approval | Milestone- Final approval of all project development documents by the designated representative of the approving organization prior to the advertisement of a capital transportation project. See Design Manual Chapter 300 |  | 3 | Milestone
DES.190 | R/W Base Map and R/W Plans | Preparation of the base map to depict property ownership lines, alignments, and Right of Way boundaries for use as a PS& E plan/profile or Right of Way plan. Includes title report work, right of entry, calculation of areas & property corners, construction permits & easements, preparation, review, and submission of relocation plans. Also includes drafting of alignments, Right of Way lines, drainage and irrigation easements, and maps and plans for hardships or other special cases. | 0119 | 2 | Group
DES.190.10 | Preliminary Right of Way | Determination of approximately how much additional Right of Way will be needed to construct the project. Includes any property impacts as defined in the Right of Way Manual Division 6. |  | 3 | Deliverable
DES.190.20 | R/W Plans | R/W Plans are submitted to the Region R/W Plans Office for review and transmittal to HQ for approval in accordance with Plans Preparation Manual (PPM) Divisions 1 and 2 |  | 3 | Deliverable
DES.190.30 | Sundry Site Plans | Legal Document/Right of Way Plan showing boundary of property to be acquired by WSDOT that is not adjacent to highway right of way. Typically these would include mitigation sites, stormwater treatment areas, and maintenance sites. |  | 3 | Deliverable
DES.190.40 | DNR Plat | Legal Document prepared by WSDOT HQ R/W Plans Office showing a survey of property to be acquired from the Department of Natural Resources - Either uplands or aquatic |  | 3 | Deliverable
DES.190.50 | Monumentation Map | The official state survey document for state highway R/W alignment, see Plans Preparation Manual (PPM) Divisions 1 and 2 |  | 3 | Deliverable
DES.190.60 | Record of Survey | Public Record filed with the County Auditor used to preserve the evidence of land surveys. The content and format of Record of Surveys are prescribed by law. |  | 3 | Deliverable
DES.190.70 | Land Corner Records | Written record of corner information as prescribed by the Department of Natural Resources, used to perpetuate or establish land corners and their accessories. |  | 3 | Deliverable
DES.190.80 | Permit to Destroy | Application made to Department of Natural Resources requesting permission to remove or destroy monuments or make them inaccessible. |  | 3 | Deliverable
DES.190.90 | Ownership Interests and Encumbrances (Title Reports) | A legal records that defines property interest and boundaries needed to prepare the R/W Plans. |  | 3 | Deliverable
DES.190.100 | Right-of-Way Project Funding Estimate (PFE) | The Project Funding Estimate (PFE) is submitted to Program Management for funding approval to begin the RW phase of the project. All RW labor costs associated with preparation of the PFE. Ideally, it is completed by an appraiser, an appraisal reviewer, and a relocation expert and is prepared for every project in which right of way will be acquired. |  | 3 | Deliverable
DES.190.110 | Right of Entry | Field investigations and field explorations, other than land surveying, that are obtrusive in nature require a Right of Entry from the property owner. RCW 47.01.170 |  | 3 | Deliverable
DES.190.120 | Right of Way and Limited Access Plan Approval | The checking of Right of Way and Limited Access plans against technical standards for the project and the preparation of federal and state Right of Way agreements. Review and approval of Right of Way and Limited Access revisions requested from Region. Includes Region and HQ review, certification to FHWA, and FHWA approval. | 0124 | 3 | Deliverable
DES.190.130 | R/W Plan Approved | Milestone- HQ R/W Plans Section makes the final review and then the Plan is stamped & signed by the responsible Project Engineer. Right of Way acquisition cannot begin without plan approval. See Plans Preparation Manual (PPM) Divisions 1 and 2. |  | 3 | Milestone
Note on B37: Parker, Julie: This activity has been added at the request of the NWR Design Guidance Team. An investigation of completed projects with large earthwork quantities that revealed that many of them have penny bids with CRIPS that contractor used native soil instead of specified import. This activity is to ensure the native soil investigation is done during the design phase of the project.
Note on C37: 610.04(6)(a) Project Definition The designer contacts and meets with the RME (and the HQ Geotechnical Office as needed) at the project site to conduct a field review to help identify the geotechnical issues for the project. In general, if soil/rock conditions are poor and/or large cuts or fills are anticipated, the RME requests that the HQ Geotechnical Office participate in the field review and reporting efforts. The designer provides a description and location of the proposed earthwork to the RME as follows: • For widening of existing facilities, the anticipated width, length, and location of the widening, relative to the current facility, are provided. • For realignments, the approximate new location proposed for the facility is provided. • Locations in terms of length can be by milepost or stations. A brief conceptual-level report that summarizes the results of the investigation is provided to the designer.
Note on D128: Parker, Julie: Definition of the work op code is: Work involved in the fulfilling Section 504 of the Rehabilitation Act and the Americans with Disabilities Act of 1990 (ADA) on new and existing transportation facilities. See Design Manual Chapter 1510 and Terminal Design Manual Chapter 300. Including design compliance efforts for crosswalks, curbs, ramps, traffic signals, sidewalk, bridge, buildings and pedestrian facilities such as Ferry Terminals and Rest Areas.

## EV
Code | Title | Description | work op | level | level description
EV | Environmental Review and Permitting | Summary task for all environmental review and permitting. See Environmental Procedures Manual (EM) Parts 4 and 5 Chapters 400 and 500. |  | 1 | Process
EV.10 | Endangered Species Act Compliance | All projects with a federal nexus must comply with ESA. EM Chapter 436 Fish, Wildlife, and Vegetation | 0132 | 2 | Group
EV.10.10 | Biological Assessment or No Effect Letter | Assessment/analysis prepared by project biologist. It describes how a project will be built, what conditions will be met, and when they will be done. EM Chapter 436 Wildlife, Fish, and Vegetation |  | 3 | Deliverable
EV.10.20 | BA Submitted to NOAA/NMFS and USFWS | Milestone: documentation submitted to federal agency. National Oceanographic and Atmospheric Administration; National Marine Fisheries Service; United States Fish and Wildlife Service. |  | 3 | Milestone
EV.10.30 | Consultation with NOAA and USFWS | EM Chapter 436 Fish, Wildlife and Vegetation |  | 3 | Deliverable
EV.10.40 | NOAA and USFWS Biological Opinion or Concurrence Letter | Milestone– The concurrence letter/BO documents resource agency agreement with project design and mitigation measures. |  | 3 | Milestone
EV.10.50 | USFW Biological Opinion or Concurrence Letter | Milestone– The concurrence letter/BO documents resource agency agreement with project design and mitigation measures. |  | 3 | Milestone
EV.20 | Section 106 & EO 05-05 Compliance | Summary task for Section 106 and EO 05-05 Compliance tasks other than the Cultural Resources Discipline Report | 0133 | 2 | Group
EV.20.10 | Section 106 & EO 05-05 Compliance Exemption Determination | EM Chapter 456 Cultural Resources |  | 3 | Deliverable
EV.20.20 | Section 106 & EO 05-05 Compliance Area of Potential Effect Map | EM Chapter 456 Cultural Resources |  | 3 | Deliverable
EV.20.30 | Cultural Resources Survey/Effect Determination | EM Chapter 456 Cultural Resources |  | 3 | Deliverable
EV.20.40 | Section 106 & EO 05-05 Letter of Concurrence or Memorandum of Agreement | EM Chapter 456 Cultural Resources |  | 3 | Deliverable
EV.20.50 | Section 106 Project Scoping and Internal Review | Review of GIS and existing documentation by Cultural Resource Specialist to ascertain presence/absence of known sites in project area. Review required prior to soil disturbance (e.g. wetland delineation, Geotech boring, or hazardous material recon). |  | 3 | Deliverable
EV.20.60 | Initial Tribal Consultation | Refer to Environmental Manual 456.05 and 530.04. Follow the WSDOT Section 106 Flow Chart (Figure 456) as guidance for implementing Tribal Consultation. Initiates the formal consultation process with Tribes and other Interested Parties. |  | 3 | Deliverable
EV.30 | Discipline Reports | Summary Task: Discipline reports and other studies prepared by WSDOT Regions or consultants to document environmental investigations called for in the EM Chapters 420-459 | 01E0 | 2 | Group
EV.30.10 | Geology & Soils | Discipline Report. EM Chapter 420 Earth (Geology & Soils) | 01ED | 3 | Deliverable
EV.30.20 | Air Quality | Discipline Report. EM Chapter 425 Air | 01EA | 3 | Deliverable
EV.30.30 | Surface Water | Discipline Report. EM Chapter 430 Surface Water | 01EC | 3 | Deliverable
EV.30.40 | Groundwater | Discipline Report. EM Chapter 433 Groundwater | 01EG | 3 | Deliverable
EV.30.50 | Floodplain | Discipline Report. EM Chapter 432 Floodplain | 01EF | 3 | Deliverable
EV.30.60 | Wildlife, Fish & Vegetation | Discipline Report. EM Chapter 436 Fish, Wildlife & Vegetation. | 01EH | 3 | Deliverable
EV.30.70 | Wetland | Discipline Report. EM Chapter 431 Wetlands --Wetland Inventory Report --Wetland and Stream Assessment --NEPA/SEPA Mitigation Memo --Critical Area Report --Jurisdictional Ditch Memorandum --Conceptual Wetland Mitigation Plan --Draft Wetland Mitigation Plan --Final Wetland Mitigation Plan | 01EJ | 3 | Deliverable
EV.30.80 | Energy | Discipline Report. EM Chapter 440 Energy | 01EE | 3 | Deliverable
EV.30.90 | Noise | Discipline Report. EM Chapter 446 Noise Noise Analysis Report (special studies) | 01EN | 3 | Deliverable
EV.30.100 | Hazardous Materials | Discipline Report. EM Chapter 447 Hazardous Materials --Phase l Environmental Site Assessment (ISA) --Phase ll Environmental Site Assessment (PSI) --Phase lll Environmental Site | 01EM | 3 | Deliverable
EV.30.110 | Land Use | Discipline Report. EM Chapter 455 Land Use and Transportation --Farmland Conversion Package --Section 6(f) Property Conversion Package, EM Chapter 457 --Section 4(f) (Public Lands) Evaluation, EM Chapter 457 | 01EL 01ER | 3 | Deliverable
EV.30.120 | Cultural Resources | Discipline Report. EM Chapter 456 Historic, Cultural, and Archeological Resources --Cultural Resources Survey --Cultural Resources Memorandum of Agreement | 01EQ | 3 | Deliverable
EV.30.130 | Relocation Report | Discipline Report. Refer to EM 458 Social and Economic & Exhibit 458-3 Social Economic and Environmental Justice Discipline Report | 01ES | 3 | Deliverable
EV.30.140 | Transportation | Discipline Report. EM Chapter 460 Transportation | 01ET | 3 | Deliverable
EV.30.150 | Public Services & Utilities | Discipline Report. EM Chapter 470 Public Services & Utilities | 01EP | 3 | Deliverable
EV.30.160 | Visual Impacts | Discipline Report. EM Chapter 459 Visual Impacts; see also DES 140.50. | 01EV | 3 | Deliverable
EV.40 | NEPA/SEPA Compliance | National Environmental Policy Act/State Environmental Policy Act (NEPA/SEPA) If project has any federal nexus (e.g. funding, permit/approval, land) follow NEPA requirements and obtain review of proposed documentation level by FHWA or the appropriate federal transportation agency. If state only funding, follow SEPA requirements. See Environmental Procedures Manual. EM Chapter 400. Consider coordination with Interchange Justification Report and Value Engineering - if applicable. | 01N0, 01N1, 01N2, 01N3, 01N4, 01N5, 01N6 | 2 | Group
EV.40.10 | this row available for other items |  | 0138 | 3 | Deliverable
EV.40.20 | Early Coordination | Involves preparation and distribution of an Environmental Pre-Scoping Package, including a Draft Coordination Plan and Public Involvement Plan, and Agency Coordination. EM Chapter 400 |  | 3 | Deliverable
EV.40.30 | Public Notice | Public notice announcing plans to prepare an EIS or EA, including a Notice of Intent for a NEPA EIS, a Determination of Significance / EIS Scoping Notice for a SEPA EIS, or an EA Scoping Notice for a NEPA EA. EM chapter 400 |  | 3 | Deliverable
EV.40.40 | Notice of Intent (NOI) | Notice of Intent (NOI) is published in the he Federal Register to begin the NEPA EIS process. Official start date of document production. EM Chapter 400 |  | 3 | Deliverable
EV.40.50 | Determination of Significance / EIS Scoping Notice | A PE / EIS Scoping Notice is sent to Ecology for publication in the SEPA Register, and to other agencies, tribes, and others with an interest in the project. EM Chapter 400 |  | 3 | Deliverable
EV.40.60 | EIS or EA Scoping | A formal process for engaging the public and agencies in identifying the range of proposed actions, alternatives, environmental elements and impacts, and mitigation measures to be analyzed in an EIS or EA. EM Chapter 400 |  | 3 | Deliverable
EV.40.70 | Draft NEPA/SEPA Environmental Document | A formal environmental document prepared and issued for public and agency comment in accordance with the National Environmental Policy Act (NEPA) and/or State Environmental Policy Act (SEPA). EM Chapter 400. --NEPA or SEPA Draft EIS,SDEIS, or PEEIS --DEIS = Draft Environmental Impact Statement --SDEIS = Supplemental DEIS --PEIS = Programmatic Environmental Impact Statement --SEPA Checklist - Determination of Non-Significance |  | 3 | Deliverable
EV.40.80 | Public Hearing / Comments | A formal or informal hearing and/or comment period that provides the public and agencies with an opportunity to comment on the social, economical, and environmental impacts of a project. See Design Manual Chapter 210. - Environmental Hearing |  | 3 | Deliverable
EV.40.90 | Final NEPA/SEPA Environmental Decision Documents | A formal document prepared and issued to demonstrate compliance with the National Environmental Policy Act and/or State Environmental Policy Act by indicating whether a proposed action constitutes a major action significantly affecting the quality of the environment, and, if so disclosing the nature and significance of any environmental effects of a proposed action, and when preceded by a draft NEPA/SEPA document, includes any comments received on the draft NEPA/SEPA document. EM Chapter 400 --NEPA Categorical Exclusion (CE) per MOU with FHWA --NEPA Documented Categorical Exclusion (DCE) --NEPA Environmental Assessment (EA) or Revised EA --Milestone- Finding of No Significant Impact (FONSI) issued --NEPA or NEPA/SEPA Final Environmental Impact Statement (FEIS) --Milestone- Record of Decision (ROD) issued --NEPA Statute of Limitations (SOL) Notice --NEPA Re-evaluation (no action in 3 years or major scope change) --SEPA Categorical Exclusion (SEPA CE) --SEPA Checklist/Determination of Non-Significance --SEPA FEIS or Final Supplemental (FSEIS) --SEPA Adoption Notice --SEPA Notice of Action Taken (NAT) |  | 3 | Deliverable
EV.40.100 | Environmental Review Documentation Complete | Milestone-For reporting purposes, the environmental review documentation is considered complete on the date that all necessary National and State Environmental Policy Act (NEPA/SEPA) documentation has been submitted by WSDOT to the appropriate regulatory agency for approval after being processed through WSDOT Headquarters. See Project Control & Reporting Manual. EM Chapter 400 |  | 3 | Milestone
EV.50 | Environmental Permits | Identify, apply for and obtain environmental permits required for the project. Permit requirements are scoped as part of the Environmental Review Summary. See Environmental Manual Chapter 500 and associate webpages for procedures. See WSDOT Environmental Permitting website https://www.wsdot.wa.gov/Environment/Permitting/ | 0138 | 2 | Group
EV.50.05 | JARPA | The Joint Aquatic Resource Permit Application (JARPA) form used to apply for individual or multiple regulatory agency permits. The application is used for Corps 404 permits, WDFW HPAs, Ecology 401 Certifications, and several local jurisdiction permits. A completed application form along with the necessary permit drawings and attachments (e.g. NPEA/SEPA Docs, Mitigation Plans, etc.) provides agencies the information necessary for them to issue a permit. Refer to EM Chapter 500 and Directional Memo ESO-09-02.
EV.50.10 | Corps Section 404 Permit | This permit is needed for discharging, dredging, or placing fill within waters of the United States (including navigable waters, wetlands, lakes, rivers, streams, tributaries, and jurisdictional ditches). Responsible Agency: Army Corps of Engineers. For additional information see the WSDOT Permits web page: http://www.wsdot.wa.gov/Environment/Programmatic/FSLPermits.htp |  | 3 | Deliverable
EV.50.20 | Corps Section 10 Permit | This permit is needed for any work in, over, or under navigable water (e.g., rechanneling, piers, wharves, dolphins, bulkheads, buoys, etc.). Responsible Agency: Army Corps of Engineers. |  | 3 | Deliverable
EV.50.30 | Coast Guard Section 9 Permit | This permit is needed for construction or modification of a bridge or causeway across a navigable water of the U.S. (includes temporary bridges over navigable waters). Responsible Agency: Coast Guard. |  | 3 | Deliverable
EV.50.40 | Coastal Zone Management Certification | Projects that need a federal license or federal permit and occur within any of Washington's 15 coastal counties require certification from Ecology that the proposed project is consistent with the Coastal Zone Management Program. Responsible Agency: Department of Ecology. |  | 3 | Deliverable
EV.50.50 | Hydraulic Project Approval (HPA) | Hydraulic Project Approval (HPA) A permit required for projects that use, divert, obstruct, or change the natural flow or bed of waters of the state. Includes bed reconfiguration, all construction or other work water work, under and over the ordinary high water line, including dry channels, and may include projects landward of the ordinary high water line (e.g., activities outside the ordinary high water line that will directly impact fish life and habitat, falling trees into streams or lakes, bridge maintenance, dike construction, etc.) Responsible Agency: Washington State Dept. of Fish and Wildlife. |  | 3 | Deliverable
EV.50.60 | Section 402 NPDES Permit | A Clean Water Act Section 402 National Pollutant Discharge Elimination System (NPDES) permit is needed for a discharge of pollutants into waters of the U.S., including drains, ditches, wetlands, creeks, rivers, lakes, and marine waters. The NPDES permit most commonly required is a construction stormwater general permit required for any construction activity that disturbs one acre or more and may result in a discharge of stormwater to such waters. Responsible Agency: Department of Ecology. |  | 3 | Deliverable
EV.50.70 | State Waste Discharge | A State Wastewater Discharge Permit is required for a discharge of wastewater to the ground or a discharge of industrial process water to a municipal treatment plant. Responsible Agency: Department of Ecology. |  | 3 | Deliverable
EV.50.80 | Section 401 Water Quality Certification | This federal permit/license is required for projects that receive a Section 404 permit from the U.S. Army Corps of Engineers or a Coast Guard permit for activities that might result in a discharge of dredge or fill material into water or non-isolated wetlands or excavation in water or non-isolated wetlands. Responsible Agency: Department of Ecology; and the Environmental Protection Agency (EPA) on federal and tribal land, except where tribes have been delegated such authority on their tribal land. |  | 3 | Deliverable
EV.50.90 | Short-Term Water Quality Modification | Issued as a condition of the Individual Section 401 Water Quality Certification for projects that need short-term modification to the mixing zone distance for measuring water quality turbidity. Responsible Agency: Department of Ecology. |  | 3 | Deliverable
EV.50.100 | Forest Practices Permit | Permit required to remove timber or convert timber land. Responsible Agency: Department of Natural Resources. |  | 3 | Deliverable
EV.50.110 | Floodplain Development Permit | A permit for any construction activity within the 100 year flood plain as defined by FEMA mapping. Responsible Agency: Department of Ecology, Cities and Counties. |  | 3 | Deliverable
EV.50.120 | Critical Area Ordinance Permit | Local approval or permits may be required for projects impacting areas defined as "critical" by counties and cities under the Growth Management Act (GMA), including wetlands, aquifer recharge areas, wellhead protections areas, frequently flooded areas, geographically hazardous areas, fish and wildlife habitat, and conservation areas. Responsible Agency: Counties and Cities. |  | 3 | Deliverable
EV.50.130 | Air Quality Permit | This permit allows temporary air pollution above allowed levels for land clearing burns, demolition of structures containing asbestos, and operation of portable asphalt batching equipment, rock crushers, and Portland cement plants. Responsible agency: Ecology, Clean Air Agencies, fire protection agencies. |  | 3 | Deliverable
EV.50.140 | Noise Variance | Construction and maintenance activities during nighttime hours may require a variance from local noise ordinances. Daytime noise from construction is usually exempt. Responsible Agency: Counties and Cities. |  | 3 | Deliverable
EV.50.150 | Shoreline Permit/Exemption | Required for any contract requiring work within 200 feet of a shoreline of the state as defined by the local agency with jurisdiction. Responsible Agency: Department of Ecology, Cities and Counties. |  | 3 | Deliverable
EV.50.160 | Land Use Permit | Construction and maintenance activities may require a Land Use Permit in select cases. Examples include a conditional use permit, unclassified use permit, or variance. Responsible Agency: Counties and Cities. |  | 3 | Deliverable
EV.50.170 | Environmental Permit for Field Exploration | Field exploration may require permits to complete. Permits need to be provided by the Project Office to HQ Geotechnical Office/Region Materials Office to enable required field work to be started. |  | 3 | Deliverable
EV.50.180 | Clearing, Grading, & Building Permit | Construction and maintenance activities outside the roadway may require a permit under local laws and codes. Roadway construction is usually exempt. Responsible Agency: Counties and Cities. |  | 3 | Deliverable
EV.50.190 | Field Exploration Permits/Agreements/Clearances | To support the work of the Geotechnical Office (GO) and/or the Region Materials Office (RMO), a Field Exploration program may be conducted. The Field Exploration Program will include site visits by staff from the GO and RMO, and may include the drilling of subsurface borings, excavation of test pits, geophysical field tests, groundwater monitoring, pump tests, and infiltration tests. The Project Office will need obtain the permits, rights of entry, and clearances to perform this work. Permits, clearances, and agreements to be supplied by the Region might include the following: • HPA • Shoreline permits • Tribal lands and waters • Railroad easement and right of way • City, county, or local agency use permits • Sensitive area ordinance permits • Environmental and Archeological Clearances |  | 3 | Deliverable
EV.50.200 | Archaeological Resources Protection Permit | This permit is required for excavation or removal of archaeological resources from tribal or federal land. Responsible agency: Tribes and federal land owners. |  | 3 | Deliverable
EV.50.210 | Archaeological Excavation and Removal Permit | This permit is required for digging, excavating, altering, defacing, or removing archaeological objects or sites; historic archaeological resources; or native Indian graves, cairns, or painted or glyptic records. Responsible agency Washington State Department of Historic Preservation. |  | 3 | Deliverable
EV.50.220 | Tribal Approvals & Permits | All environmental permits and approvals for which tribes have been delegated authority that are not covered by another item in the MDL. EM Chapter 530 |  | 3 | Deliverable
EV.50.230 | Migratory Bird Treaty Act Evaluation | This federal law, administered by the USFWS, makes it unlawful to take, import, export, possess, sell, purchase, or barter any migratory bird, with the exception of the taking of game birds during established hunting seasons. The law also applies to feathers, eggs, nests, and products made from migratory birds. This law is of particular concern when birds nest on bridges, buildings, signs, and ferry dock structures. |  | 3 | Deliverable
EV.50.240 | Bald and Golden Eagle Protection Act Evaluation | This federal law, administered by the USFWS, makes it unlawful to take, import, export, sell, purchase, or barter any bald or golden eagle, their parts, products, nests, or eggs. "Take” includes pursuing, shooting, poisoning, wounding, killing, capturing, trapping, collecting, molesting, or disturbing the eagles. |  | 3 | Deliverable
EV.50.250 | Marine Mammal Protection Act Permit | This Federal Law, administered by NOAA, prohibits the take of marine mammals in U.S. Waters. WSDOT projects that involve marine waters; including Puget Sound, Georgia Basin and the Columbia River up to Bonneville Dam, must consider potential impacts to marine mammals. A permit may be required from NOAA for Level A harassment (injury level take) or Level B harassment (disturbance level take). There are two permit options: a Letter of Authorization (good for 5 years) or an Incidental Harassment Authorization (good for 1 year). An Endangered Species Act (ESA) consultation is required in coordination with the MMPA application to receive either permit. The application is done in report format and includes: potential project-specific impacts to marine mammals, species/numbers of marine mammals in the project area, a request for take levels, and a mitigation proposal. For additional information see EPM Chapter 436. |  | 3 | Deliverable
EV.50.260 | Miscellaneous Permits & Approvals | Examples include: Federal Aviation Administration (FAA), sole source aquifer, water use permit, etc. |  | 3 | Deliverable
EV.50.270 | Environmental Permits Received | Milestone- All environmental permits acquired for project to go to Ad/Construction. | N/R | 3 | Milestone
EV.60 | Environmental Commitment File | Identify and document all environmental commitments for the project. See Environmental Procedures Manual Chapters 490 and 590 for procedures. |  | 2 | Group
EV.60.10 | Environmental Commitments Meeting | A project-level meeting between the Design, Construction, Plans, and Environmental Offices used to incorporate commitments into contracts. |  | 3 | Deliverable
EV.60.20 | Environmental Compliance Notes Finalized | Milestone - All Environmental Compliance Notes are finalized and entered into the Commitment Tracking System. The Commitment Tracking System is a WSDOT database that allows you to store commitments in a secure computer network server, plus manage the responsibility (WSDOT or contractor) and implementation method (guidance document or contract) for the commitment. It also allows you to store compliance records, document the status, and report details about commitments from their inception through project delivery and on to maintenance. |  | 3 | Milestone
EV.60.30 | Environmental Commitments List (Design Build Only) | A project-specific list of environmental commitments prepared by WSDOT for inclusion in the Request for Proposal (RFP). The Environmental Commitment List includes all of the known or anticipated environmental commitments for which the Design-Builder will be responsible for fulfilling. |  | 3 | Deliverable

## DB
Code | Title | Description | work op | level | level description
DB | Design-Build Procurement | The process resulting in an executed contract that represents the best value to the public. All work involved in the solicitation for interest, preparation and distribution of the RFP package, including the request for qualifications (RFQ), evaluation criteria, selection procedures and technical requirements for the design and construction. (Note: Review Contract Ad & Award and Construction Milestones for additional Design Build Reporting Milestones.) | 0190 | 1 | Process
DB.100 | Design-Build Contract Package | The document package issued by WSDOT requesting submittal of proposals for the Project and providing information relevant to the preparation and submittal of proposals, including Instructions to Proposers, Contract Documents and Reference Documents. |  | 2 | Group
DB.100.10 | Request For Proposal Chapter & Appendix | DESIGN-BUILD - WSDOT Design office will request specialty group provide RFP criteria for the Chapter 1 Proposal. This may also include an Appendix referenced in the RFP, the term Appendix (Appendices) refers to the documents listed in Appendix A1 of the Technical Requirements. |  |  | Deliverable
DB.100.20 | Conceptual Plans | Conceptual Plans: Conceptual plans are developed to the point that we have enough information to gain environmental approval, acquire permits, acquire right of way, and to demonstrate that our contract requirements are feasible. Typically to 15-30%, but can be more or less depending on the project scope/discipline. Each discipline may be developed to a different level. Basic Configuration needs to be defined in this process. |  | 3 | Deliverable
DB.100.30 | Basic Configuration | The Basic Configuration are the elements of the Conceptual Plans which the Design-Builder may rely on. These elements may be modified by Pre-Approved Design Variances/Analyses or Alternative Technical Concepts (ATC’s). |  | 3 | Deliverable
DB.100.40 | Reference Documents | The non-binding reference documents included in the Request for Proposal. These documents are provided for information purposes to assist the Proposers in preparing their Proposals, but the Reference Documents do not represent requirements binding on the Design-Builder. |  | 3 | Deliverable
DB.100.50 | Contract Documents | Design Build Contract Documents include: -- Request for Qualifications (RFQ) -- Request for Proposal (RFP): Containing Instruction to Proposers (ITP), Contract Form, General Provisions (Ch. 1), Technical Requirements (Ch. 2) and Appendices |  | 3 | Deliverable
DB.200 | Statement of Qualification Phase | WSDOT will use a two-step procurement process to select a design-build contractor (Design-Builder) to deliver the Project. The issuance of this RFQ is part of the first step to solicit information from potential design-builders in the form of SOQs. WSDOT will evaluate and score submitted SOQs to determine which Submitters are the most highly qualified to deliver the Project. WSDOT will short-list three to five of the most highly qualified Submitters to advance to the second step in the procurement for the Proposal Phase. |  | 2 | Group
DB0.200.10 | Request For Qualifications (RFQ) Preparation | The Request For Qualifications (RFQ) is a document asking interested proposing teams to submit a Statement of Qualifications (SOQ). The RFQ gives a general description of the project and the attributes desired of prospective proposers. It provides specific terms for the submittal of the SOQ and how it will be scored. |  | 3 | Deliverable
DB0.200.20 | RFQ Issue Date | Milestone - Date the RFQ is issued by WSDOT. |  | 3 | Milestone
DBO.200.30 | this row available for other items |  |  | 3 | Milestone
DB0.200.40 | Voluntary Submitter's Meeting | WSDOT will hold an informational meeting for potential Submitters regarding the SOQ. |  | 3 | Deliverable
DB0.200.50 | Deadline for submitting RFQ questions | Milestone - Design Builder teams submit formal questions for answers from WSDOT. |  | 3 | Milestone
DB0.200.60 | Deadline for WSDOT response to RFQ questions | Milestone - WSDOT supplies formal answers to questions |  | 3 | Milestone
DB0.200.70 | SOQ Due Date | Milestone - The date the Statement of Qualifications (SOQ) is due to WSDOT. |  | 3 | Milestone
DB0.200.80 | Evaluate Statement of Qualifications (SOQ) | Design Builders are scored on their qualifications and experience of Key Personnel and the Major Participants against the project goals. Major Participants include the Prime and subs doing 20% or more of the work; Key Personnel are people filling identified positions (Project Manager, Design Manager, Construction Manager). Key part of the process is reference checks, relies on candid, specific and objective responses from PE’s and EMs. WSDOT evaluates the SOQ based on criteria included in RFQ and the Evaluation Manual. The Evaluation Manual is created by the project team based on the requirements of the RFQ and guides the evaluation team. The Team evaluates the SOQ’s and provides a score. |  | 3 | Deliverable
DB0.200.90 | Shortlist Bidders Selected | Milestone - The date the shortlist of selected bidders is issued; these bidders may submit a proposal in response to the subsequent RFP. This is the result of the review of the SOQ documents submitted by prospective proposers. |  | 3 | Milestone
DB.300 | Proposal Phase | WSDOT will issue a Request for Proposal (RFP) for the Project to the short-list Submitters (Proposers). The Request for Proposal requires Proposers to address how they plan to deliver the project (Specific Approach). WSDOT may award a Design Build Contract for the Project to the Proposer offering the apparent best value, to be determined as described in the RFP. |  | 2 | Group
DB.300.10 | Request For Proposal (RFP) preparation | The final Request for Proposals document is the official notice to interested proposing teams to prepare and submit proposals, with the project's technical criteria and requirements. The issuance of the RFP is considered the Advertisement of the contract - see that Performance Reporting Major Milestone. |  | 3 | Deliverable
DB.300.20 | Issue RFP | Milestone - The date the Request for Proposals (RFP) is issued or circulated. |  | 3 | Milestone
DB.300.30 | Voluntary Proposer's Meeting | WSDOT will hold an informational meeting for proposer's regarding the RFP. |  | 3 | Deliverable
DB.300.40 | Alternate Technical Concept Submittal Deadline | Milestone - Alternative Technical Concept (ATC) – Concepts proposed by the Design-Builder and approved by WSDOT pursuant to the Instructions to Proposers, which modify the Basic Configuration or other Contract requirements. WSDOT may approve changes to the contract that are determined to be “Equal or Better” to the RFP. |  | 3 | Milestone
DB.300.50 | Deadline for Submitting Proposers’ questions | Milestone - Design Builder teams submit formal questions for answers from WSDOT. |  | 3 | Milestone
DB.300.60 | Deadline for WSDOT response to Proposers’ questions | Milestone - WSDOT supplies formal answers to questions |  | 3 | Milestone
DB.300.70 | Proposals Due Date | Milestone - The date specified for the delivery of the Proposals in the Instructions to Proposers. Proposals include the technical proposal and the price proposal which is sealed until bid opening. |  | 3 | Milestone
DB.300.80 | Request For Proposal (RFP) Evaluation | A systematic evaluation and scoring of the technical portions of the proposals. Teams of Advisors review specific sections of the proposals in accordance with the terms of the RFP and ITP and make comments and assign score values. They report to the Evaluators who compile and finalize the technical score for each of the proposals. This activity begins on the Proposal Due Date. |  | 3 | Deliverable
DB.300.90 | Best Value Determination | Milestone - The date of the bid opening for DB Proposals. The DB Price proposals are opened, then combined with the technical score to yield a net or best value. Generally, the technical score is subtracted from the price of qualified proposals to arrive at the net value. An Apparent Best Value proposer is announced at this point. |  | 3 | Milestone
DB.300.100 | Region Betterments Supplied | Betterments – With respect to the Technical Proposal, any item included in the Design-Builder’s Technical Proposal that clarifies the Design-Builder’s intention to exceed a requirement included in the Contract Documents. The project is awarded after we the Region provides a list of betterments and funding approval proposal amount from ABV. A betterment is something that contractor commits to in the Technical Proposal that exceeds the contract requirements. |  | 3 | Deliverable
DB.300.110 | Notice to Proceed Issued (NTP) | Milestone - The written authorization issued by WSDOT that permits the Design-Builder to commence performance of the Work. |  | 3 | Milestone

## PSE
Code | Title | Description | work op | level | level description
PSE | Plans, Specifications and Estimates | Development of the Contract Plans, specifications and estimate for bid letting (parent or summary activity). |  | 1 | Process
PSE.10 | Contract Plan Sheets Preparation | Development of the Contract Plan sheets. See Plans Preparation Manual (PPM) M22-31 for full list of Plans and sequence. This task may be used as a hammock task for uniform resource loading the effort involved with contract plan preparation. This task is used when the plan sheet deliverables are constrained by other activities or dates and are not resource loaded. When used, this task will have no constraints, in order to have the task span the entire duration of plan preparation (parent or summary activity). | 178 | 2 | Group
PSE.10.10 | Index | Required on all projects with 30 plan sheets or more, see Plans Preparation Manual (PPM) 400.06 and 400.06(3) |  | 3 | Deliverable
PSE.10.20 | Vicinity Map | A plan sheet that is required for all projects to show the approximate location of the project on the state route, see Plans Preparation Manual (PPM) 400.06 |  | 3 | Deliverable
PSE.10.30 | Summary of Quantities | These plans are a complete tabulation of all bid items and pay quantities required for the project, see Plans Preparation Manual (PPM) 400.06 |  | 3 | Deliverable
PSE.10.40 | Reclamation Plans | Plans that are required on all WSDOT projects that contain a WSDOT furnished material source, including borrow, pit, quarry, stockpile, waste site, and reclamation plans. See Plans Preparation Manual (PPM) 700.05(34); 400.06(6) |  | 3 | Deliverable
PSE.10.50 | Roadway Section Plans | Plans that show the geometric roadway cross section from subgrade up to finished grade, see Plans Preparation Manual (PPM) 400.06(7) |  | 3 | Deliverable
PSE.10.60 | Grading Section Plans | Plans that show finished ground contours, see Plans Preparation Manual (PPM) 400.06(8) |  | 3 | Deliverable
PSE.10.70 | Stage Construction Plans | These plans show the different stages required to construct the project. See Plans Preparation Manual (PPM) 400.06 |  | 3 | Deliverable
PSE.10.80 | Alignment / Right of Way Plans | Plans that contain horizontal alignment & R/W information, see Plans Preparation Manual (PPM) 400.06(10) |  | 3 | Deliverable
PSE.10.90 | Quantity Tabs | Plans that tabulate quantities and identifies locations and notes pertaining to specific bid items, see Plans Preparation Manual (PPM) 400.06(9); Appendix 1 |  | 3 | Deliverable
PSE.10.100 | Site Preparation Plans | These plans show existing topography, removal & demolition work, see Plans Preparation Manual (PPM) 400.06(11) |  | 3 | Deliverable
PSE.10.110 | Existing Utilities Plan | This is an extension of the Site Preparation Plan and is only required if the existing utilities are so extensive that they cannot be clearly shown of the site preparation plans. See Plans Preparation Manual (PPM) 400.06(16) |  | 3 | Deliverable
PSE.10.120 | Environmental and/or Wetland Mitigation Plans | A plan sheet that identifies wetland mitigation. See Plans Preparation Manual (PPM) 400.06(19) |  | 3 | Deliverable
PSE.10.130 | Roadway Profiles | Plans that identify a change in the vertical alignment of the roadway, see Plans Preparation Manual (PPM) 400.06(12) |  | 3 | Deliverable
PSE.10.140 | TESC Plans | Temporary Erosion and Sediment Control plans are required if the project involves land disturbance. To include Q-tabs, Plan sheets, and Details. see Plans Preparation Manual (PPM) 700.05(30); 400.06 |  | 3 | Deliverable
PSE.10.150 | Drainage Plans | Plans that show how the drainage system relates to the rest of the project, including Drainage Structure Notes, Drainage Profiles, and Drainage Details. See Plans Preparation Manual (PPM) 400.06(14)(15)(16) |  | 3 | Deliverable
PSE.10.160 | Landscape & Roadside Restoration | Plans that identify Wetland Mitigation Plans, Wetland Mitigation/Landscape Plan Sheet.
PSE.10.170 | Utility Plans | Plans that are required when there is work on existing utilities as part of the contract, to include Utility Structure Notes and utility details. See Plans Preparation Manual (PPM) 400.06 |  | 3 | Deliverable
PSE.10.180 | Interchange Contours | Plan sheets showing the contour grading of interchanges. See Plans Preparation Manual (PPM) 400.06(17) |  | 3 | Deliverable
PSE.10.190 | Paving Plans | Plans that show total roadway widths to be paved, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06(18) |  | 3 | Deliverable
PSE.10.200 | Pavement Marking Plans | Plans that show the type and location of pavement markings for the project, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06(18) |  | 3 | Deliverable
PSE.10.210 | Minor Structures Plans | Plans that show the information required to construct retaining walls, etc. Includes Q-tabs, profiles, and details. See Plans Preparation Manual (PPM) 400.06(21) |  | 3 | Deliverable
PSE.20 | Contract Specifications Development | Development of Contract Provisions. See Plans Preparation Manual (PPM). | Multiple | 2 | Group
PSE.20.10 | Contract Specifications | Development of Contract Provisions, Amendments, General Special Provisions, and appendices. See Plans Preparation Manual (PPM) Division 6. | 179 | 3 | Deliverable
PSE.20.20 | Summary of Geotechnical Conditions | HQ Geotechnical and/or Region Materials prepares summary of geotechnical conditions for inclusion into the PS&E as Appendix B. The Summary is prepared as part of the PS&E Review. | 141 | 3 | Deliverable
PSE.30 | Construction Estimate Development | Development of Contract Estimates for costs and time. See Plans Preparation Manual (PPM). | 01A0 | 2 | Group
PSE.30.10 | Basis of Estimate (BOE) | The BOE is characterized as the one deliverable that defines the scope of the project, and ultimately becomes the basis for change management. When the BOE is prepared correctly, our customers can use it to understand and assess the estimate, independent of any other supporting documentation. A well-written BOE achieves these goals by clearly and concisely stating the purpose of the prepared estimate (i.e., cost study, project options, benefit/cost study, funding, etc.), the project scope, pricing basis, allowances, assumptions, exclusions, cost risks and opportunities, and any deviations from standard practices. The BOE is a documented record of pertinent communications that have occurred and agreements that have been made between the estimator and other project stakeholders. | 01AP | 3 | Deliverable
PSE.30.20 | Engineer's Cost Estimate of Construction | An estimate used to initiate funds for the construction activity and to evaluate the contractor's bids, see Plans Preparation Manual (PPM) Division 8. See also DM Chapter 300 | 01AC | 3 | Deliverable
PSE.30.30 | Lump Sum Breakout | Calculations for determining estimate of Lump Sum items. | 01AC | 3 | Deliverable
PSE.30.40 | Working Day Estimate | Contract time determined in accordance with Plans Preparation Manual (PPM) Appendix A6 | 01AC | 3 | Deliverable
PSE.40 | Construction Permits | Development and documentation of permits from other public agencies for work to be done outside of WSDOT right of way and within other public agency right of way. | 182 | 2 | Group
PSE.40.10 | Construction Permits | Construction Permits accommodate WSDOT activities on public owned right of way. See Design Manual, Chapter 510. |  | 3 | Deliverable
PSE.40.20 | Aquatic Lands Use Authorization | For projects involving aquatic lands contact Real Estate Services. Responsible Agency: Department of Natural Resources. |  | 3 | Deliverable
PSE.40.30 | Authorization for use of federal land | This permit is required for construction of roads, utility lines, and associated uses, such as staging areas for construction or borrow pits, on federal lands. Responsible agency: USFS and BLM. |  | 3 | Deliverable
PSE.40.40 | Haul Road and Detour Agreement | When the project provides a materials source, or requires traffic to be detoured from the state highway, the region is required to acquire agreements with the owners of the roads (usually cities or counties) that will be used as the haul route or the detour route. See Plans Preparation Manual (PPM) 700.05(14) |  | 3 | Deliverable
PSE.40.50 | Turnback Agreement | Areas for relinquishment are areas that the state acquires for the improvement or construction of roads that will not remain a part of the highway system. See Plans Preparation Manual (PPM) 100.03 |  | 3 | Deliverable
PSE.50 | Constructability Reviews | To develop a quality project, WSDOT uses a series of reviews at predetermined stages of project development. These reviews, called constructability reviews, attempt to ensure that: project development process is on schedule; project definition and estimates are correct; project is buildable; project is maintainable; and project documents are biddable. | 180 | 2 | Group
PSE.50.10 | Scoping Phase Review | Scoping Phase Review. See Deliverable Expectation Matrix & Project Management Guide https://wsdot.wa.gov/engineering-standards/project-management-training/project-management/project-management-guide |  | 3 | Deliverable
PSE.50.20 | 0% Constructability Review - transitional/design | Transitional / Design Re-Start Review; interdisciplinary.. See Deliverable Expectation Matrix & Project Management Guide (PMG) https://wsdot.wa.gov/engineering-standards/project-management-training/project-management/project-management-guide |  | 3 | Deliverable
PSE.50.30 | 30% Constructability Review - geometric | Geometric Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) https://wsdot.wa.gov/engineering-standards/project-management-training/project-management/project-management-guide |  | 3 | Deliverable
PSE.50.40 | 60% Constructability Review - general plans | General Plans Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) https://wsdot.wa.gov/engineering-standards/project-management-training/project-management/project-management-guide |  | 3 | Deliverable
PSE.50.50 | 90% Constructability Review - contract plans | Contract Plans Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) https://wsdot.wa.gov/engineering-standards/project-management-training/project-management/project-management-guide |  | 3 | Deliverable
PSE.60 | PS&E Reviews | Plans Specifications & Estimate (PS&E) Reviews. Check for completeness and compatibility between the Plans, Specifications and Estimate. See Deliverable Expectation Matrix/ Project Management Guide | 181 | 2 | Group
PSE.60.10 | Local Agency Review | A check of the plans, specification and estimate by a local governmental or non-governmental agency or tribal nation to ensure compliance with established agreements or memorandum of understandings. |  | 3 | Deliverable
PSE.60.20 | Region PS&E Review | Region Project Office submits PS&E package to Region for review. Includes -- State Materials Justification/Approval -- Proprietary Item Approval |  | 3 | Deliverable
PSE.60.30 | Final Contract Review | This review (sometimes referred to as a Round Table review) should be scheduled by the PEO when the project is either large, complex with multiple staging, unique construction methods or a shortened PS&E Review period. The review should follow the comments due date within a few work days. The PEO leads the discussion of review comments and maintains the focus of the meeting. The focus of the discussion should be constructability, significant review comments, and the concerns of the Construction PE. As time allows other issues should be discussed. Comments and concerns should be resolved during the discussion; otherwise, key players should be identified to resolve specific issues outside of the round table meeting. |  | 3 | Deliverable
PSE.60.40 | Final Signed PS&E to Region | Milestone - Project Manager returns stamped and signed AD ready PS&E package to the Region. |  | 3 | Milestone
PSE.60.50 | Ad Package to Headquarters | Milestone - Final PS&E to HQ with all appropriate attachments as required on the Final Check Sheet, five(5) days prior to the scheduled Ad date. |  | 2 | Milestone
PSE.70 | Project Shelf | Completion milestones and documentation for projects not funded for construction. Re-start milestones for projects coming off the shelf for advertisement. | 0187 | 2 | Group
PSE.70.10 | Incomplete Project to Shelf | Milestone - The date that an incomplete project goes to a holding area (called "the shelf"). This project is not ready for advertisement and will need to undergo further design/adjustments and reviews. |  | 3 | Milestone
PSE.70.20 | AD Ready Project to Shelf | Milestone - The date that a fully designed, reviewed and permitted project goes to a holding area called "the shelf". This project is ready for advertisement without any further adjustments or reviews |  | 3 | Milestone
PSE.70.30 | Shelf to AD Ready | Milestone - Date project is taken off shelf. |  | 3 | Deliverable
PSE.70.40 | Shelf/Ad Ready Letter | A Memo from the Project Engineer to the Assistant Region Administrator for Project Development to formally suspend work on a project until a later date. |  | 3 | Deliverable
PSE.70.50 | Estimate to Make AD Ready | Estimate of scope, time, and cost to get an incomplete, "shelved", project ready for advertisement |  | 2 | Deliverable
PSE.80 | Contract Ad & Award | Advertisement and award of construction contracts. See Ad and Award Manual. | Multiple | 2 | Group
PSE.80.10 | Contracts & Legal | The Ferry Vessels Projects delivered to C&L for review and AD Specification, Contract drawings, and other documents provided to C&L for publishing in Bid Package | 189 | 3 | Deliverable
PSE.80.20 | Pre-AD Review | HQ review of pre-PS&E documents and the PS&E within various HQ units. Includes performance of the plans-in-hand inspection with FHWA, preparation of data for securing federal funds for the subsequent approval to expend those funds for a project. | 185 | 3 | Milestone
PSE.80.30 | Construction Funding Approval | Milestone - Official approval from HQ and FHWA (if federal funds are used) to move ahead with the advertisement of the construction phase of a project |  | 3 | Deliverable
PSE.80.35 | Construction Specifications Approved | Milestone - Final approval from HQ of specifications for advertisement of the construction phase of a project |  | 3 | Milestone
PSE.80.40 | Printing | Reproduction and distribution of plans, specifications, and bid proposal package. Contact HQ Printing Services for information. | 189 | 3 | Deliverable
PSE.80.50 | Project Geotechnical Documentation Package | Printing of pertinent geotechnical reports for sale to prospective bidders. Prepared by HQ Geotechnical and/or Region Materials and printed by HQ Printing Services. | 143 | 3 | Milestone
PSE.80.60 | Advertisement (AD Date) | PERFORMANCE REPORTING MAJOR Milestone- This is the date that WSDOT publicly solicits bids from contractors to construct the project. When a project is advertised, it has a completed set of plans and specifications, along with a construction cost estimate. The Milestone is met on the date of the advertisement. (Note: For Design-Build, the RFP date is reported as the AD date) |  | 3 | Deliverable
PSE.80.70 | Addenda | Work associated with preparing addendums to our construction contracts that are on advertisement. | 199 | 3 | Deliverable
PSE.80.80 | Construction Phase Preparation | Work performed during the bid period to prepare for construction including setting project files, sending notifications and RFI from contractors. | 198 | 3 | Milestone
PSE.80.90 | Addenda Deadline | Milestone - Date addenda are due in headquarters. 14 calendar days prior to the scheduled bid opening. |  | 3 | Milestone
PSE.80.100 | Bid Opening | Milestone - Public opening and reading of sealed bids. (Note: For Design-Build projects, this is reported as the selection date or Best Value Determination.) |  | 3 | Milestone
PSE.80.110 | Award | Milestone - Official notice of award of the contract to the successful bidder. (For Design-Build projects, this is reported as the Contract Award date.) |  | 3 | Deliverable
PSE.80.120 | Phase Transition & Close | Design to Construction/ Transition . The processes performed to formally terminate all activities of a project or phase, and transfer the completed product to the next phase, normally Construction. See Design Manual Chapter 300. --Plan and Document Archive -Incorporating contract special provisions and plans into the Regional Plan and Document Archive database for historical documentation and data preservation. --Computer Aided Engineering (CAE) Archive - Incorporating electronic engineering files and CAD files into the Computer Aided Engineering (CAE) database. | 01Z0 | 3 | Milestone
PSE.80.130 | PE Phase End | Milestone - All PE costs are finished and the work order is closed in TRAINS |  |  | Deliverable

## RES
Code | Title | Description | work op | level | level description
RES | Real Estate Services | The Real Estate Services phase of the project contains all work to acquire rights of way and perform and coordinate all real estate transactions for the department. The process of securing the property or property rights or agreements needed for highway improvements that conforms with Federal and State regulations called the Uniform Act. It includes, but is not limited to fee acquisition, access rights, and easements. This includes the General Project Management, RW Project Management Plan and Consultant Selection/Agreements. | 0201, 0206, 0208 | 1 | Group
RES.10 | Appraisal/Administrative Offer Summary | The appraisal of parcels and the administration of real property appraisal functions including contracting fee appraisers. An analysis of real estate market used to estimate the Fair Market Value of the real property and the damages to the remaining property. | 0222 | 2 | Deliverable
RES.20 | Review & Determination of Value (DV) | Appraisal Review checks the accuracy of the appraisal data and the soundness of the appraisers reasoning then writes a Determination of Value (DV) which is the amount of money (Just Compensation) to be offered to the property owner for the property needed for the highway project. | 0224 | 2 | Deliverable
RES.30 | Acquisition | The negotiation with property owners, government agencies or railroads for acquisition of property. Also includes development of legal descriptions for real property or property rights to be acquired, time spent conducting title reviews and title searches, clearing encumbrances and maintenance of acquisition status data (via IRIS). | 0220, 0221, 0224, 0225 | 2 | Deliverable
RES.40 | Relocation/Relocation Review Board and/or Adjudicative Hearings | The work required to prepare for and provide relocation assistance for eligible parties. The Adjudicative Hearing and/or Relocation Review Board decisions documents. | 0240/0241 | 2 | Deliverable
RES.50 | Property Management | The maintenance and management of the inventory of department-owned properties. The preparation of rental agreements or leases on department-owned property, and maintenance of rental property. Sales of properties no longer needed for transportation purposes. Demolition of property improvements no longer needed for transportation purposes. | 0210, 0211, 0212, 0213 | 2 | Deliverable
RES.60 | Condemnation/Possession & Use | A judicial process to acquire property where the state has been unable to reach a settlement through negotiation. This is handled by the office of the Attorney General. A regional or judicial formal document that grants the State the ability to possess and use the property in its construction project prior to the condemnation trial. | 0230 | 2 | Deliverable
RES.70 | R/W Certification | A statement certifying that all right-of-way clearance, including relocation assistance, has been completed or that all necessary arrangements have been made for it to be undertaken and completed as required for proper coordination with the physical construction schedule. The purpose of this certification is to inform the contractor of the status of right-of-way clearance and to certify that the requirements of the Uniform Act have been met on federally-funded projects. --R/W Recertification PERFORMANCE REPORTING MAJOR Milestone- The Milestone has been met on the date the Right of Way Certification is signed by the region Real Estate Services Manager on state funds only projects, or upon approval of FHWA on a project with federal funds. For Design-Build a minimum of right of way certification 3 is often necessary before going out to RFP. See Right of Way Manual M26-01 Chapter 17. | 0201 | 2 | Deliverable

## CN
Code | Title | Description | work op | level | level description
CN | Construction | For description of Construction Work see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm and Standard Specifications http://www.wsdot.wa.gov/Publications/Manuals/M41-10.htm |  | 1 | Process
CN.01 | Construction Engineering | Construction Engineering - Group Category 03 in the Work Order | Multiple | 2 | Group
CN.01.10 | Survey and Base Map | See Survey Manual for description of work http://www.wsdot.wa.gov/Publications/Manuals/M22-97.htm | 0310/0311/0312 | 3 | Deliverable
CN.01.20 | Design-Build Oversight | All work involved in the oversight of work plans, over-the-shoulder reviews, formally submitted reviews, task force meetings, design QV/QC/QA, deviations, and engineering decisions. It also includes work involved in the oversight of the project environmental review and compliance to commitments, permits, and approvals on Design-Build contracts. Does not include work on environmental documents, permits, and approvals done prior to award of the Design-build contract. Utilities oversight involves all work associated with identifying the location of utilities and determining relocation and/or adjustments and protection of facilities. This includes work to prepare and administer utility agreements on Design-Build contracts. Granting permission to the Design-Builder to enter and do work on right-of way owned by WSDOT at the time of entry. Monitoring the Design-Builder’s compliance with all applicable provisions of the contract and further conditions identified in any right-of-way, easements or right of entry onto property and their activities within. Assisting the Design-Builder in obtaining temporary construction easements. Does not include work involved in the review and approval of the right-of-way plan. Construction oversight and management on Design-Build contracts, of all project construction activities, control of materials, audit, inspection and testing, construction safety, and all other construction-related functions. | 0305/0307/0308/0313/0314,0323/0324/0325/0335/0336/0337/03SB | 3 | Deliverable
CN.01.30 | Inspection | All inspection necessary to ensure conformance of workmanship, methods, and procedures. For Inspection description see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm Inspection: General, Earthwork, Drainage, Surface and Paving, Structures, Environmental and Scale Operations. | 0330/0331/0332/0333/0334/0350 | 3 | Deliverable
CN.01.40 | Testing | For material Testing see Construction Manual for requirements and frequency http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm (Structures, Earthwork, Surface and Paving, Drainage, Miscellaneous) and Materials Manual for test procedures http://www.wsdot.wa.gov/Publications/Manuals/M46-01.htm --Stormwater BMP Maintenance Plan --Earthwork, Surface and Paving, Drainage, Miscellaneous --Structures | 0340/0341 | 3 | Deliverable
CN.01.50 | Contract Administration & Documentation | For Contract Administration and Documentation, see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm Contract Administration and Documentation includes these items at a minimum. --Working Drawings, Plan Checking, Data Preparation --Progress and Final Estimates and Records --Preparation of Change Order --Field Measurement - Progress and Final Estimates and Records --Equal Employment Opportunity and Minority Business Enterprise --Force Account Documentation --Agreements Management --Materials Approval and Acceptance | 0305/0309/0320/0321/0322/0351/0352/0361/0362 | 3 | Deliverable
CN.02 | Construction Milestones | Milestones for Construction phase of the project, for Project Control and Reporting, for the Construction Contract Information System (CCIS), and other purposes. Other project specific milestones can be added per project needs. |  | 2 | Group
CN.02.10 | Contract Execution | Milestone - Project Control & Reporting (PC&R) Milestone, CPMS, and CCIS milestone. This is the date when the Department signs the actual contract with the contractor. This typically occurs within 21 days following contract award. See 1-03.3 of the Standard Specifications for further detail. |  | 3 | Milestone
CN.02.20 | Construction Work Start | Milestone - This is the date when work actually starts on building the project and activity might be seen on the site. See 1-08.5 of the Standard Specifications and contract special provisions for further details. |  | 3 | Milestone
CN.02.30 | Operationally Complete | PERFORMANCE REPORTING MAJOR MILESTONE- This is the date when the public has free and unobstructed use of the facility. In some cases, the facility will be open, but minor work items may remain to be completed. See Section 1-01.3 of the Standard Specifications for further details on substantial completion. For example, a paving project would be considered Operationally Complete when the final lift is laid and the final striping is applied. Judgment must be used in determining the date the Milestone is accomplished, such as when a formal ribbon cutting celebration occurs or the delay of minor work items prevent the actual substantial completion, but the public actually has use of the completed roadway. |  | 3 | Milestone
CN.02.40 | Substantial Completion | Milestone - CCIS milestone. The Substantial Completion date is the day the Engineer determines the Contracting Agency has full and unrestricted use and benefit of the facilities, both from the operational and safety standpoint, all the initial plantings are completed and only minor incidental work, replacement of temporary substitute facilities, plant establishment periods, or correction or repair remains for the Physical Completion of the total Contract. See 1-08.5 and 1-08.9 of the Standard Specifications for further detail. |  | 3 | Milestone
CN.02.50 | Physical Completion | Milestone - CCIS milestone. The Physical Completion date is the day all of the Work is physically completed on the project. All documentation required by the Contract and required by law does not necessarily need to be furnished by the Contractor by this date. See 1-08.5 of the Standard Specifications for further detail. |  | 3 | Milestone
CN.02.60 | Completion | Milestone - Project Control & Reporting (PC&R) Milestone, CPMS, and CCIS milestone. The Completion date is the day all the Work specified in the Contract is completed and all the obligations of the Contractor under the Contract are fulfilled by the Contractor. All documentation required by the Contract and required by law must be furnished by the Contractor before establishment of this date. See 1-08.5 of the Standard Specifications for further detail. |  | 3 | Milestone
CN.02.70 | CN Phase End | Milestone - All CN costs are finished and the work order is closed in TRAINS |  | 3 | Milestone

## How to Use
Purpose - provide an organized and consistent list of wsdot milestones and deliverables. Approach is in accordance with Project Management Institute Project Management Body of Knowledge (PMBOK) most recent edition.
LEVEL 1 Process - actions or steps taken to achieve an objective; (contrast with phase which is a distinct period of development or funding, for example PE, RW, CN).
LEVEL 2 Group - identifies specialty groups or major element of work that will achieve milestones and produce deliverables.
LEVEL 3 Milestones & Deliverables - a milestone marks a major point in a timeline and serves as a reference point for major project decisions or events; a deliverable is a product or service - a project may contain multiple deliverables. LEVEL 4 and Below - Activities or groupings that are added and defined by the user, team or region. Deliverables Examples: Basis of Design (signed and approved); Design Approval; Environmental Documentation Complete; Project Development Approval; Right of Way Certification. Milestones Examples: Ad Date, Construction Start, Issue RFP
HOW TO USE - carefully review the groups, delete those not needed for your project. Those that remain comprise the initial work breakdown structure for the project. For each group in your project review the deliverables (3rd level) to ascertain those needed for your project. MDL tabs are organized by significant work processes, they may be arranged or combined in any fashion to represent the project delivery process. For example community engagement efforts may take place in scoping, design and construction on a project. Users of this tool should use it in the manner that works best for the project.
Figure 1 - Example

## Crosswalk
Code | Title | Description | Action | 2011 MDL Code | 2011 MDL Name
PM | Project Management | See Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PM | Project Management & Overhead - Preliminary Engineering
PM.01 | Project Management Plan Development & Maintenance | The Project Management Plan describes both the Project Performance Baseline for the project deliverables and the schedule and budget/cost plans for delivering them, and the Project Management Methods that will be used by the Project Team during their delivery. This item is for such work as is charged to the PE/RW/CN phases. See Project Management Guide (PMG) for details. http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PM.03 | Project Management Plan Development & Maintenance
PM.01.10 | Work Order Authorized | This marks the start of the project process. It is usually considered accomplished when the PE Work Order is authorized by Region Program Management. It can be used for any Work Order Phase PE/RW/CN. Can align with the Begin Preliminary Engineering CPDM milestone. |  | PE.PM.01 | Begin Preliminary Engineering
PM.01.20 | Project Kick Off | The purpose of the kickoff meeting is to formally notify all team members and stakeholders that the project has begun and make sure everyone has a common understanding of the project and their roles. Like all formal meetings, there should be an agenda, a preparation packet, and a team charter. Deliverable is called Pre-Construction meeting in the CN Phase. | Added
PM.01.30 | WSDOT Project Management Plan (PMP) | Describes project performance Baseline and deliverables: schedule and budget/cost plans internal scope of work marketing plan |  | PE.PM.03.04 | WSDOT Project Management Plan (PMP)
PM.01.35 | DBE/WBE Goal requirements determined | During development of the Project Management Plan identify I the project schedule when DBE/WBE goal requirements will be determined. | Added
PM.01.40 | Internal Scope Of Work Agreement | This process applies to the development of preconstruction and construction internal scope of work agreements between the Project Team and Specialty Groups within WSDOT. This process is a complement to the Internal Scope of Work Agreement Development Process Map. Reference PMRS Procedure documents Internal SOW Agreement Development, Internal SOW Agreement Management, Internal SOW Agreement Change Management. |  | PE.PM.03.05 | Internal SOW Agreement
|  |  | Deleted | PE.PM.03.06 | PMP Endorsement
PM.01.50 | FHWA Project Management Plan | The 2005 surface transportation act, the "Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users" (SAFETEA-LU) (Pub.L. 109-59, 119 Stat. 1144) increased requirements for Project Management Plans and Annual Financial Plans on major projects. The general requirements are contained in section 1904(a) of SAFETEA-LU, while the guidance and standards from the FHWA are at this web site: http://www.fhwa.dot.gov/programadmin/mega/ Any project with an estimated total cost of $500 million or more shall complete a project management plan. The PMP shall document "the procedures and processes that are in effect to provide timely information to the project decision makers to effectively manage the scope, costs, schedules, and quality of, and the Federal requirements applicable to, the project; and "the role of the agency leadership and management team in the delivery of the project." |  | PE.PM.03.03 | FHWA Project Management Plan
PM.01.60 | FHWA Finance Plan | The 2005 surface transportation act, the "Safe, Accountable, Flexible, Efficient Transportation Equity Act: A Legacy for Users" (SAFETEA-LU) (Pub.L. 109-59, 119 Stat. 1144) increased requirements for Project Management Plans and Annual Financial Plans on major projects. The general requirements are contained in section 1904(a) of SAFETEA-LU, while the guidance and standards from the FHWA are at this web site: http://www.fhwa.dot.gov/programadmin/mega/ The SAFETEA-LU changed the criteria for classification as a Major Project to an estimated total cost of $500 million or greater. and requires recipients of funds for a project with an estimated total cost from $100 million to $500 million to prepare an annual financial plan. A Financial Plan shall “be based on detailed estimates of the cost to complete the project and provide for the annual submission of updates to the Secretary that are based on reasonable assumptions, as determined by the Secretary, of future increases in the cost to complete the project. |  | PE.PM.04 | FHWA Finance Plan
PM.02 | Consultant Administration | The process concerning the authorization, selection, management, and oversight of consultants for Personal Service and Architect & Engineering (A&E) agreements and/or supplements. Includes all work involved in the general management of Consultant Agreements related to construction services, including negotiations, agreement and supplement requests, invoice processing, DRB agreement management, meetings with consultants, submittal reviews, compliance reviews and other services offered to the consultants and to the state as related to consultants. Including Vessel Construction Engineering and Design Build. See Consultant Services Procedures Manual M27-50. |  | PE.PM.06 | Consultant Administration
PM.02.10 | Consultant RFP | Request for Proposal (RFP): A legal notice for solicitation of consulting services. Please see the Consultant Services Procedures Manual M 27-50, Chapter 1 for procedures. |  | PE.PM.06.01 | Consultant RFP
|  |  | Deleted | PE.PM.06.02 | Consultant Selection
PM.20.20 | Consultant Signed Contract | A legally binding contract between WSDOT and a Consultant for services rendered. Please see the Consultant Services Procedures Manual M 27-50, Chapters 5, 6, and 7 for procedures. |  | PE.PM.06.03 | Consultant Signed Contract
|  |  | Deleted | PE.PM.06.04 | Consultant Management
PM.03 | Community Engagement & Public Involvement | All work involved in the preparation and implementation of the public involvement plan; including work with the Communications Office and preparation and participation at public meetings. Does not include design or access hearings. See WSDOT Communication Manual M3030, as well as EM chapter 400 (EV.40.30 Early Coordination). |  | PE.PM.05 | Public and Agency Involvement
PM.03.10 | Community Engagement Plan/ Public Involvement Plan | The public involvement plan includes methods that will elicit the best participation from the community, including traditionally underrepresented groups. Developing an effective public involvement plan is a strategic effort. WSDOT must identify audiences, messages, strategies, and techniques that will meet the unique needs of a proposed transportation project, as well as the needs of the public. The ultimate goal of the public involvement plan is to allow members of the public opportunities throughout the process to: --Learn about the project --Provide information and options --Collaborate --Provide input intended to influence WSDOT decisions --All Agreements and Memorandums of Understanding (MOUs) complete |  | PE.PM.05.01 | Public Involvement Plan
PM.03.20 | Media & Public Outreach Activities | Community engagement Outreach to public such as stakeholder interviews, mailers, press releases, folios, open houses, booths at local events, traveling displays, briefings, presentations, meetings & other outreach activities; preparation of all media & public involvement communication materials; distribution of materials; on-going written, email & phone communications with media & public; establish & maintain project web page. • Media Relations Plan • Public Meetings • Open Houses • Community Engagement activities |  | SC.30.30 | Media & Public Outreach Activities
|  |  | Combined into PM.03 | SC.30 | Public Involvement for Planning Studies
|  |  | Combined into PE.03.20 | SC.30.10 | Media Relations Plan
|  |  | Combined into PE.03.20 | SC.30.20 | Community Engagement (public involvement)
|  |  | Combined into PE.30.10 | SC.30.40 | Public Involvement Summary
PM.04 | Cost Risk Estimating & Management | Cost Risk Estimating and Management (CREM) involves developing the project cost and schedule estimates and assessing project risk. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20 | Cost Risk Estimating & Management
PM.04.10 | CEVP® | Cost Estimate Validation Process (CEVP®) is required for any project with an estimated cost of $100 million or more. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.10 | CEVP®
PM.04.20 | CRA Workshop | Cost Risk Assessment (CRA) is required for all projects with an estimated cost of $25 million +. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.20 | CRA Workshop
PM.04.30 | Cost Risk Analysis | Cost Risk Analysis is required for all projects of $10 million or more. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.30 | Cost Risk Analysis
PM.04.40 | Qualitative Risk Assessment | A qualitative risk assessment is required for all projects. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.40 | Qualitative Risk Assessment
PM.04.50 | Combined Value Engineering and Risk Analysis (VERA) | On occasion it may be possible to combine value engineering with a project risk assessment. http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.50 | Combined Value Engineering and Risk Analysis (VERA)
PM.04.60 | Risk Management Plan | A document prepared by Regional managers that includes specific responses for each of the risk identified. See Cost Risk Estimate & Management website at: http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/ |  | DES.20.60 | Risk Management Plan
PM.05 | Value Engineering | A systematic process of project review and analysis, during concept and design phases, by a multidisciplinary team to provide recommendations for: providing needed functions safely, reliably, efficiently, and at the lowest overall cost; improving the value and quality of the project; and reducing the time to complete the project. Simply stated, VE is an organized application of common sense and technical to find and eliminate unnecessary costs in a project. |  | DES.40 | Value Engineering
PM.05.10 | VE Study | See Design Manual Chapter 310 for details. All projects with a total estimated cost (construction, right of way, preliminary engineering, utilities, etc.) over $25 million and any bridge project over $20 million will need to have a VE Study. |  | DES.40.10 | VE Study
PM.05.20 | VE Final Report | The VE study Final Report and Workbook should include a narrative description of project input information, background and history, constraints and drivers, VE team focus areas, and a discussion of the team speculation, evaluation, and recommendations. All of other team's evaluation documentation including sketches, calculations, analysis, and rationale for recommendations must be included in the Workbook as part of the Final Report. |  | DES.40.20 | VE Final Report
PM.05.30 | VE Recommendations implementation | Project decision makers act to ensure a fair and serious consideration of the proposed recommendations. The information is share within the agency as recommendations are implemented and associated savings are realized. The completed VE Recommendations Approval Form documents project team decisions with respect to VE recommendations. The completed form is sent to the HQ VE Program Manager. |  | DES.40.30 | VE Recommendations implementation
|  |  | Combined into PM.01 | PE.PM.02 | Project Management and Overhead
|  |  | Deleted | PE.PM.02.01 | General Project Management (Project Office)
|  |  | Deleted | PE.PM.02.02 | Redistributed PE Project Management and Overhead (HQ & Region)
|  |  | Deleted | PE.PM.10 | Ferry Vessels Engineering
|  |  | Deleted | PE.PM.10.01 | Scope from Port Engineers
|  |  | Deleted | PE.PM.10.02 | Vessels Kickoff Meeting
|  |  | Deleted | PE.PM.10.03 | Specifications/ Preliminary Estimates/ Schedules
|  |  | Deleted | PE.PM.10.04 | Spec Review/ Issue Work Order
|  |  | Deleted | PE.PM.10.05 | Spec Revise Finalized
|  |  | Deleted | PE.PM.10.06 | Final Estimate
|  |  | Deleted | PE.PM.10.07 | Project Summary and Deliverables
|  |  | Deleted | PE.PM.10.08 | Shipyard Planning
|  |  | Deleted | PE.PM.12 | Other Work for Management and Overhead
SC | Project Scoping | Some capital projects have the project scoping included as a specific part of the project. Some projects include work to plan further projects to be subsequently developed and constructed. |  | PE.PS | Project Scoping
SC.10 | Preliminary Estimates & Schedules for Scoping | Estimates and schedules developed for programming. |  | PE.PS.01 | Preliminary Estimates & Schedules for Scoping
SC.10.10 | PE Estimate | The estimated cost and schedule to complete the design phase of a project. Developed for programming the project. Contact Specialty groups to obtain an estimate for their services. |  | PE.PS.01.01 | PE Estimate
SC.10.20 | RW Estimate | The estimated cost and schedule to complete the right of way phase of a project. Includes all resource costs. Developed for programming the project. |  | PE.PS.01.02 | RW Scoping Estimate
SC.10.30 | CN Estimate | The estimated cost and schedule to complete the construction phase of a project. Developed for programming the project. |  | PE.PS.01.03 | CN Estimate
SC.20 | Agency & Tribal Coordination for Planning Studies | Outreach to public agencies & tribes |  | PE.PS.02 | Agency & Tribal Coordination for Planning Studies
SC.20.10 | Agency Outreach | Outreach to public agencies including initial interviews of partner agencies; briefings, presentations and meetings with technical staff and elected officials; written, email and phone communications |  | PE.PS.02.01 | Agency Outreach
SC.20.20 | Tribal Outreach | Outreach to tribes including initial contact letter; briefings, presentations, meetings and consultations with tribal staff and members; written, email and phone communications |  | PE.PS.02.02 | Tribal Outreach
SC.20.30 | Corridor Working Group | Establish Corridor Working Group (CWG); conduct CWG meetings; prepare CWG meeting materials; on-going communications with CWG members |  | PE.PS.02.03 | Corridor Working Group
SC.20.40 | Agency & Tribal Coordination Summary | Document summarizing communications and coordination with public agencies & tribes |  | PE.PS.02.04 | Agency & Tribal Coordination Summary
SC.30 | Existing Conditions Inventory & Analysis for Planning Studies and Scoping | For a planning or corridor study, inventory and analysis of existing facility, study area and travel conditions; identification of existing & future no-build deficiencies in accordance with Design Manual Chapter 300 |  | PE.PS.04 | Existing Conditions Inventory & Analysis for Planning Studies and Scoping
SC.30.10 | Existing Facility & Study Area Conditions | Inventory & description of roadway classifications, function and characteristics; vicinity & study area map; inventory & description of facility including geometrics, structures, traffic signals & control devices, terrain & roadside characteristics; inventory & description of study area transportation network (all modes) and land use/zoning conditions |  | PE.PS.04.01 | Existing Facility & Study Area Conditions
SC.30.20 | Environmental Inventory & Overview | Inventory & description of natural and built environment; inventory & description of archeological, historical and cultural resources; identify potential environmental justice issues and potential mitigation requirements of proposed improvements |  | PE.PS.04.02 | Environmental Inventory & Overview
SC.30.30 | Travel Conditions Analysis & Deficiencies Identification | Inventory of existing and historical traffic data & collisions; collect additional counts/data if needed; select & validate model; model existing and future no-build traffic conditions; analysis of data and forecasts; identify existing & future no-build access, safety, mobility and modal needs and deficiencies |  | PE.PS.04.03 | Travel Conditions Analysis & Deficiencies Identification
SC.30.40 | Existing Conditions Summary | Document summarizing existing conditions & identified deficiencies |  | PE.PS.04.04 | Existing Conditions Summary
SC.40 | Improvement Options Development & Assessment for Planning Studies | For a planning or corridor study, development & assessment of options to address identified deficiencies |  | PE.PS.05 | Improvement Options Development & Assessment for Planning Studies
SC.40.10 | Improvement Options | Identify & develop concept-level short & long-term improvements for all modes & TSM/TDM |  | PE.PS.05.01 | Improvement Options
SC.40.20 | Screening Criteria & Analysis | Establish screening criteria, methodology & process; select & validate model; model future build (improvement options) traffic conditions; analyze forecasts; screen proposed options |  | PE.PS.05.02 | Screening Criteria & Analysis
SC.40.30 | Short & Long-Term Recommendations | Establish prioritization process; select and prioritize screened improvement options into short-and long-term list of recommended improvement projects |  | PE.PS.05.03 | Short & Long-Term Recommendations
SC.40.40 | Funding Program & Financial Resources | Identify funding program and financial resources available to implement RDP recommendations & next steps within the decision process to implement the RDP |  | PE.PS.05.04 | Funding Program & Financial Resources
SC.50 | Planning Report | Planning Report documenting project work and recommendations |  | PE.PS.06 | Planning Report
SC.50.10 | Draft Planning Report | Draft report documenting project inventory and analysis work, outreach activities, and improvement recommendations; circulate draft report to CWG, partner agencies & WSDOT for review & comment |  | PE.PS.06.01 | Draft Planning Report
SC.50.20 | Final Planning Report | Revise & finalize report in response to comments; distribute report |  | PE.PS.06.02 | Final Planning Report
|  |  | Deleted | PE.PS.07 | WSF Pre-Design Study
SC.60 | Project Profile (Project Summary) | A document which comprises the Project Definition, Design Decisions and the Environmental Review Summary for a project |  | PE.PS.08 | Project Summary
SC.60.10 | Project Definition | The official document that states the purpose and need for the project and the solution of the deficiency. This is a formal document that must have Region and HQ concurrence. |  | PE.PS.08.01 | Project Definition
SC.60.20 | Basis Of Design, Design Parameter Sheets, Alternative Comparison Table (Design Decisions Summary) | A document which is part of the Project Summary which illustrates design considerations and details about design aspects of the project. |  | PE.PS.08.02 | Design Decisions Summary
SC.60.30 | Environmental Review Summary | A document which illustrates environmental permit needs and addresses the level of environmental approval and classification of the project. |  | PE.PS.08.03 | Environmental Review Summary
SC.60.40 | Project Definition Complete (Region) | PERFORMANCE REPORTING MAJOR Milestone- The official document that states the purpose and need for the project and the solution of the deficiency is a formal document called Project Summary. For reporting purposes, the Project Definition Milestone is considered complete on the date the Regional Administrator (RA) or the RA designee signs the Project Summary document. |  | PE.PS.08.04 | Project Definition Complete (Region)
SC.60.50 | Project Definition Complete (HQ) | Milestone- The Project Definition is formally approved when Project Summary has received Headquarters signature. (formally the Project Summary which includes the Project Definition, ERS, DDS) |  | PE.PS.08.05 | Project Definition Complete (HQ)
DES | Design | Planning and scoping typically have separate budgets but are encompassed under Design or Preliminary Engineering (PE). The terms “Design” or “Design Phase” are sometimes used interchangeably with DES. |  | PE.PD | Project Development
DES.10 | Project Delivery Method Selection | A systematic process based on a balance of the anticipated benefits and allocated risks used in the selection of the project delivery method for a project. |  | PE.PD.02 | Design-Build Assessment
DES.10.10 | Project Delivery Method Selection Document | Document of the final decision to proceed contracting via the selected project delivery method. |  | PE.PD.02.01 | Design-Build Decision Document
DES.10.20 | Project Need Statement | A project need statement (or statement of need) provides clear, accurate plain talk description of the root needs that will facilitate the development of efficient, focused project alternatives. DM 1101.05 | Added
DES.10.30 | Define Project Concept | Technical analysis | Added
DES.10.40 | Solution Alternatives & Selection | This involves generating alternatives, evaluating alternatives, checking costs and --Generate Alternatives --Evaluate Alternatives --Alternative Reviews --Solution Selection --Appraise R/W Costs --Preliminary Project Development | Added
DES.20 | Project Data, Survey Data, and Base Map | All work to collect background, project, survey, and field data and background data, and develop the base map. |  | PE.PD.06 | Project Data, Survey Data, and Base map
DES.20.10 | Project Data | All work to collect field data and background date, except ground collection of survey data. Background Data, Aerial Photographs, Data Collection - Aerial Photography, Clear Zone Inventory, As-Built Data Verified, ADA Accessibility Feature Inventory |  | PE.PD.06.01 | Project Data
|  |  | Combined into DES.20.10 | PE.PD.06.02 | Background Data
|  |  | Combined into DES.20.10 | PE.PD.06.03 | Aerial Photographs
|  |  | Combined into DES.20.10 | PE.PD.06.04 | Data Collection - Aerial Photography
|  |  | Combined into DES.20.10 | PE.PD.06.05 | Clear Zone Inventory
|  |  | Combined into DES.20.10 | PE.PD.06.06 | As-Built Data Verified
|  |  | Combined into DES.20.10 | PE.PD.06.07 | Maintenance Review Documentation
|  |  | Combined into DES.20.10 | PE.PD.06.08 | ADA Accessibility Feature Inventory
DES.20.20 | Surveying Data | All work to collect, measure, and record ground topography necessary to build a base map for the project, including the work to prepare structural site data. This includes all work to establish project control, traversing, installing bench marks, etc. Contact GeoMetrix Office/ HQ Survey and Mapping Branch as needed. Establish Geodetic Survey Control Establish Project Geometric Framework Geodetic Survey Monument Location Geodetic Survey Monument Re-establishment Monitor Slope and Structure Movement Utility Location Data Collection -Survey Data Collection - 3D Terrestrial LiDAR (Laser Scanning) Data Collection - Hydrographic Survey Data Collection - Field Topography Data Collection – Borehole Survey (SPS Easting, SPS Northing, Station, Offset, and Elevation) |  | PE.PD.06.20 | Surveying Data
|  |  | Combined into DES.20.20 | PE.PD.06.20.01 | Establish Geodetic Survey Control
|  |  | Combined into DES.20.20 | PE.PD.06.20.02 | Establish Project Geometric Framework
|  |  | Combined into DES.20.20 | PE.PD.06.20.03 | Geodetic Survey Monument Location
|  |  | Combined into DES.20.20 | PE.PD.06.20.04 | Geodetic Survey Monument Re-establishment
|  |  | Combined into DES.20.20 | PE.PD.06.20.05 | Monitor Slope and Structure Movement
|  |  | Combined into DES.20.20 | PE.PD.06.20.06 | Utility Location
|  |  | Combined into DES.20.20 | PE.PD.06.20.07 | Data Collection -Survey
|  |  | Combined into DES.20.20 | PE.PD.06.20.08 | Data Collection - 3D Terrestrial LiDAR (Laser Scanning)
|  |  | Combined into DES.20.20 | PE.PD.06.20.09 | Data Collection - Hydrographic Survey
|  |  | Combined into DES.20.20 | PE.PD.06.20.10 | Data Collection - Field Topography
DES.20.30 | Site Data for Geotech | Site information provided to the Geotechnical Office (GO) and/or Region Materials Office (RMO) by the project design office (specific to the type of project) to initiate geotechnical work on a project during the design and PS&E phases. See Design Manual Chapter 610. Typically this includes: • A plan view showing: R/W, alignments, wetlands, 100 yr. and 500yr high water elevations, utilities, contours, and existing features; with the proposed new project elements overlaid. • Elevation view • Cross-sections • CAD DTM |  | PE.PD.18.01 | Preliminary Site Data
DES.20.40 | Base Map | Development of the project base map for Preliminary Engineering. This Work Op does not include Base Map work for Right of Way Plans, use Work Op 0119. Contact GeoMetrix Office/HQ Survey and Mapping Branch as needed. Data Processing Photogrammetry and Point Cloud. |  | PE.PD.06.30 | Basemap
|  |  | Combined into DES.20.30 | PE.PD.06.30.01 | Data Processing - Photogrammetry
|  |  | Combined into DES.20.30 | PE.PD.06.30.02 | Data Processing - Point Cloud
DES.20.50 | Maintenance and Design Collaboration | An onsite review of the project with maintenance to look at existing situations and any concerns about the proposed design. | Added
DES.20.60 | Design Visualization | Still Image or Visualization using 3D CAD modeling to effectively explain complicated design options and/or practical design decisions. Contact GeoMetrix Office / Visual Engineering Resource Group (VERG) as needed. |  | PE.PD.28.06 | Monumentation Map
|  |  | Deleted | PE.PD.07 | WSF Vessels Design Work
|  |  | Deleted | PE.PD.07.01 | Electrical Design
|  |  | Deleted | PE.PD.07.02 | Mechanical Design
|  |  | Deleted | PE.PD.07.03 | Hull Design
|  |  | Deleted | PE.PD.07.04 | Security Design - Mechanical
|  |  | Deleted | PE.PD.07.05 | Security Design - Hull
|  |  | Deleted | PE.PD.07.06 | Security Design - Electrical
DES.30 | Interchange Justification | Evaluate when new or reconstructed access on limited access facilities will be affected. See Design Manual Chapter 550. |  | PE.PD.12 | Interchange Justification
DES.30.10 | Interchange Justification Report (IJR) | An IJR is required for new/reconstruction of accesses on limited access facilities. It is required to be submitted to the Assistant State Design Engineer. FHWA approval is required for all interstate highways. See Design Manual Chapter 550. |  | PE.PD.12.01 | Interchange Justification Report (IJR)
DES.40 | Access Control | Evaluation of limited access and managed access components on WSDOT facilities. See Design Manual Chapters 520, 530 and 540. |  | PE.PD.14 | Access Control
DES.40.10 | Managed Access Permit | All new access connections and alterations/improvements to existing access connections to state highways require an access connection permit. See Design Manual Chapter 520 and 540. |  | PE.PD.14.01 | Managed Access Permit
DES.40.20 | Hearings | Certain capital transportation projects require a public hearing by state and federal statutes. See Design Manual Chapter 210 |  | PE.PD.14.02 | Hearings
DES.40.30 | Limited Access Hearing | An L/A hearing is required by law (per RCW 47.52) whenever limited access is established or revised on new or existing highways. (See Design Manual Chapter 210) |  | PE.PD.14.03 | Limited Access Hearing
DES.40.40 | Limited Access Report & Plans | The access report and plans notifies the local agency how the limited access will impact their transportation system. The access report and plans are submitted to the HQ Access and Hearings Unit for approval. The Local Agency(ies) must concur with the Access Report. See Design Manual Chapter 210 & 530 and the Plans Preparation Manual Section 100.05. |  | PE.PD.14.04 | Limited Access Report & Plans
DES.40.50 | Limited Access Hearing Packet | The prehearing packet (including legal notices, news releases, and exhibits) is prepared and submitted to HQ Access Office at least 45 days prior to the hearing. This packet will be sent to abutting owners. See Design Manual Chapter 210. |  | PE.PD.14.05 | Limited Access Hearing Packet
DES.40.60 | Formal Access Hearing | Milestone- A formal hearing that gives local public officials, owners of abutting property, and other interested citizens an opportunity to be heard concerning any plan that proposes the limitation of access to the highway system. See Design Manual Chapter 210. |  | PE.PD.14.06 | Formal Access Hearing
DES.40.70 | Limited Access Findings & Order | A document containing the findings and conclusions of a limited access hearing that is approved by the Environmental and Engineering Programs Director. See Design Manual Chapter 210. |  | PE.PD.14.07 | Limited Access Findings & Order
DES.40.80 | Adoption of Limited Access Findings & Order | Milestone- The date of formal adoption of the Findings and Order for limited Access. See Design Manual Chapter 210. |  | PE.PD.14.08 | Adoption of Limited Access Findings & Order
DES.40.90 | Design Hearing Packet | When it is determined that a hearing is to be held, the region prepares a pre-hearing packet. See Design manual Chapter 210 for details. |  | PE.PD.14.09 | Design Hearing Packet
DES.40.100 | Design Hearing | A Design Hearing is required when there are social, economic, or environmental impacts. This hearing is held after a route is established, but before final design is complete and ensures the public has an opportunity to present views on design alternatives. This hearing may be formal or informal. See Design Manual Chapter 210. |  | PE.PD.14.10 | Design Hearing
DES.40.110 | Adoption of Design Hearing Summary | A document containing the Design Hearing Summary and responses to all questions as a result of the hearing. State Design Engineer approves the summary for state routes, and FHWA approves the summary for interstate projects. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | PE.PD.14.11 | Adoption of Design Hearing Summary
DES.40.120 | Corridor Hearing | A Corridor hearing is required if there is a proposed route on new location, or a significant change in layout of connecting roads. See Design Manual Chapter 210 |  | PE.PD.14.12 | Corridor Hearing
DES.40.130 | Adoption of Corridor Hearing Summary | A document containing the Corridor Hearing Summary and responses to all questions as a result of the hearing. The Director of Environmental and Engineering Programs approves the summary for state routes. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | PE.PD.14.13 | Adoption of Corridor Hearing Summary
DES.40.140 | Environmental Documentation Hearing | Normally held for projects requiring an EIS, the hearing is timed to fall within the comment period for the Draft EIS. |  | PE.PD.14.14 | Environmental Documentation Hearing
DES.40.150 | Adoption of Environmental Hearing Summary | A document containing the Environmental Hearing Summary and responses to all questions as a result of the hearing. The Director of Environmental and Engineering Programs approves the summary for state routes. Submitted to HQ Access & Hearings Section within two months following hearing. See Design Manual Chapter 210. |  | PE.PD.14.15 | Adoption of Environmental Hearing Summary
DES.50 | Materials (Roadway) | Development of soils, surfacing, and materials reports for project. |  | PE.PD.16 | Materials (Roadway)
DES.50.10 | Pavement Determination | Preliminary recommendations for surfacing materials. See WSDOT pavement interactive guide at http://wwwi.wsdot.wa.gov/MaintOps/mats/pavementguide.htm |  | PE.PD.16.01 | Pavement Determination
DES.50.20 | Surfacing/Resurfacing Report | A report that lists the recommendations for type, size, & depth of surfacing for each roadway and recommendations for rehabilitation of existing roadways |  | PE.PD.16.02 | Surfacing/Resurfacing Report
DES.50.30 | Materials Source Report | A report on a specific WSDOT material source that verifies the quality and quantity of the material requested. |  | PE.PD.16.03 | Materials Source Report
DES.50.40 | Native Soil Exploration | See Chapter 610 Investigation of Soils, Rock, and Surfacing Materials. The designer contacts and meets with the Regional Materials Engineer (RME) (and the HQ Geotechnical Office as needed) at the project site to conduct a field review to help identify the geotechnical issues for the project. A brief conceptual-level report that summarizes the results of the investigation is provided to the designer. The information from this report will be used to prepare the contract as well as by the Construction Office to evaluate Value Engineering Change Proposals (VECP). For example a contractor may want to use native soil instead of the specified import in the contract to save money. | Added
DES.60 | Geotechnical | Development of Geotechnical reports for project. |  | PE.PD.18 | Geotechnical Evaluations
DES.60.10 | Soil Boring Notice of Intent | All drilling activities, including Geotech soil borings, monitoring/resource protection wells, and developing or decommissioning water wells. See Geotechnical Design Manual M46-03, Appendix 1-A. | Moved from EV | PE.EV.21.19 | Soil Boring Notice of Intent
DES.60.20 | Geotechnical Recommendations - RMO | Region Materials Office (RMO) The RMO provides geotechnical recommendations to the Project Office or other Specialty Offices, which they then incorporate into the project, see Chapter 1 of the Geotechnical Design Manual M 46-03. Project elements usually addressed by the RMO include: sign, signal, luminaire, and camera foundations, retaining walls less than 10 ft. in height, noise wall foundations, cuts and fills less than 10 ft. in height, culverts less than 30-inches, infiltration rates, and material sources. There can be several deliverables that are provided depending upon what the project contains. • Geotechnical Memorandums – Geotechnical memorandums are usually prepared for smaller projects, projects where the stakeholders are all WSDOT offices, to address one or two project specific elements, or to provide recommendations that are conceptual or preliminary. • Boring Logs – Borings logs are usually included in the Geotechnical Memorandum, and the Project Office includes them in the Contract Provisions. • Geotechnical Reference Information – The RMO will prepare a package of project related geotechnical references and provide that to Contract Ad and Award office who will post that information on their website for contractor use. | Added
DES.60.30 | Geotechnical Recommendations - GO | Construction Division – Geotechnical Office (GO) The GO provides geotechnical recommendations to the Project Office or other Specialty Offices, which they then incorporate into the project, see Chapter 1 of the Geotechnical Design Manual M 46-03. There can be several deliverables that are provided depending upon what the project contains and the delivery method; Design-Build (DB) or Design-Bid-Build (DBB). Not all of the deliverables listed below are required. Typical DBB Deliverables • Geotechnical Reports – Geotechnical reports are prepared for larger projects or for projects that have external stakeholders. They typically address more than one project element. • Geotechnical Memorandums – Geotechnical memorandums are usually prepared for smaller projects, projects where the stakeholders are all WSDOT offices, to address one or two project specific elements, to provide early final recommendations to team members to keep work moving forward, or to provide recommendations that are conceptual or preliminary. • Boring Logs – Borings logs are usually included in the Geotechnical Report or Geotechnical Memorandum, and the Project Office includes them in the Contract Provisions. • Geotechnical Reference Information – The GO will prepare a package of project related geotechnical references and provide that to Contract Ad and Award office who will post that information on their website for contractor use. Typical DB Deliverables • Geotechnical Memorandums – Geotechnical recommendations may be prepared for project elements in the basic configuration. They are not intended to provide enough information to complete final design. The have just enough content to help assess feasibility, costs and risks. • Request for Proposal (RFP) Section 2.6 – Section 2.6 of the RFP is Geotechnical. The Project Office is responsible to deliver the entire RFP, but project specific technical requirements will be added into the 2.6 section template by the GO. • Geotechnical Data Report (GDR) – The GO will prepare the GDR and any supplements. • Geotechnical Reference Information - The GO will assemble a package of reference information which the Project Office will make available to the Design Builder along with the RFP. • Geotechnical Baseline Report (GBR) - The GO will prepare the GBR. • Request for Qualifications (RFQ) – The Project Office will prepare the RFQ, but the GO may prepare a portion of the document and should review it. • Instructions to Proposers (ITP) - The Project Office will prepare the ITP, but the GO may prepare a portion of the document. | Added
|  |  | Combined into DES.20.30 | PE.PD.18.01 | Preliminary Site Data
|  |  | Combined into DES.60 | PE.PD.18.02 | Conceptual Geotechnical Report
|  |  | Combined into DES.20.30 | PE.PD.18.03 | Project Site Data
|  |  | Combined into DES.60.20 | PE.PD.18.04 | RME Geotech Report(s)
|  |  | Combined into DES.60.30 | PE.PD.18.05 | HQ Geotechnical Report(s)
DES.70 | Bridge and Structures | Preliminary work, design, and PS&E for bridges and structures. See Bridge Design Manual: http://www.wsdot.wa.gov/Publications/Manuals/M23-50.htm | Moved to Design | PE.BR | Bridge and Structures
|  |  | Deleted | PE.BR.01 | Structural Site Data
DES.70.10 | Bridge Site Data | Structure Site Data to be sent to HQ Bridge for design and PS&E. See Design Manual Chapter 710. |  | PE.BR.01.01 | Bridge Site Data
DES.70.20 | Wall Site Data | Structure Site Data to be sent to HQ Bridge, HQ Geotechnical, or Region Materials for design and PS&E. See Design Manual Chapter 730. |  | PE.BR.01.02 | Wall Site Data
DES.70.30 | Noise Wall Site Data | Plan and profile along centerline of the wall. Data to be sent to HQ Geotechnical or Region Materials for design. See Design Manual Chapter 740. |  | PE.BR.01.03 | Noise Wall Site Data
DES.70.40 | Noise Barrier Height & Verification Analysis | This deliverable uses more detailed design data to optimize barrier height and verify that feasibility and requirements are met. |  | PE.BR.01.04 | Noise Barrier Height & Verification Analysis
|  |  | Deleted | PE.BR.02 | Bridge / Structure Design & Plans
DES.70.50 | Bridge Condition Report | Produced by the Bridge Office - describes condition of deck and general information about the structure. |  | PE.BR.02.01 | Bridge Condition Report
DES.70.60 | Preliminary Bridge Plan | Preliminary plan showing location, length, type of structure (TS&L) and estimate. |  | PE.BR.02.02 | Preliminary Bridge Plan
DES.70.70 | Sign Structure Design & Plans | All work to design, review and finalize the sign structure plans. |  | PE.BR.02.03 | Sign Structure Design & Plans
DES.70.80 | Noise Wall Design | Document/design noise walls that are non-standard or are part of a retaining wall. |  | PE.BR.02.04 | Noise Wall Design
DES.70.90 | Retaining Wall Design | Document/design non standard retaining walls & soldier pile walls |  | PE.BR.02.05 | Retaining Wall Design
DES.70.100 | Bridge Rails/Expansion Joints Design | Document/design rehabilitation of bridge rails, expansion joints and bridge decks |  | PE.BR.02.06 | Bridge Rails/Expansion Joints Design
DES.70.110 | Other Structure Design | Document/design approach slabs, tunnel, emergency repairs and other structural design. |  | PE.BR.02.07 | Other Structure Design
DES.70.120 | Consultant Structural Plans Review | Performed by HQ Bridge & Structure office on preliminary or structural design layouts prepared by non-WSDOT personnel. Includes plans and specifications review and revisions. This work op is only for use by the HQ Bridge & Structures Office. |  | PE.BR.02.08 | Consultant Structural Plans Review
DES.70.130 | Bridge Architect | Work to prepare preliminary designs and design concepts; review and finalize the architectural features for bridge, retaining walls, noise walls, and other structures. |  | PE.BR.02.09 | Bridge Architect
DES.70.140 | Bridge Design | All work to design, review and finalize the bridge plans, including 90% Plans turn-in to the regions 4 weeks prior to 100% turn-in |  | PE.BR.02.10 | Bridge Design
DES.70.150 | Bridge Specials and Estimates | All work to prepare Bridge & Structures contract provisions including Std. Spec. Amendments, GSP’s, Special Provisions, Appendices and estimates. |  | PE.BR.02.12 | Bridge Specials and Estimates
DES.80 | Roadway Geometrics and Plans | Development of earthwork design and channelization design. Also includes minor safety design and documentation. |  | PE.PD.20 | Roadway Geometrics and Plans
DES.80.10 | Roadway Design | Finalization of the horizontal and vertical alignments for each roadway in the project, see Design Manual Chapters 1210 & 1220 |  | PE.PD.20.01 | Roadway Design
DES.80.20 | Alignment Plan | Horizontal and vertical alignment plans for each roadway in the project, see Design Manual Chapters 1210 & 1220 |  | PE.PD.20.02 | Alignment Plan
DES.80.30 | Intersection Plan for Approval | A plan that address the intersection design considerations in accordance with Design Manual Chapter 1310 |  | PE.PD.20.03 | Intersection Plan for Approval
DES.80.40 | Interchange Plan for Approval | A plan that address the interchange design considerations in accordance with Design Manual Chapter 1360 |  | PE.PD.20.04 | Interchange Plan for Approval
DES.80.50 | Channelization Plan | A plan that address the channelization design considerations in accordance with Design Manual Chapter 1310 |  | PE.PD.20.05 | Channelization Plan
DES.80.60 | Project footprint & Earthwork Quantities | The Project Footprint & Earthwork Quantities are calculations that determine the cut/fill lines and project footprint, and the earthwork cut/fill quantities that specialty groups such as Environmental and Real Estate need to start their processes. These lines and quantities help identify if the project extends beyond WSDOT R/W, which determine the need for Right of Way acquisition. They also define the limits of the Area of Potential Effect map, which must be developed prior to the Section 106 cultural investigation and other Environmental documentation. The project footprint and earthwork quantities are critical for the NEPA/SEPA process, and Environmental permits such as the NPDES. See Design Manual Chapter 1600 |  | PE.PD.20.06 | Project footprint & Earthwork Quantities
DES.80.70 | Roadway Sections | Geometric roadway cross section from the subgrade to finish grade |  | PE.PD.20.07 | Roadway Sections
DES.80.80 | Roadside Safety Analysis | Address items on the Clear Zone Inventory and any other safety items that have been discovered including documenting a decision to fix or not. Design Manual Chapter 1600 |  | PE.PD.20.08 | Roadside Safety Analysis
DES.80.90 | Minor Safety Documentation | Paving projects (P1) have opportunities to improve minor deficiencies as part of the preservation work. See Design Manual Chapter 1120 |  | PE.PD.20.09 | Minor Safety Documentation
DES.80.100 | Corridor or Project Analysis | If completed - a corridor or project analysis in accordance with Design Manual Chapter 300 |  | PE.PD.20.10 | Corridor or Project Analysis
DES.90 | Hydraulics/Drainage | The Hydraulic Report is intended to serve as a complete documented record containing the engineering justification for all drainage modifications that occur as a result of the project. See Hydraulics Manual. See Highway Run Off Manual M31-16. See Design Manual Chapter 301 Design Maintenance Coordination. |  | PE.PD.22 | Hydraulics
DES.90.10 | Type A Hydraulic Report | Type A Hydraulic Reports contain documentation of design for major hydraulic work. See the Hydraulics Manual. |  | PE.PD.22.01 | Type A Hydraulic Report
DES.90.20 | Type B Hydraulic Report | Type B Hydraulics Reports contain documentation of design for hydraulics. See the Hydraulics Manual. |  | PE.PD.22.02 | Type B Hydraulic Report
DES.90.30 | Hydraulic Summary | At the Region's discretion, smaller projects may replace a Type B report with a Hydraulic Summary, see the Hydraulics Manual and Region Hydraulics Engineer for more information. |  | PE.PD.22.03 | Hydraulic Summary
DES.90.40 | Specialized Hydraulics Design and Analyses | Specialized hydraulic design and analyses are stream designs, floodplain analyses, bridge backwater analyses, scour analyses, fish passage designs, and other HQ Hydraulics roles and responsibilities. See Hydraulics Manual Section 1-2. |  | PE.PD.22.04 | Specialized Hydraulics Design and Analyses
DES.90.50 | Stormwater BMP Maintenance Plan | It is the responsibility of the Project Design office to prepare Stormwater Best Management Practice Maintenance Plans for hand off to Construction Office for construction of the BMP and field survey verification testing of the constructed facility. See Highway Runoff Manual M31-16, Chapter 3 & 5. Construction Office then provides as-built feedback to the Author of the BMP plan, which will be finalized into the a WSDOT Owner's Manual for the Stormwater facility. Governed by the National Pollution Discharge Elimination System (NPDES) stormwater permit and the Clean Water Act, WSDOT constructs facilities to control and remove pollutants from stormwater discharged to surface waters. The NPDES permit requires that these best management practice (BMP) facilities be maintained for long-term performance. Stormwater BMPs are the physical, structural, and managerial practices that, when used singly or in combination, prevent or reduce the detrimental impacts of stormwater, such as the pollution of water, degradation of channels, damage to structures, and flooding. | Added
DES.90.60 | Hydraulic Report Approved | Milestone- Hydraulics Report Approved for project. |  | PE.PD.22.05 | Hydraulic Report Approved
DES.100 | Partnerships | A contract entered into by two or more groups. |  | PE.PD.24 | Partnerships
DES.100.10 | Local Agencies Agreements/MOU's | A contract between the Washington State Department of Transportation and a local governmental agency that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | PE.PD.24.01 | Local Agencies Agreements/MOU's
DES.100.20 | Other Agencies Agreements/MOU's | A contract between the Washington State Department of Transportation and other governmental agencies or non-governmental agencies that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | PE.PD.24.02 | Other Agencies Agreements/MOU's
DES.100.30 | Tribal Agreements/MOU's | A contract between the Washington State Department of Transportation and a tribal government that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | PE.PD.24.03 | Tribal Agreements/MOU's
DES.100.40 | Developer Agreements/MOU's | A contract between the Washington State Department of Transportation and a private developer that includes an offer and an acceptance. Agreements are necessary to accomplish the transfer of funds into and out of state accounts for goods and services. |  | PE.PD.24.04 | Developer Agreements/MOU's
DES.110 | Railroad | Communication and tasks related to Railroads. Contact the Region Utilities Office, Railroad and Agreements Office. |  | PE.PD.26 | Railroad
|  |  | Combined into DES.110.10 | PE.PD.26.01 | Preliminary Relocation Plan
|  |  | Combined into DES.110.10 | PE.PD.26.02 | Existing Railroad Facilities Located
DES.110.10 | Railroad Facility Plan | A plan showing the location of known railroad facilities. This plan should include all additional data acquired to insure the accuracy needed for the project. --Preliminary Relocation Plan --Existing Railroad Facilities Located --Updated Railroad Facility Location Plan --Railroad Facilities Relocation Plan |  | PE.PD.26.03 | Existing Railroad Facility Plan
|  |  | Combined into DES.110.10 | PE.PD.26.04 | Updated Railroad Facility Location Plan
|  |  | Combined into DES.110.10 | PE.PD.26.05 | Railroad Facilities Relocation Plan
DES.110.20 | Railroad Agreements | A contract between the Department and a railroad for work by either party where the department will receive or pay funds. |  | PE.PD.26.06 | Railroad Agreements
DES.120 | Facilities Plans | The design of facilities and buildings, including architectural, structural, mechanical, electrical, and landscape architecture aspects. These buildings and facilities include highway safety rest areas, ferry terminals, and other facilities. |  | PE.PD.30 | Facilities
DES.120.10 | Site Design (Facility) | All work to develop, review and finalize design criteria, plans and specifications for all site grading, stormwater, utilities, roadways, parking lots, and other landscape architecture or civil engineering tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.01 | Site Design Plan (Facility)
DES.120.20 | Architectural Design | All work to develop, review and finalize design criteria, plans and specifications for all site layout, building design (floor plans, elevations) and other architectural tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.02 | Architectural Design Plan
DES.120.30 | Facilities Structural | All work to develop, review and finalize design criteria, plans and specifications for all structural design of buildings and other structural tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.03 | Facilities Structural Plan
DES.120.40 | Facility Mechanical | All work to develop, review and finalize design criteria, plans and specifications for all plumbing, HVAC, steam lines, and other facility mechanical tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.04 | Facility Mechanical Plan
DES.120.50 | Facility Electrical | All work to develop, review and finalize design criteria, plans and specifications for all electrical design and other facility electrical tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.05 | Facility Electrical Plan
DES.120.60 | Site Restoration | All work to develop, review and finalize design criteria, plans and specifications for all finish grading, plantings and irrigation and other landscape architecture tasks associated with new or alterations to existing buildings, structures or facilities. |  | PE.PD.30.06 | Site Restoration Plan
DES.130 | Roadside Restoration and Site Development | Work to meet landscaping and roadside policies. Meet regulatory requirements. The funding type determines the limits of roadside restoration, and the character classification determines the appropriate treatment. |  | PE.PD.32 | Roadside Restoration and Site Development
DES.130.10 | Roadside Master Plan | Work required to meet agency policy and regulatory requirements. The Roadside Policy Manual describes restoration requirements. Impact area/location, roadside character and context determines the appropriate treatment. See Region Landscape Architect or HQ Roadside Development Manager. |  | PE.PD.32.01 | Roadside Master Plan
DES.130.20 | Restoration Estimate Worksheet | Region Landscape Architects or the HQ Roadside and Site Development Section prepares a restoration estimate which includes all costs to restore and establish a sustainable plant community per the Roadside Policy Manual, and the Roadside Manual Chapter 810. |  | PE.PD.32.02 | Restoration Estimate Worksheet
DES.130.30 | Roadside Restoration Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications related to roadside restoration associated with new or alterations to existing roadway projects. See the Roadside Policy Manual and Roadside Manual Chapter 800. |  | PE.PD.32.03 | Roadside Restoration Plan
DES.130.40 | Irrigation Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans and specifications relating to irrigation, including Irrigation Structure notes and details. See Plans Preparation Manual (PPM) 400.06 |  | PE.PD.32.04 | Irrigation Plan
DES.130.50 | Aesthetics Treatment Plan | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications related to architectural treatment and visual aspects of projects associated with new or alterations to existing roadway projects. See Design Manual Chapter 950; Environmental Manual Chapter 459 and Visual Discipline reports for the project. The Aesthetics Treatment Plan is a deliverable performed by a landscape architect for EV.30.160 Visual Impacts Discipline Report. |  | PE.PD.32.05 | Aesthetics Treatment Plan
DES.130.60 | Mitigation Design and Plan Sheets | All landscape architecture work to develop, review and finalize design criteria, reports, plans, and specifications associated with permit requirements for mitigation and environmental restoration. |  | PE.PD.32.06 | Mitigation Design and Plan Sheets
DES.130.70 | Plant Establishment Implementation Plan | All landscape architecture work to develop, review and finalize criteria during design including reports, plans, and specifications related to plant establishment requirements associated with roadside or mitigation design. |  | PE.PD.32.07 | Plant Establishment Implementation Plan
DES.140 | Traffic Analysis | The determination of whether or not the proposed improvement(s) will satisfy future capacity needs and/or establishment of the requirements necessary for the facility to operate at an acceptable level of service through the design year. Refer to Design Manual 320. |  | PE.PD.34 | Traffic Analysis
DES.140.10 | Collision Data | Validate accident data. Update / supplement if necessary |  | PE.PD.34.01 | Collision Data
DES.140.20 | Preliminary Traffic Analysis Report | A report that identifies safety and/or capacity deficiencies and provides recommendations including geometric configurations, intersection control, and appropriate traffic control devices. |  | PE.PD.34.02 | Preliminary Traffic Analysis Report
DES.140.30 | Traffic Volumes & Movements | Validate traffic counts. Update / supplement if necessary |  | PE.PD.34.03 | Traffic Volumes & Movements
DES.140.40 | Traffic Model | Validate traffic model. Update/supplement if necessary |  | PE.PD.34.04 | Traffic Model
DES.140.50 | Traffic Analysis Report | Review the operational needs of a study area with consideration of multimodal factors. |  | PE.PD.34.05 | Traffic Analysis Report
DES.140.60 | Bus Stop Inventory | Design decisions . Approval, denial, or variance per engineering and traffic considerations. |  | PE.PD.34.06 | Bus Stop Inventory
DES.140.70 | Intersection Control Alternatives Analysis (ICA) | An objective of the ICA are to: provide a consistent framework to determine the most compatible intersection control type for the location, context, economics, and balance of performance needs. See DM 1300 for further details. |  | PE.PD.34.07 | Intersection Control Alternatives Analysis
DES.140.80 | Collision Analysis Report | Review safety aspects of the project study area. | Added
DES.150 | Traffic Design & Plans | Gathering of traffic data and development of Traffic reports, studies, designs, and plans. |  | PE.PD.36 | Traffic Design & Plans
DES.150.10 | Signing Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Develop plan sheets in accordance with Plans Preparation Manual (PPM) 400.06. Includes sign specification sheets and details. See also Design Manual Chapter 1020. |  | PE.PD.36.01 | Signing Design & Plans
DES.150.20 | Illumination Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Develop plans that show street lighting, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1040 |  | PE.PD.36.02 | Illumination Design & Plans
DES.150.30 | Signal Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, traffic volume and turning movements counts, Speed Study, utility service agreement. Plans developed by the Region or HQ Traffic Office, including details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1330 |  | PE.PD.36.03 | Signal Design & Plans
DES.150.40 | Traffic Signal Permit | State statutes (RCWs) require Department of Transportation approval for the design and location of all conventional traffic signals, ramp meters and some types of beacons located on city streets forming parts of state highways. Approval by the Department of Transportation for the design, location, installation, and operation of all other traffic control signals installed on state highways is required by department policy. The Traffic Signal Permit (DOT Form 242-014 EF) is the formal record of the department’s approval of the installation and type of signal. The permit is completed by the responsible agency and submitted to the Regional Administrator for approval. |  | PE.PD.36.04 | Traffic Signal Permit
DES.150.50 | ITS Design & Plans | Document project specific design decisions, deviations, justifications, and other approvals. Request soils investigation, foundation design, utility service agreement. Plans normally developed by the Region Traffic Office that show how to construct Intelligent Transportation Systems, including details. See Plans Preparation Manual (PPM) 400.06. See also Design Manual Chapter 1050 |  | PE.PD.36.05 | ITS Design & Plans
DES.160 | Utilities | The Utility Accommodation Team evaluates and authorizes the installation of utilities and other facilities or activities within the state highway right of way. This team will also coordinate any necessary relocations. |  | PE.PD.38 | Utilities
DES.160.10 | Existing Utilities Located | Locate existing utilities in the field to level of accuracy required. Can vary from quality level D (most basic) to quality level A (Subsurface Utility Engineering (SUE)). See Utilities Manual. Determine the best method to use and the level of detail needed. |  | PE.PD.38.01 | Existing Utilities Located
DES.160.20 | Existing Utility Plan | A plan showing the location of known aerial and underground utility facilities. This plan should include all additional data acquired to insure the accuracy needed for the project. |  | PE.PD.38.02 | Existing Utility Plan
DES.160.30 | Utility Relocation Plan | A plan showing utility relocations/adjustments. |  | PE.PD.38.03 | Utility Relocation Plan
DES.160.40 | Utility Agreements | A contract between the Department and a utility for work by either party where the department will receive or pay funds. |  | PE.PD.38.04 | Utility Agreements
DES.170 | Work Zone Traffic Control (WZTC) - Design & Plans | The planning, design, and preparation of the Transportation Management Plan and contract documents for the modification of traffic patterns during construction is known as work zone traffic control. See Design Manual Chapter 1010. |  | PE.PD.40 | Work Zone Traffic Control (WZTC) - Design & Plans
DES.170.10 | Work Zone Traffic Control Meeting | A meeting with the Work Zone Traffic Control (WZTC) design team, construction office, and other stakeholders to discuss various traffic control strategies for the project. See Design Manual Chapter 1010. |  | PE.PD.40.01 | Work Zone Traffic Control Meeting
DES.170.20 | Transportation Management Plan (TMP) | Includes the plans and actions to address the work zone safety and mobility impacts of the project. A TMP document is required for significant projects. See Design Manual Chapter 1010. |  | PE.PD.40.02 | Transportation Management Plan (TMP)
DES.170.30 | Staging Design | Development of a construction sequence/staging strategy that is efficient, cost effective, and safe. See Design Manual Chapter 1010. |  | PE.PD.40.03 | Staging Design
DES.170.40 | Traffic Control Plans | Temporary Traffic Control strategies developed into site specific, project specific or typical traffic control plans. see Plans Preparation Manual (PPM) Chapter 460 and Design Manual Chapter 1010. |  | PE.PD.40.04 | Traffic Control Plans
DES.170.50 | Detour Plan | Plans that show the route to be used as a detour while the project is being constructed. See Plans Preparation Manual (PPM) 400.06 |  | PE.PD.40.05 | Detour Plan
DES.180 | Design Documentation | Design documentation is prepared to record the evaluations by the various disciplines that result in design recommendations. See Design Manual Chapter 300 |  | PE.PD.42 | Design Documentation
DES.180.10 | Design Approval | Milestone- (May be delayed/combined with Project Development Approval) Design approval includes: a memo that describes the project, Project Summary Documents, Design Criteria, Design Variances, known deviations, applicable Channelization plans, Intersection plans, Interchange plans, or Alignment plans and a current cost estimate. See Design Manual Chapter 300 |  | PE.PD.42.01 | Design Approval
DES.180.20 | Design Documentation Package | A compilation of assumptions, decisions, justifications, and approvals that support the ultimate design of the project, to include review of the package. This file is designated for long term storage in accordance with WSDOT's document retention policies. See Design Manual Chapter 300. Basis Of Design, Scope Validation, Deliverables for the Project, Schedule, Cost Estimate, Risk management plan, Change management plan, Quality Management Plan, Human Resources Plan Project Profile - comprised of Project Definition, Environmental Review Summary, and Basis Of Design for a project |  | PE.PD.42.02 | Design Documentation Package
DES.180.30 | ADA Accessibility Design Documentation (MEF Maximum Extent Feasible) | ADA Accessibility of existing Pedestrian Facilities to the Maximum Extend Feasible Documentation . See Design Manual Chapter 1510 |  | PE.PD.42.03 | ADA Accessibility Design Documentation
DES.180.40 | Design Analysis | A documented decision granting approval at project specific locations to differ from the design level specified in the Design Manual. DM Chapters 300 and 1100. |  | PE.PD.42.04 | Deviation
|  |  | Deleted | PE.PD.42.05 | Evaluate Upgrade
|  |  | Deleted | PE.PD.42.06 | Design Exception
DES.180.50 | Project Development Approval | Milestone- Final approval of all project development documents by the designated representative of the approving organization prior to the advertisement of a capital transportation project. See Design Manual Chapter 300 |  | PE.PD.42.07 | Project Development Approval
DES.190 | R/W Base Map and R/W Plans | Preparation of the base map to depict property ownership lines, alignments, and Right of Way boundaries for use as a PS& E plan/profile or Right of Way plan. Includes title report work, right of entry, calculation of areas & property corners, construction permits & easements, preparation, review, and submission of relocation plans. Also includes drafting of alignments, Right of Way lines, drainage and irrigation easements, and maps and plans for hardships or other special cases. |  | PE.PD.28 | Right of Way (R/W) Engineering
DES.190.10 | Preliminary Right of Way | Determination of approximately how much additional Right of Way will be needed to construct the project. Includes any property impacts as defined in the Right of Way Manual Division 6. |  | PE.PD.28.02 | Preliminary Right of Way
DES.190.20 | R/W Plans | R/W Plans are submitted to the Region R/W Plans Office for review and transmittal to HQ for approval in accordance with Plans Preparation Manual (PPM) Divisions 1 and 2 |  | PE.PD.28.03 | R/W Plans
DES.190.30 | Sundry Site Plans | Legal Document/Right of Way Plan showing boundary of property to be acquired by WSDOT that is not adjacent to highway right of way. Typically these would include mitigation sites, stormwater treatment areas, and maintenance sites. |  | PE.PD.28.04 | Sundry Site Plans
DES.190.40 | DNR Plat | Legal Document prepared by WSDOT HQ R/W Plans Office showing a survey of property to be acquired from the Department of Natural Resources - Either uplands or aquatic |  | PE.PD.28.05 | DNR Plat
DES.190.50 | Monumentation Map | The official state survey document for state highway R/W alignment, see Plans Preparation Manual (PPM) Divisions 1 and 2 |  | PE.PD.28.06 | Monumentation Map
DES.190.60 | Record of Survey | Public Record filed with the County Auditor used to preserve the evidence of land surveys. The content and format of Record of Surveys are prescribed by law. |  | PE.PD.28.07 | Record of Survey
DES.190.70 | Land Corner Records | Written record of corner information as prescribed by the Department of Natural Resources, used to perpetuate or establish land corners and their accessories. |  | PE.PD.28.08 | Land Corner Records
DES.190.80 | Permit to Destroy | Application made to Department of Natural Resources requesting permission to remove or destroy monuments or make them inaccessible. |  | PE.PD.28.09 | Permit to Destroy
DES.190.90 | Ownership Interests and Encumbrances (Title Reports) | A legal records that defines property interest and boundaries needed to prepare the R/W Plans. |  | PE.PD.28.10 | Ownership Interests and Encumbrances (Title Reports)
DES.190.100 | Right-of-Way Project Funding Estimate (PFE) | The Project Funding Estimate (PFE) is submitted to Program Management for funding approval to begin the RW phase of the project. All RW labor costs associated with preparation of the PFE. Ideally, it is completed by an appraiser, an appraisal reviewer, and a relocation expert and is prepared for every project in which right of way will be acquired. |  | PE.PD.28.11 | Right-of-Way Project Funding Estimate (PFE)
DES.190.110 | Right of Entry | Field investigations and field explorations, other than land surveying, that are obtrusive in nature require a Right of Entry from the property owner. RCW 47.01.170 |  | PE.PD.28.12 | Right of Entry
DES.190.120 | Right of Way and Limited Access Plan Approval | The checking of Right of Way and Limited Access plans against technical standards for the project and the preparation of federal and state Right of Way agreements. Review and approval of Right of Way and Limited Access revisions requested from Region. Includes Region and HQ review, certification to FHWA, and FHWA approval. |  | PE.PD.28.13 | Right of Way and Limited Access Plan Approval
DES.190.130 | R/W Plan Approved | Milestone- HQ R/W Plans Section makes the final review and then the Plan is stamped & signed by the responsible Project Engineer. Right of Way acquisition cannot begin without plan approval. See Plans Preparation Manual (PPM) Divisions 1 and 2. |  | PE.PD.28.14 | R/W Plan Approved
EV | Environmental Review and Permitting | Summary task for all environmental review and permitting. See Environmental Procedures Manual (EM) Parts 4 and 5 Chapters 400 and 500. |  | PE.EV | Environmental Review and Permitting
EV.10 | Endangered Species Act Compliance | All projects with a federal nexus must comply with ESA. EM Chapter 436 Fish, Wildlife, and Vegetation |  | PE.EV.01 | Endangered Species Act Compliance
EV.10.10 | Biological Assessment or No Effect Letter | Assessment/analysis prepared by project biologist. It describes how a project will be built, what conditions will be met, and when they will be done. EM Chapter 436 Wildlife, Fish, and Vegetation |  | PE.EV.01.01 | Biological Assessment or No Effect Letter
EV.10.20 | BA Submitted to NOAA/NMFS and USFWS | Milestone: documentation submitted to federal agency. National Oceanographic and Atmospheric Administration; National Marine Fisheries Service; United States Fish and Wildlife Service. |  | PE.EV.01.02 | BA Submitted to NOAA
|  |  | Combined into EV.10.20 | PE.EV.01.03 | BA Submitted to USFWS
EV.10.30 | Consultation with NOAA and USFWS | EM Chapter 436 Fish, Wildlife and Vegetation |  | PE.EV.01.04 | Consultation with NOAA
|  |  | Combined into EV.10.30 | PE.EV.01.05 | Consultation with USFWS
EV.10.40 | NOAA and USFWS Biological Opinion or Concurrence Letter | Milestone– The concurrence letter/BO documents resource agency agreement with project design and mitigation measures. |  | PE.EV.01.06 | NOAA Biological Opinion or Concurrence Letter
EV.10.50 | USFW Biological Opinion or Concurrence Letter | Milestone– The concurrence letter/BO documents resource agency agreement with project design and mitigation measures. |  | PE.EV.01.07 | USFW Biological Opinion or Concurrence Letter
EV.20 | Section 106 & EO 05-05 Compliance | Summary task for Section 106 and EO 05-05 Compliance tasks other than the Cultural Resources Discipline Report |  | PE.EV.02 | Section 106 & EO 05-05 Compliance
EV.20.10 | Section 106 & EO 05-05 Compliance Exemption Determination | EM Chapter 456 Cultural Resources |  | PE.EV.02.01 | Section 106 & EO 05-05 Compliance Exemption Determination
EV.20.20 | Section 106 & EO 05-05 Compliance Area of Potential Effect Map | EM Chapter 456 Cultural Resources |  | PE.EV.02.02 | Section 106 & EO 05-05 Compliance Area of Potential Effect Map
EV.20.30 | Cultural Resources Survey/Effect Determination | EM Chapter 456 Cultural Resources |  | PE.EV.02.03 | Cultural Resources Survey/Effect Determination
EV.20.40 | Section 106 & EO 05-05 Letter of Concurrence or Memorandum of Agreement | EM Chapter 456 Cultural Resources |  | PE.EV.02.04 | Section 106 & EO 05-05 Letter of Concurrence or Memorandum of Agreement
EV.20.50 | Section 106 Project Scoping and Internal Review | Review of GIS and existing documentation by Cultural Resource Specialist to ascertain presence/absence of known sites in project area. Review required prior to soil disturbance (e.g. wetland delineation, Geotech boring, or hazardous material recon). |  | PE.EV.02.05 | Section 106 Project Scoping and Internal Review
EV.20.60 | Initial Tribal Consultation | Refer to Environmental Manual 456.05 and 530.04. Follow the WSDOT Section 106 Flow Chart (Figure 456) as guidance for implementing Tribal Consultation. Initiates the formal consultation process with Tribes and other Interested Parties. |  | PE.EV.02.06 | Initial Tribal Consultation
EV.30 | Discipline Reports | Summary Task: Discipline reports and other studies prepared by WSDOT Regions or consultants to document environmental investigations called for in the EM Chapters 420-459 |  | PE.EV.10 | Discipline Reports
EV.30.10 | Geology & Soils | Discipline Report. EM Chapter 420 Earth (Geology & Soils) |  | PE. EV.10.01 | Geology & Soils Discipline Report
EV.30.20 | Air Quality | Discipline Report. EM Chapter 425 Air |  | PE.EV.10.02 | Air Quality Discipline Report
EV.30.30 | Surface Water | Discipline Report. EM Chapter 430 Surface Water |  | PE.EV.10.03 | Surface Water Discipline Report
EV.30.40 | Groundwater | Discipline Report. EM Chapter 433 Groundwater |  | PE.EV.10.04 | Groundwater Discipline Report
EV.30.50 | Floodplain | Discipline Report. EM Chapter 432 Floodplain |  | PE.EV.10.05 | Floodplain Discipline Report
EV.30.60 | Wildlife, Fish & Vegetation | Discipline Report. EM Chapter 436 Fish, Wildlife & Vegetation. |  | PE.EV.10.06 | Wildlife, Fish & Vegetation Discipline Report
EV.30.70 | Wetland | Discipline Report. EM Chapter 431 Wetlands --Wetland Inventory Report --Wetland and Stream Assessment --NEPA/SEPA Mitigation Memo --Critical Area Report --Jurisdictional Ditch Memorandum --Conceptual Wetland Mitigation Plan --Draft Wetland Mitigation Plan --Final Wetland Mitigation Plan |  | PE.EV.10.07 | Wetland Discipline Report
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.01 | Wetland Inventory Report
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.02 | NEPA/SEPA Mitigation Memo
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07 .03 | Critical Area Report
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.04 | Jurisdictional Ditch Memorandum
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.05 | Conceptual Wetland Mitigation Report/Plan
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.06 | Draft Wetland Mitigation Report/Plan
|  |  | Combined into EV.30.70 wetland | PE.EV.10.07.07 | Final Wetland Mitigation Report/Plan
EV.30.80 | Energy | Discipline Report. EM Chapter 440 Energy |  | PE.EV.10.08 | Energy Discipline Report
EV.30.90 | Noise | Discipline Report. EM Chapter 446 Noise Noise Analysis Report (special studies) |  | PE.EV.10.09 | Noise Discipline Report
|  |  | Combined into EV.30.90 | PE.EV.10.09.01 | Noise Analysis Report
EV.30.100 | Hazardous Materials | Discipline Report. EM Chapter 447 Hazardous Materials --Phase l Environmental Site Assessment (ISA) --Phase ll Environmental Site Assessment (PSI) --Phase lll Environmental Site |  | PE.EV.10.10 | Hazardous Materials Discipline Report
|  |  | Combined into EV.30.100 | PE.EV.10.10.01 | Phase l Environmental Site Assessment (ISA)
|  |  | Combined into EV.30.100 | PE.EV.10.10.02 | Phase ll Environmental Site Assessment (PSI)
|  |  | Combined into EV.30.100 | PE.EV.10.10.03 | Phase lll Environmental Site
EV.30.110 | Land Use | Discipline Report. EM Chapter 455 Land Use and Transportation --Farmland Conversion Package --Section 6(f) Property Conversion Package, EM Chapter 457 --Section 4(f) (Public Lands) Evaluation, EM Chapter 457 |  | PE.EV.10.11 | Land Use Discipline Report
|  |  | Combined into EV.30.110 | PE.EV.10.11.01 | Farmland Conversion Package
|  |  | Combined into EV.30.110 | PE.EV.10.11.02 | Section 6(f) Property Conversion Package
|  |  | Combined into EV.30.110 | PE.EV.10.12 | Section 4(f) (Public Lands) Evaluation
EV.30.120 | Cultural Resources | Discipline Report. EM Chapter 456 Historic, Cultural, and Archeological Resources --Cultural Resources Survey --Cultural Resources Memorandum of Agreement |  | PE.EV10.13 | Cultural Resources Discipline Report
|  |  | Combined into EV.30.120 | PE.EV.10.13.01 | Cultural Resources Survey
|  |  | Combined into EV.30.120 | PE.EV.10.13.02 | Cultural Resources Memorandum of Agreement
EV.30.130 | Relocation Report | Discipline Report. Refer to EM 458 Social and Economic & Exhibit 458-3 Social Economic and Environmental Justice Discipline Report |  | PE.EV.10.14 | Relocation Report
|  |  | Combined into EV.30.130 | PE.EV.10.14.01 | Social Economic and Environmental Justice Discipline Report
EV.30.140 | Transportation | Discipline Report. EM Chapter 460 Transportation |  | PE.EV.10.15 | Transportation Discipline Report
EV.30.150 | Public Services & Utilities | Discipline Report. EM Chapter 470 Public Services & Utilities |  | PE.EV.10.16 | Public Services & Utilities Discipline Report
EV.30.160 | Visual Impacts | Discipline Report. EM Chapter 459 Visual Impacts; see also DES 140.50. |  | PE.EV.10.17 | Visual Impacts Discipline Report
EV.40 | NEPA/SEPA Compliance | National Environmental Policy Act/State Environmental Policy Act (NEPA/SEPA) If project has any federal nexus (e.g. funding, permit/approval, land) follow NEPA requirements and obtain review of proposed documentation level by FHWA or the appropriate federal transportation agency. If state only funding, follow SEPA requirements. See Environmental Procedures Manual. EM Chapter 400. Consider coordination with Interchange Justification Report and Value Engineering - if applicable. |  | PE.EV.11 | NEPA/SEPA Compliance
EV.40.10 | JARPA | The Joint Aquatic Resource Permit Application (JARPA) form used to apply for individual or multiple regulatory agency permits. The application is used for Corps 404 permits, WDFW HPAs, Ecology 401 Certifications, and several local jurisdiction permits. A completed application form along with the necessary permit drawings and attachments (e.g. NPEA/SEPA Docs, Mitigation Plans, etc.) provides agencies the information necessary for them to issue a permit. Refer to EM Chapter 500 and Directional Memo ESO-09-02 |  | PE. EV. 11.01 | JARPA
EV.40.20 | Early Coordination | Involves preparation and distribution of an Environmental Pre-Scoping Package, including a Draft Coordination Plan and Public Involvement Plan, and Agency Coordination. EM Chapter 400 |  | PE.EV.11.02 | Early Coordination
EV.40.30 | Public Notice | Public notice announcing plans to prepare an EIS or EA, including a Notice of Intent for a NEPA EIS, a Determination of Significance / EIS Scoping Notice for a SEPA EIS, or an EA Scoping Notice for a NEPA EA. EM chapter 400 |  | PE.EV.11.03 | Public Notice
EV.40.40 | Notice of Intent (NOI) | Notice of Intent (NOI) is published in the he Federal Register to begin the NEPA EIS process. Official start date of document production. EM Chapter 400 |  | PE.EV.11.04 | Notice of Intent (NOI)
EV.40.50 | Determination of Significance / EIS Scoping Notice | A PE / EIS Scoping Notice is sent to Ecology for publication in the SEPA Register, and to other agencies, tribes, and others with an interest in the project. EM Chapter 400 |  | PE.EV.11.05 | Determination of Significance / EIS Scoping Notice
EV.40.60 | EIS or EA Scoping | A formal process for engaging the public and agencies in identifying the range of proposed actions, alternatives, environmental elements and impacts, and mitigation measures to be analyzed in an EIS or EA. EM Chapter 400 |  | PE.EV.11.06 | EIS or EA Scoping
EV.40.70 | Draft NEPA/SEPA Environmental Document | A formal environmental document prepared and issued for public and agency comment in accordance with the National Environmental Policy Act (NEPA) and/or State Environmental Policy Act (SEPA). EM Chapter 400. --NEPA or SEPA Draft EIS,SDEIS, or PEEIS --DEIS = Draft Environmental Impact Statement --SDEIS = Supplemental DEIS --PEIS = Programmatic Environmental Impact Statement --SEPA Checklist - Determination of Non-Significance |  | PE.EV.11.40 | Draft NEPA/SEPA Environmental Document
|  |  | Combined into EV.40.70 | PE.EV.11.40.01 | NEPA Draft EIS, SDEIS, or DSEIS
|  |  | Combined into EV.40.70 | PE.EV.11.40.02 | SEPA Draft EIS, SDEIS, or DSEIS
|  |  | Combined into EV.40.70 | PE.EV.11.40.03 | SEPA Checklist / DNS
EV.40.80 | Public Hearing / Comments | A formal or informal hearing and/or comment period that provides the public and agencies with an opportunity to comment on the social, economical, and environmental impacts of a project. See Design Manual Chapter 210. - Environmental Hearing |  | PE.EV.11.50 | Public Hearing / Comments
EV.40.90 | Final NEPA/SEPA Environmental Decision Documents | A formal document prepared and issued to demonstrate compliance with the National Environmental Policy Act and/or State Environmental Policy Act by indicating whether a proposed action constitutes a major action significantly affecting the quality of the environment, and, if so disclosing the nature and significance of any environmental effects of a proposed action, and when preceded by a draft NEPA/SEPA document, includes any comments received on the draft NEPA/SEPA document. EM Chapter 400 --NEPA Categorical Exclusion (CE) per MOU with FHWA --NEPA Documented Categorical Exclusion (DCE) --NEPA Environmental Assessment (EA) or Revised EA --Milestone- Finding of No Significant Impact (FONSI) issued --NEPA or NEPA/SEPA Final Environmental Impact Statement (FEIS) --Milestone- Record of Decision (ROD) issued --NEPA Statute of Limitations (SOL) Notice --NEPA Re-evaluation (no action in 3 years or major scope change) --SEPA Categorical Exclusion (SEPA CE) --SEPA Checklist/Determination of Non-Significance --SEPA FEIS or Final Supplemental (FSEIS) --SEPA Adoption Notice --SEPA Notice of Action Taken (NAT) |  | PE.EV.11.60 | Final NEPA/SEPA Environmental Decision Documents
|  |  | Combined into EV.40.90 | PE.EV.11.60.01 | NEPA CE (ERS)
|  |  | Combined into EV.40.90 | PE.EV.11.60.02 | NEPA DCE (ECS)
|  |  | Combined into EV.40.90 | PE.EV.11.60.03 | NEPA EA or Revised EA
|  |  | Combined into EV.40.90 | PE.EV.11.60.04 | FONSI Issued
|  |  | Combined into EV.40.90 | PE.EV.11.60.05 | NEPA FEIS or FSEIS
|  |  | Combined into EV.40.90 | PE.EV.11.60.06 | ROD
|  |  | Combined into EV.40.90 | PE.EV.11.60.07 | NEPA Statute of Limitations (SOL) Notice
|  |  | Combined into EV.40.90 | PE.EV.11.60.08 | NEPA Re-evaluation
|  |  | Combined into EV.40.90 | PE.EV.11.60.09 | SEPA CE
|  |  | Combined into EV.40.90 | PE.EV.11.60.10 | SEPA Checklist / DNS
|  |  | Combined into EV.40.90 | PE.EV.11.60.11 | SEPA FEIS or FSEIS
|  |  | Combined into EV.40.90 | PE.EV.11.60.12 | SEPA Adoption Notice
|  |  | Combined into EV.40.90 | PE.EV.11.60.13 | SEPA Notice of Action Taken (NAT)
EV.40.100 | Environmental Review Documentation Complete | Milestone-For reporting purposes, the environmental review documentation is considered complete on the date that all necessary National and State Environmental Policy Act (NEPA/SEPA) documentation has been submitted by WSDOT to the appropriate regulatory agency for approval after being processed through WSDOT Headquarters. See Project Control & Reporting Manual. EM Chapter 400 |  | PE.EV.18 | Environmental Review Documentation Complete
|  |  | Deleted | PE.EV.19 | Environmental Review Documentation Approved
EV.50 | Environmental Permits | Identify, apply for and obtain environmental permits required for the project. Permit requirements are scoped as part of the Environmental Review Summary. See Environmental Manual Chapter 500 and associate webpages for procedures. See WSDOT Environmental Permitting website https://www.wsdot.wa.gov/Environment/Permitting/ |  | PE.EV.21 | Environmental Permits
EV.50.10 | Corps Section 404 Permit | This permit is needed for discharging, dredging, or placing fill within waters of the United States (including navigable waters, wetlands, lakes, rivers, streams, tributaries, and jurisdictional ditches). Responsible Agency: Army Corps of Engineers. For additional information see the WSDOT Permits web page: http://www.wsdot.wa.gov/Environment/Programmatic/FSLPermits.htp |  | PE.EV.21.01 | Corps Section 404 Permit
EV.50.20 | Corps Section 10 Permit | This permit is needed for any work in, over, or under navigable water (e.g., rechanneling, piers, wharves, dolphins, bulkheads, buoys, etc.). Responsible Agency: Army Corps of Engineers. |  | PE.EV.21.02 | Corps Section 10 Permit
EV.50.30 | Coast Guard Section 9 Permit | This permit is needed for construction or modification of a bridge or causeway across a navigable water of the U.S. (includes temporary bridges over navigable waters). Responsible Agency: Coast Guard. |  | PE.EV.21.03 | Coast Guard Section 9 Permit
EV.50.40 | Coastal Zone Management Certification | Projects that need a federal license or federal permit and occur within any of Washington's 15 coastal counties require certification from Ecology that the proposed project is consistent with the Coastal Zone Management Program. Responsible Agency: Department of Ecology. |  | PE.EV.21.04 | Coastal Zone Management Certification
EV.50.50 | Hydraulic Project Approval (HPA) | Hydraulic Project Approval (HPA) A permit required for projects that use, divert, obstruct, or change the natural flow or bed of waters of the state. Includes bed reconfiguration, all construction or other work water work, under and over the ordinary high water line, including dry channels, and may include projects landward of the ordinary high water line (e.g., activities outside the ordinary high water line that will directly impact fish life and habitat, falling trees into streams or lakes, bridge maintenance, dike construction, etc.) Responsible Agency: Washington State Dept. of Fish and Wildlife. |  | PE.EV.21.05 | Hydraulic Project Approval (HPA)
EV.50.60 | Section 402 NPDES Permit | A Clean Water Act Section 402 National Pollutant Discharge Elimination System (NPDES) permit is needed for a discharge of pollutants into waters of the U.S., including drains, ditches, wetlands, creeks, rivers, lakes, and marine waters. The NPDES permit most commonly required is a construction stormwater general permit required for any construction activity that disturbs one acre or more and may result in a discharge of stormwater to such waters. Responsible Agency: Department of Ecology. |  | PE.EV.21.06 | Section 402 NPDES Permit
EV.50.70 | State Waste Discharge | A State Wastewater Discharge Permit is required for a discharge of wastewater to the ground or a discharge of industrial process water to a municipal treatment plant. Responsible Agency: Department of Ecology. |  | PE.EV.21.07 | State Waste Discharge
EV.50.80 | Section 401 Water Quality Certification | This federal permit/license is required for projects that receive a Section 404 permit from the U.S. Army Corps of Engineers or a Coast Guard permit for activities that might result in a discharge of dredge or fill material into water or non-isolated wetlands or excavation in water or non-isolated wetlands. Responsible Agency: Department of Ecology; and the Environmental Protection Agency (EPA) on federal and tribal land, except where tribes have been delegated such authority on their tribal land. |  | PE.EV.21.08 | Section 401 Water Quality Certification
EV.50.90 | Short-Term Water Quality Modification | Issued as a condition of the Individual Section 401 Water Quality Certification for projects that need short-term modification to the mixing zone distance for measuring water quality turbidity. Responsible Agency: Department of Ecology. |  | PE.EV.21.09 | Short-Term Water Quality Modification
EV.50.100 | Forest Practices Permit | Permit required to remove timber or convert timber land. Responsible Agency: Department of Natural Resources. |  | PE.EV.21.10 | Forest Practices Permit
EV.50.110 | Floodplain Development Permit | A permit for any construction activity within the 100 year flood plain as defined by FEMA mapping. Responsible Agency: Department of Ecology, Cities and Counties. |  | PE.EV.21.11 | Floodplain Development Permit
EV.50.120 | Critical Area Ordinance Permit | Local approval or permits may be required for projects impacting areas defined as "critical" by counties and cities under the Growth Management Act (GMA), including wetlands, aquifer recharge areas, wellhead protections areas, frequently flooded areas, geographically hazardous areas, fish and wildlife habitat, and conservation areas. Responsible Agency: Counties and Cities. |  | PE.EV.21.12 | Critical Area Ordinance Permit
EV.50.130 | Air Quality Permit | This permit allows temporary air pollution above allowed levels for land clearing burns, demolition of structures containing asbestos, and operation of portable asphalt batching equipment, rock crushers, and Portland cement plants. Responsible agency: Ecology, Clean Air Agencies, fire protection agencies. |  | PE.EV.21.13 | Air Quality Permit
EV.50.140 | Noise Variance | Construction and maintenance activities during nighttime hours may require a variance from local noise ordinances. Daytime noise from construction is usually exempt. Responsible Agency: Counties and Cities. |  | PE.EV.21.14 | Noise Variance
EV.50.150 | Shoreline Permit/Exemption | Required for any contract requiring work within 200 feet of a shoreline of the state as defined by the local agency with jurisdiction. Responsible Agency: Department of Ecology, Cities and Counties. |  | PE.EV.21.15 | Shoreline Permit/Exemption
EV.50.160 | Land Use Permit | Construction and maintenance activities may require a Land Use Permit in select cases. Examples include a conditional use permit, unclassified use permit, or variance. Responsible Agency: Counties and Cities. |  | PE.EV.21.16 | Land Use Permit
EV.50.170 | Environmental Permit for Field Exploration | Field exploration may require permits to complete. Permits need to be provided by the Project Office to HQ Geotechnical Office/Region Materials Office to enable required field work to be started. |  | PE.EV.21.17 | Environmental Permit for Field Exploration
EV.50.180 | Clearing, Grading, & Building Permit | Construction and maintenance activities outside the roadway may require a permit under local laws and codes. Roadway construction is usually exempt. Responsible Agency: Counties and Cities. |  | PE.EV.21.18 | Clearing, Grading, & Building Permit
EV.50.190 | Field Exploration Permits/Agreements/Clearances | To support the work of the Geotechnical Office (GO) and/or the Region Materials Office (RMO), a Field Exploration program may be conducted. The Field Exploration Program will include site visits by staff from the GO and RMO, and may include the drilling of subsurface borings, excavation of test pits, geophysical field tests, groundwater monitoring, pump tests, and infiltration tests. The Project Office will need obtain the permits, rights of entry, and clearances to perform this work. Permits, clearances, and agreements to be supplied by the Region might include the following: • HPA • Shoreline permits • Tribal lands and waters • Railroad easement and right of way • City, county, or local agency use permits • Sensitive area ordinance permits • Environmental and Archeological Clearances | Added
EV.50.200 | Archaeological Resources Protection Permit | This permit is required for excavation or removal of archaeological resources from tribal or federal land. Responsible agency: Tribes and federal land owners. |  | PE.EV.21.20 | Archaeological Resources Protection Permit
EV.50.210 | Archaeological Excavation and Removal Permit | This permit is required for digging, excavating, altering, defacing, or removing archaeological objects or sites; historic archaeological resources; or native Indian graves, cairns, or painted or glyptic records. Responsible agency Washington State Department of Historic Preservation. |  | PE.EV.21.21 | Archaeological Excavation and Removal Permit
EV.50.220 | Tribal Approvals & Permits | All environmental permits and approvals for which tribes have been delegated authority that are not covered by another item in the MDL. EM Chapter 530 |  | PE.EV.21.22 | Tribal Approvals & Permits
EV.50.230 | Migratory Bird Treaty Act Evaluation | This federal law, administered by the USFWS, makes it unlawful to take, import, export, possess, sell, purchase, or barter any migratory bird, with the exception of the taking of game birds during established hunting seasons. The law also applies to feathers, eggs, nests, and products made from migratory birds. This law is of particular concern when birds nest on bridges, buildings, signs, and ferry dock structures. |  | PE.EV.21.23 | Migratory Bird Treaty Act Evaluation
EV.50.240 | Bald and Golden Eagle Protection Act Evaluation | This federal law, administered by the USFWS, makes it unlawful to take, import, export, sell, purchase, or barter any bald or golden eagle, their parts, products, nests, or eggs. "Take” includes pursuing, shooting, poisoning, wounding, killing, capturing, trapping, collecting, molesting, or disturbing the eagles. |  | PE.EV.21.24 | Bald and Golden Eagle Protection Act Evaluation
EV.50.250 | Marine Mammal Protection Act Permit | This Federal Law, administered by NOAA, prohibits the take of marine mammals in U.S. Waters. WSDOT projects that involve marine waters; including Puget Sound, Georgia Basin and the Columbia River up to Bonneville Dam, must consider potential impacts to marine mammals. A permit may be required from NOAA for Level A harassment (injury level take) or Level B harassment (disturbance level take). There are two permit options: a Letter of Authorization (good for 5 years) or an Incidental Harassment Authorization (good for 1 year). An Endangered Species Act (ESA) consultation is required in coordination with the MMPA application to receive either permit. The application is done in report format and includes: potential project-specific impacts to marine mammals, species/numbers of marine mammals in the project area, a request for take levels, and a mitigation proposal. For additional information see EPM Chapter 436. |  | PE.EV.21.25 | Marine Mammal Protection Act Permit
EV.50.260 | Miscellaneous Permits & Approvals | Examples include: Federal Aviation Administration (FAA), sole source aquifer, water use permit, etc. |  | PE.EV.21.26 | Miscellaneous Permits & Approvals
EV.50.270 | Environmental Permits Received | Milestone- All environmental permits acquired for project to go to Ad/Construction. |  | PE.EV.29 | Environmental Permits Received
EV.60 | Environmental Commitment File | Identify and document all environmental commitments for the project. See Environmental Procedures Manual Chapters 490 and 590 for procedures. |  | PE.EV.31 | Environmental Commitment File
EV.60.10 | Environmental Commitments Meeting | A project-level meeting between the Design, Construction, Plans, and Environmental Offices used to incorporate commitments into contracts. |  | PE.EV.31.01 | Environmental Compliance Meeting
EV.60.20 | Environmental Compliance Notes Finalized | Milestone - All Environmental Compliance Notes are finalized and entered into the Commitment Tracking System. The Commitment Tracking System is a WSDOT database that allows you to store commitments in a secure computer network server, plus manage the responsibility (WSDOT or contractor) and implementation method (guidance document or contract) for the commitment. It also allows you to store compliance records, document the status, and report details about commitments from their inception through project delivery and on to maintenance. |  | PE.EV.31.02 | Environmental Compliance Notes Finalized
EV.60.30 | Environmental Commitments List (Design Build Only) | A project-specific list of environmental commitments prepared by WSDOT for inclusion in the Request for Proposal (RFP). The Environmental Commitment List includes all of the known or anticipated environmental commitments for which the Design-Builder will be responsible for fulfilling. | Added
DB | Design-Build Procurement | The process resulting in an executed contract that represents the best value to the public. All work involved in the solicitation for interest, preparation and distribution of the RFP package, including the request for qualifications (RFQ), evaluation criteria, selection procedures and technical requirements for the design and construction. (Note: Review Contract Ad & Award and Construction Milestones for additional Design Build Reporting Milestones.) | Moved from Design | PE.PD.44 | Design-Build Procurement
DB.100 | Design Build Contract Package | The document package issued by WSDOT requesting submittal of proposals for the Project and providing information relevant to the preparation and submittal of proposals, including Instructions to Proposers, Contract Documents and Reference Documents. | Added
DB.100.10 | Request For Proposal Chapter & Appendix | DESIGN-BUILD - WSDOT Design office will request specialty group provide RFP criteria for the Chapter 1 Proposal. This may also include an Appendix referenced in the RFP, the term Appendix (Appendices) refers to the documents listed in Appendix A1 of the Technical Requirements. | Added
DB.100.20 | Conceptual Plans | Conceptual Plans: Conceptual plans are developed to the point that we have enough information to gain environmental approval, acquire permits, acquire right of way, and to demonstrate that our contract requirements are feasible. Typically to 15-30%, but can be more or less depending on the project scope/discipline. Each discipline may be developed to a different level. Basic Configuration needs to be defined in this process. | Added
DB.100.30 | Basic Configuration | The Basic Configuration are the elements of the Conceptual Plans which the Design-Builder may rely on. These elements may be modified by Pre-Approved Design Variances/Analyses or Alternative Technical Concepts (ATC’s). | Added
DB.100.40 | Reference Documents | The non-binding reference documents included in the Request for Proposal. These documents are provided for information purposes to assist the Proposers in preparing their Proposals, but the Reference Documents do not represent requirements binding on the Design-Builder. | Added
DB.100.50 | Contract Documents | Design Build Contract Documents include: -- Request for Qualifications (RFQ) -- Request for Proposal (RFP): Containing Instruction to Proposers (ITP), Contract Form, General Provisions (Ch. 1), Technical Requirements (Ch. 2) and Appendices | Added
DB.200 | Statement of Qualification Phase | WSDOT will use a two-step procurement process to select a design-build contractor (Design-Builder) to deliver the Project. The issuance of this RFQ is part of the first step to solicit information from potential design-builders in the form of SOQs. WSDOT will evaluate and score submitted SOQs to determine which Submitters are the most highly qualified to deliver the Project. WSDOT will short-list three to five of the most highly qualified Submitters to advance to the second step in the procurement for the Proposal Phase. | Added
DB0.200.10 | Request For Qualifications (RFQ) Preparation | The Request For Qualifications (RFQ) is a document asking interested proposing teams to submit a Statement of Qualifications (SOQ). The RFQ gives a general description of the project and the attributes desired of prospective proposers. It provides specific terms for the submittal of the SOQ and how it will be scored. |  | PE.PD.44.01 | Request For Qualifications (RFQ) Preparation
DB0.200.20 | RFQ Issue Date | Milestone - Date the RFQ is issued by WSDOT. | Added
DB0.200.30 | Publish Request for Statements of Qualifications SOQ | Milestone - The date the Request for Statements of Qualifications (SOQ) is due to WSODT. |  | PE.PD.44.02 | Publish Request for Statements of Qualifications (RFQ)
DB0.200.40 | Voluntary Submitter's Meeting | WSDOT will hold an informational meeting for potential Submitters regarding the SOQ. | Added
DB0.200.50 | Deadline for submitting RFQ questions | Milestone - Design Builder teams submit formal questions for answers from WSDOT. | Added
DB0.200.60 | Deadline for WSDOT response to RFQ questions | Milestone - WSDOT supplies formal answers to questions | Added
DB0.200.70 | SOQ Due Date | Milestone - The Design Builder prepares their Statement of Qualifications in response to the RFQ. | Added
DB0.200.80 | Evaluate Statement of Qualifications (SOQ) | Design Builders are scored on their qualifications and experience of Key Personnel and the Major Participants against the project goals. Major Participants include the Prime and subs doing 20% or more of the work; Key Personnel are people filling identified positions (Project Manager, Design Manager, Construction Manager). Key part of the process is reference checks, relies on candid, specific and objective responses from PE’s and EMs. WSDOT evaluates the SOQ based on criteria included in RFQ and the Evaluation Manual. The Evaluation Manual is created by the project team based on the requirements of the RFQ and guides the evaluation team. The Team evaluates the SOQ’s and provides a score. | Added
DB0.200.90 | Shortlist Bidders Selected | Milestone - The date the shortlist of selected bidders is issued; these bidders may submit a proposal in response to the subsequent RFP. This is the result of the review of the SOQ documents submitted by prospective proposers. |  | PE.PD.44.03 | Shortlist Bidders Selected
DB.300 | Proposal Phase | WSDOT will issue a Request for Proposal (RFP) for the Project to the short-list Submitters (Proposers). The Request for Proposal requires Proposers to address how they plan to deliver the project (Specific Approach). WSDOT may award a Design Build Contract for the Project to the Proposer offering the apparent best value, to be determined as described in the RFP. | Added
DB.300.10 | Request For Proposal (RFP) preparation | The final Request for Proposals document is the official notice to interested proposing teams to prepare and submit proposals, with the project's technical criteria and requirements. The issuance of the RFP is considered the Advertisement of the contract - see that Performance Reporting Major Milestone. |  | PE.PD.44.04 | Request For Proposal (RFP) preparation
DB.300.20 | Issue RFP | Milestone - The date the Request for Proposals (RFP) is issued or circulated. |  | PE.PD.44.05 | Publish Request for Proposals (RFP)
DB.300.30 | Voluntary Proposer's Meeting | WSDOT will hold an informational meeting for proposer's regarding the RFP. | Added
DB.300.40 | Alternate Technical Concept Submittal Deadline | Milestone - Alternative Technical Concept (ATC) – Concepts proposed by the Design-Builder and approved by WSDOT pursuant to the Instructions to Proposers, which modify the Basic Configuration or other Contract requirements. WSDOT may approve changes to the contract that are determined to be “Equal or Better” to the RFP. | Added
DB.300.50 | Deadline for Submitting Proposers’ questions | Milestone - Design Builder teams submit formal questions for answers from WSDOT. | Added
DB.300.60 | Deadline for WSDOT response to Proposers’ questions | Milestone - WSDOT supplies formal answers to questions | Added
DB.300.70 | Proposals Due Date | Milestone - The date specified for the delivery of the Proposals in the Instructions to Proposers. Proposals include the technical proposal and the price proposal which is sealed until bid opening. | Added
DB.300.80 | Request For Proposal (RFP) Evaluation | A systematic evaluation and scoring of the technical portions of the proposals. Teams of Advisors review specific sections of the proposals in accordance with the terms of the RFP and ITP and make comments and assign score values. They report to the Evaluators who compile and finalize the technical score for each of the proposals. This activity begins on the Proposal Due Date. |  | PE.PD.44.06 | Request For Proposal (RFP) evaluation
DB.300.90 | Best Value Determination | Milestone - The date of the bid opening for DB Proposals. The DB Price proposals are opened, then combined with the technical score to yield a net or best value. Generally, the technical score is subtracted from the price of qualified proposals to arrive at the net value. An Apparent Best Value proposer is announced at this point. |  | PE.PD.44.07 | Best Value Determination
DB.300.100 | Region Betterments Supplied | Betterments – With respect to the Technical Proposal, any item included in the Design-Builder’s Technical Proposal that clarifies the Design-Builder’s intention to exceed a requirement included in the Contract Documents. The project is awarded after we the Region provides a list of betterments and funding approval proposal amount from ABV. A betterment is something that contractor commits to in the Technical Proposal that exceeds the contract requirements. | Added
DB.300.110 | Notice to Proceed Issued (NTP) | Milestone - The written authorization issued by WSDOT that permits the Design-Builder to commence performance of the Work. | Added
PSE | Plans, Specifications and Estimates | Development of the Contract Plans, specifications and estimate for bid letting (parent or summary activity). | Moved from Design | PE.PD.80 | Plans, Specifications and Estimates
PSE.10 | Contract Plan Sheets Preparation | Development of the Contract Plan sheets. See Plans Preparation Manual (PPM) M22-31 for full list of Plans and sequence. This task may be used as a hammock task for uniform resource loading the effort involved with contract plan preparation. This task is used when the plan sheet deliverables are constrained by other activities or dates and are not resource loaded. When used, this task will have no constraints, in order to have the task span the entire duration of plan preparation (parent or summary activity). |  | PE.PD.50 | Contract Plan Sheets Preparation
PSE.10.10 | Index | Required on all projects with 30 plan sheets or more, see Plans Preparation Manual (PPM) 400.06 and 400.06(3) |  | PE.PD.50.01 | Index
PSE.10.20 | Vicinity Map | A plan sheet that is required for all projects to show the approximate location of the project on the state route, see Plans Preparation Manual (PPM) 400.06 |  | PE.PD.50.02 | Vicinity Map
PSE.10.30 | Summary of Quantities | These plans are a complete tabulation of all bid items and pay quantities required for the project, see Plans Preparation Manual (PPM) 400.06 |  | PE.PD.50.03 | Summary of Quantities
PSE.10.40 | Reclamation Plans | Plans that are required on all WSDOT projects that contain a WSDOT furnished material source, including borrow, pit, quarry, stockpile, waste site, and reclamation plans. See Plans Preparation Manual (PPM) 700.05(34); 400.06(6) |  | PE.PD.50.04 | Reclamation Plans
PSE.10.50 | Roadway Section Plans | Plans that show the geometric roadway cross section from subgrade up to finished grade, see Plans Preparation Manual (PPM) 400.06(7) |  | PE.PD.50.05 | Roadway Section Plans
PSE.10.60 | Grading Section Plans | Plans that show finished ground contours, see Plans Preparation Manual (PPM) 400.06(8) |  | PE.PD.50.06 | Grading Section Plans
PSE.10.70 | Stage Construction Plans | These plans show the different stages required to construct the project. See Plans Preparation Manual (PPM) 400.06 |  | PE.PD.50.07 | Stage Construction Plans
PSE.10.80 | Alignment / Right of Way Plans | Plans that contain horizontal alignment & R/W information, see Plans Preparation Manual (PPM) 400.06(10) |  | PE.PD.50.08 | Alignment / Right of Way Plans
PSE.10.90 | Quantity Tabs | Plans that tabulate quantities and identifies locations and notes pertaining to specific bid items, see Plans Preparation Manual (PPM) 400.06(9); Appendix 1 |  | PE.PD.50.09 | Quantity Tabs
PSE.10.100 | Site Preparation Plans | These plans show existing topography, removal & demolition work, see Plans Preparation Manual (PPM) 400.06(11) |  | PE.PD.50.10 | Site Preparation Plans
PSE.10.110 | Existing Utilities Plan | This is an extension of the Site Preparation Plan and is only required if the existing utilities are so extensive that they cannot be clearly shown of the site preparation plans. See Plans Preparation Manual (PPM) 400.06(16) |  | PE.PD.50.11 | Existing Utilities Plan
PSE.10.120 | Environmental and/or Wetland Mitigation Plans | A plan sheet that identifies wetland mitigation. See Plans Preparation Manual (PPM) 400.06(19) |  | PE.PD.50.12 | Environmental and/or Wetland Mitigation Plans
PSE.10.130 | Roadway Profiles | Plans that identify a change in the vertical alignment of the roadway, see Plans Preparation Manual (PPM) 400.06(12) |  | PE.PD.50.13 | Roadway Profiles
PSE.10.140 | TESC Plans | Temporary Erosion and Sediment Control plans are required if the project involves land disturbance. To include Q-tabs, Plan sheets, and Details. see Plans Preparation Manual (PPM) 700.05(30); 400.06 |  | PE.PD.50.14 | TESC Plans
PSE.10.150 | Drainage Plans | Plans that show how the drainage system relates to the rest of the project, including Drainage Structure Notes, Drainage Profiles, and Drainage Details. See Plans Preparation Manual (PPM) 400.06(14)(15)(16) |  | PE.PD.50.15 | Drainage Plans
PSE.10.160 | Landscape & Roadside Restoration | Plans that identify Wetland Mitigation Plans, Wetland Mitigation/Landscape Plan Sheet. | Added
PSE.10.170 | Utility Plans | Plans that are required when there is work on existing utilities as part of the contract, to include Utility Structure Notes and utility details. See Plans Preparation Manual (PPM) 400.06 |  | PE.PD.50.16 | Utility Plans
PSE.10.180 | Interchange Contours | Plan sheets showing the contour grading of interchanges. See Plans Preparation Manual (PPM) 400.06(17) |  | PE.PD.50.17 | Interchange Contours
PSE.10.190 | Paving Plans | Plans that show total roadway widths to be paved, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06(18) |  | PE.PD.50.18 | Paving Plans
PSE.10.200 | Pavement Marking Plans | Plans that show the type and location of pavement markings for the project, including Q-tabs and details. See Plans Preparation Manual (PPM) 400.06(18) |  | PE.PD.50.19 | Pavement Marking Plans
PSE.10.210 | Minor Structures Plans | Plans that show the information required to construct retaining walls, etc. Includes Q-tabs, profiles, and details. See Plans Preparation Manual (PPM) 400.06(21) |  | PE.PD.50.20 | Minor Structures Plans
PSE.20 | Contract Specifications Development | Development of Contract Provisions. See Plans Preparation Manual (PPM). |  | PE.PD.60 | Contract Specifications Development
PSE.20.10 | Contract Specifications | Development of Contract Provisions, Amendments, General Special Provisions, and appendices. See Plans Preparation Manual (PPM) Division 6. |  | PE.PD.60.01 | Contract Specifications
PSE.20.20 | Summary of Geotechnical Conditions | HQ Geotechnical and/or Region Materials prepares summary of geotechnical conditions for inclusion into the PS&E as Appendix B. The Summary is prepared as part of the PS&E Review. |  | PE.PD.60.02 | Summary of Geotechnical Conditions
PSE.30 | Construction Estimate Development | Development of Contract Estimates for costs and time. See Plans Preparation Manual (PPM). |  | PE.PD.65 | Construction Estimate Development
PSE.30.10 | Basis of Estimate (BOE) | The BOE is characterized as the one deliverable that defines the scope of the project, and ultimately becomes the basis for change management. When the BOE is prepared correctly, our customers can use it to understand and assess the estimate, independent of any other supporting documentation. A well-written BOE achieves these goals by clearly and concisely stating the purpose of the prepared estimate (i.e., cost study, project options, benefit/cost study, funding, etc.), the project scope, pricing basis, allowances, assumptions, exclusions, cost risks and opportunities, and any deviations from standard practices. The BOE is a documented record of pertinent communications that have occurred and agreements that have been made between the estimator and other project stakeholders. |  | PE.PD.65.01 | Basis of Estimate (BOE)
PSE.30.20 | Engineer's Cost Estimate of Construction | An estimate used to initiate funds for the construction activity and to evaluate the contractor's bids, see Plans Preparation Manual (PPM) Division 8. See also DM Chapter 300 |  | PE.PD.65.02 | Engineer's Cost Estimate of Construction
PSE.30.30 | Lump Sum Breakout | Calculations for determining estimate of Lump Sum items. |  | PE.PD.65.03 | Lump Sum Breakout
PSE.30.40 | Working Day Estimate | Contract time determined in accordance with Plans Preparation Manual (PPM) Appendix A6 |  | PE.PD.65.04 | Working Day Estimate
PSE.40 | Construction Permits | Development and documentation of permits from other public agencies for work to be done outside of WSDOT right of way and within other public agency right of way. |  | PE.PD.70 | Construction Permits
PSE.40.10 | Construction Permits | Construction Permits accommodate WSDOT activities on public owned right of way. See Design Manual, Chapter 510. |  | PE.PD.70.01 | Construction Permits
PSE.40.20 | Aquatic Lands Use Authorization | For projects involving aquatic lands contact Real Estate Services. Responsible Agency: Department of Natural Resources. |  | PE.PD.70.02 | Aquatic Lands Use Authorization
PSE.40.30 | Authorization for use of federal land | This permit is required for construction of roads, utility lines, and associated uses, such as staging areas for construction or borrow pits, on federal lands. Responsible agency: USFS and BLM. |  | PE.PD.70.03 | Authorization for use of federal land
PSE.40.40 | Haul Road and Detour Agreement | When the project provides a materials source, or requires traffic to be detoured from the state highway, the region is required to acquire agreements with the owners of the roads (usually cities or counties) that will be used as the haul route or the detour route. See Plans Preparation Manual (PPM) 700.05(14) |  | PE.PD.70.04 | Haul Road and Detour Agreement
PSE.40.50 | Turnback Agreement | Areas for relinquishment are areas that the state acquires for the improvement or construction of roads that will not remain a part of the highway system. See Plans Preparation Manual (PPM) 100.03 |  | PE.PD.70.05 | Turnback Agreement
PSE.50 | Constructability Reviews | To develop a quality project, WSDOT uses a series of reviews at predetermined stages of project development. These reviews, called constructability reviews, attempt to ensure that: project development process is on schedule; project definition and estimates are correct; project is buildable; project is maintainable; and project documents are biddable. |  | PE.PD.75 | Constructability Reviews
PSE.50.10 | Scoping Phase Review | Scoping Phase Review. See Deliverable Expectation Matrix & Project Management Guide http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PD.75.01 | Scoping Phase Review (PDR)
PSE.50.20 | 0% Constructability Review - transitional/design | Transitional / Design Re-Start Review; interdisciplinary.. See Deliverable Expectation Matrix & Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PD.75.02 | 0% Constructability Review
PSE.50.30 | 30% Constructability Review - geometric | Geometric Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PD.75.03 | 30% Constructability Review
PSE.50.40 | 60% Constructability Review - general plans | General Plans Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PD.75.04 | 60% Constructability Review
PSE.50.50 | 90% Constructability Review - contract plans | Contract Plans Review. See Deliverable Expectation Matrix & Project Management Guide (PMG) http://www.wsdot.wa.gov/Projects/ProjectMgmt/ |  | PE.PD.75.05 | 90% Constructability Review
PSE.60 | PS&E Reviews | Plans Specifications & Estimate (PS&E) Reviews. Check for completeness and compatibility between the Plans, Specifications and Estimate. See Deliverable Expectation Matrix/ Project Management Guide |  | PE.PD.80 | PS&E Reviews
PSE.60.10 | Local Agency Review | A check of the plans, specification and estimate by a local governmental or non-governmental agency or tribal nation to ensure compliance with established agreements or memorandum of understandings. |  | PE.PD.80.01 | Local Agency Review
PSE.60.20 | Region PS&E Review | Region Project Office submits PS&E package to Region for review. Includes -- State Materials Justification/Approval -- Proprietary Item Approval |  | PE.PD.80.02 | Region PS&E Review
|  |  | Combined into PSE.60.20 | PE.PD.80.03 | State Materials Justification/Approval
|  |  | Combined into PSE.60.20 | PE.PD.80.04 | Proprietary Item Approval
PSE.60.30 | Final Contract Review | This review (sometimes referred to as a Round Table review) should be scheduled by the PEO when the project is either large, complex with multiple staging, unique construction methods or a shortened PS&E Review period. The review should follow the comments due date within a few work days. The PEO leads the discussion of review comments and maintains the focus of the meeting. The focus of the discussion should be constructability, significant review comments, and the concerns of the Construction PE. As time allows other issues should be discussed. Comments and concerns should be resolved during the discussion; otherwise, key players should be identified to resolve specific issues outside of the round table meeting. | Added
|  |  | Deleted | PE.PD.80.05 | HQ PS&E Review
|  |  | Deleted | PE.PD.80.06 | FHWA PS&E Review
|  |  | Deleted | PE.PD.80.07 | FRA PS&E Review
|  |  | Deleted | PE.PD.80.08 | Federal Transit Agency (FTA) PS&E Review
PSE.60.40 | Final Signed PS&E to Region | Milestone - Project Manager returns stamped and signed AD ready PS&E package to the Region. |  | PE.PD.80.04 | Proprietary Item Approval
PSE.60.50 | Ad Package to Headquarters | Milestone - Final PS&E to HQ with all appropriate attachments as required on the Final Check Sheet, five(5) days prior to the scheduled Ad date. |  | PE.PD.80.05 | HQ PS&E Review
PSE.70 | Project Shelf | Completion milestones and documentation for projects not funded for construction. Re-start milestones for projects coming off the shelf for advertisement. |  | PE.PD.85 | Project Shelf
PSE.70.10 | Incomplete Project to Shelf | Milestone - The date that an incomplete project goes to a holding area (called "the shelf"). This project is not ready for advertisement and will need to undergo further design/adjustments and reviews. |  | PE.PD.85.01 | Incomplete Project to Shelf
PSE.70.20 | AD Ready Project to Shelf | Milestone - The date that a fully designed, reviewed and permitted project goes to a holding area called "the shelf". This project is ready for advertisement without any further adjustments or reviews |  | PE.PD.85.02 | AD Ready Project to Shelf
PSE.70.30 | Shelf to AD Ready | Milestone - Date project is taken off shelf. |  | PE.PD.85.03 | Shelf to AD Ready
PSE.70.40 | Shelf/Ad Ready Letter | A Memo from the Project Engineer to the Assistant Region Administrator for Project Development to formally suspend work on a project until a later date. |  | PE.PD.85.04 | Shelf/Ad Ready Letter
PSE.70.50 | Estimate to Make AD Ready | Estimate of scope, time, and cost to get an incomplete, "shelved", project ready for advertisement |  | PE.PD.85.05 | Estimate to Make AD Ready
PSE.80 | Contract Ad & Award | Advertisement and award of construction contracts. See Ad and Award Manual. |  | PE.PD.90 | Contract Ad & Award
PSE.80.10 | Contracts & Legal | The Ferry Vessels Projects delivered to C&L for review and AD Specification, Contract drawings, and other documents provided to C&L for publishing in Bid Package |  | PE.PD.90.01 | Contracts & Legal
PSE.80.20 | Pre-AD Review | HQ review of pre-PS&E documents and the PS&E within various HQ units. Includes performance of the plans-in-hand inspection with FHWA, preparation of data for securing federal funds for the subsequent approval to expend those funds for a project. |  | PE.PD.90.02 | Pre-AD Review
|  |  | Moved to RES.70 | PE.PD.90.03 | R/W Certification
|  |  | Combined to RES.70 | PE.PD.90.04 | R/W Recertification
PSE.80.30 | Construction Funding Approval | Milestone - Official approval from HQ and FHWA (if federal funds are used) to move ahead with the advertisement of the construction phase of a project |  | PE.PD.90.05 | Construction Funding Approval
PSE.80.35 | Construction Specifications Approved | Milestone - Final approval from HQ of specifications for advertisement of the construction phase of a project | Added
PSE.80.40 | Printing | Reproduction and distribution of plans, specifications, and bid proposal package. Contact HQ Printing Services for information. |  | PE.PD.90.06 | Printing
PSE.80.50 | Project Geotechnical Documentation Package | Printing of pertinent geotechnical reports for sale to prospective bidders. Prepared by HQ Geotechnical and/or Region Materials and printed by HQ Printing Services. |  | PE.PD.90.07 | Project Geotechnical Documentation Package
PSE.80.60 | Advertisement (AD Date) | PERFORMANCE REPORTING MAJOR Milestone- This is the date that WSDOT publicly solicits bids from contractors to construct the project. When a project is advertised, it has a completed set of plans and specifications, along with a construction cost estimate. The Milestone is met on the date of the advertisement. (Note: For Design-Build, the RFP date is reported as the AD date) |  | PE.PD.90.08 | Advertisement (AD Date)
PSE.80.70 | Addenda | Work associated with preparing addendums to our construction contracts that are on advertisement. |  | PE.PD.90.09 | Addenda
PSE.80.80 | Construction Phase Preparation | Work performed during the bid period to prepare for construction including setting project files, sending notifications and RFI from contractors. |  | PE.PD.90.10 | Construction Phase Preparation
PSE.80.90 | Addenda Deadline | Milestone - Date addenda are due in headquarters. 14 calendar days prior to the scheduled bid opening. |  | PE.PD.90.11 | Addenda Deadline
PSE.80.100 | Bid Opening | Milestone - Public opening and reading of sealed bids. (Note: For Design-Build projects, this is reported as the selection date or Best Value Determination.) |  | PE.PD.90.12 | Bid Opening
PSE.80.110 | Award | Milestone - Official notice of award of the contract to the successful bidder. (For Design-Build projects, this is reported as the Contract Award date.) |  | PE.PD.90.13 | Award
PSE.80.120 | Phase Transition & Close | Design to Construction/ Transition . The processes performed to formally terminate all activities of a project or phase, and transfer the completed product to the next phase, normally Construction. See Design Manual Chapter 300. --Plan and Document Archive -Incorporating contract special provisions and plans into the Regional Plan and Document Archive database for historical documentation and data preservation. --Computer Aided Engineering (CAE) Archive - Incorporating electronic engineering files and CAD files into the Computer Aided Engineering (CAE) database. | Added
|  |  | Combined into PSE.80.120 | PE.PD.90.14 | Plan and Document Archive (PDA )
|  |  | Combined into PSE.80.120 | PE.PD.90.15 | Computer Aided Engineering (CAE) Archive
PSE.80.130 | PE Phase End | Milestone - All PE costs are finished and the work order is closed in TRAINS |  | PE.PD.90.16 | PE Phase End
RES | Real Estate Services | The Real Estate Services phase of the project contains all work to acquire rights of way and perform and coordinate all real estate transactions for the department. The process of securing the property or property rights or agreements needed for highway improvements that conforms with Federal and State regulations called the Uniform Act. It includes, but is not limited to fee acquisition, access rights, and easements. This includes the General Project Management, RW Project Management Plan and Consultant Selection/Agreements. |  | RW | Right of Way
|  |  | Combined into PM.01 | RW.PM | Project Management & Overhead - Right of Way
|  |  | Combined into PM.01 | RW.PM.02 | Project Management and Overhead
|  |  | Combined into PM.01 | RW.PM.02.01 | General Project Management (Project Office and Real Estate Services)
|  |  | Combined into PM.01 | RW.PM.02.02 | Redistributed Right of Way Project Management and Overhead (HQ & Region)
|  |  | Combined into PM.01 | RW.PM.03 | Project Management Plan Development & Maintenance
|  |  | Combined into PM.02 | RW.PM.06 | Consultant Selection/Agreements – Real Estate
|  |  | Combined into PM.01 | RW.PM.12 | Other Work for Management and Overhead
|  |  | Deleted | RW.PM.12.01 | Travel To & From the Office to the Job Site
|  |  | Deleted | RW.PM.90 | RW Phase End
|  |  | Moved to Design, now DES.190.130 | RW.PM.01 | R/W Phase Start (Funding Approved)
|  |  | Deleted | RW.PA | Parcel/Agreement (Parcel/Agreement ID)
RES.10 | Appraisal/Administrative Offer Summary | The appraisal of parcels and the administration of real property appraisal functions including contracting fee appraisers. An analysis of real estate market used to estimate the Fair Market Value of the real property and the damages to the remaining property. |  | RW.PA.03 | Appraisal/Administrative Offer Summary
RES.20 | Review & Determination of Value (DV) | Appraisal Review checks the accuracy of the appraisal data and the soundness of the appraisers reasoning then writes a Determination of Value (DV) which is the amount of money (Just Compensation) to be offered to the property owner for the property needed for the highway project. |  | RW.PA.04 | Review & Determination of Value (DV)
RES.30 | Acquisition | The negotiation with property owners, government agencies or railroads for acquisition of property. Also includes development of legal descriptions for real property or property rights to be acquired, time spent conducting title reviews and title searches, clearing encumbrances and maintenance of acquisition status data (via IRIS). |  | RW.PA.01 | Acquisition - Labor
|  |  | Combined into RES.30 | RW.PA.02 | Acquisition - Labor - Wetland Mitigation Site
|  |  | Combined into RES.30 | RW.PA.05 | Acquisition - Parcel Payment
|  |  | Combined into RES.30 | RW.PA.06 | Acquisition - Parcel Remainders
|  |  | Deleted | RW.PA.07 | Right of Way - Agreements
RES.40 | Relocation/Relocation Review Board and/or Adjudicative Hearings | The work required to prepare for and provide relocation assistance for eligible parties. The Adjudicative Hearing and/or Relocation Review Board decisions documents. |  | RW.PA.09 | Relocation
|  |  | Combined into RES.40 | RW.PA.09.01 | Relocation - Labor
|  |  | Combined into RES.40 | RW.PA.09.02 | Relocation Review Board and/or Adjudicative Hearings
|  |  | Combined into RES.40 | RW.PA.09.03 | Relocation - Parcel Payment
RES.50 | Property Management | The maintenance and management of the inventory of department-owned properties. The preparation of rental agreements or leases on department-owned property, and maintenance of rental property. Sales of properties no longer needed for transportation purposes. Demolition of property improvements no longer needed for transportation purposes. |  | RW.PA.10 | Property Management
|  |  | Combined into RES.50 | RW.PA.10.01 | Inventory
|  |  | Combined into RES.50 | RW.PA.10.02 | Rentals
|  |  | Combined into RES.50 | RW.PA.70.03 | Sales
|  |  | Combined into RES.50 | RW.PA.10.04 | Demolition
RES.60 | Condemnation/Possession & Use | A judicial process to acquire property where the state has been unable to reach a settlement through negotiation. This is handled by the office of the Attorney General. A regional or judicial formal document that grants the State the ability to possess and use the property in its construction project prior to the condemnation trial. |  | RW.PA.08 | Condemnation / Preparation / Trial
|  |  | Combined into RES.60 | RW.PA.08.01 | Condemnation
|  |  | Combined into RES.60 | RW.PA.08.02 | Possession & Use
RES.70 | R/W Certification | A statement certifying that all right-of-way clearance, including relocation assistance, has been completed or that all necessary arrangements have been made for it to be undertaken and completed as required for proper coordination with the physical construction schedule. The purpose of this certification is to inform the contractor of the status of right-of-way clearance and to certify that the requirements of the Uniform Act have been met on federally-funded projects. --R/W Recertification PERFORMANCE REPORTING MAJOR Milestone- The Milestone has been met on the date the Right of Way Certification is signed by the region Real Estate Services Manager on state funds only projects, or upon approval of FHWA on a project with federal funds. For Design-Build a minimum of right of way certification 3 is often necessary before going out to RFP. See Right of Way Manual M26-01 Chapter 17. | Moved from Design | PE.PD.90.03 | R/W Certification
CN | Construction | For description of Construction Work see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm and Standard Specifications http://www.wsdot.wa.gov/Publications/Manuals/M41-10.htm |  | CN | Construction
CN.01 | Construction Engineering | Construction Engineering - Group Category 03 in the Work Order |  | CN.03 | Construction Engineering
|  |  | Combined into PM.01 | CN.03.PM | Project Management and Overhead - Construction
|  |  | Combined into PM.01 | CN.03.PM.02 | Project Management and Overhead
|  |  | Combined into PM.01 | CN.03.PM.02.01 | General Project Management (Project Office)
|  |  | Combined into CN.01 | CN.03.PM.02.02 | Execution Period
|  |  | Combined into PM.01 | CN.03.PM.02.03 | Redistributed Project Management and Overhead (HQ & Region)
|  |  | Combined into PM.01 | CN.03.PM.03 | Project Management Plan Development & Maintenance
|  |  | Combined into PM.01 | CN.03.PM.03.01 | PMP Endorsement
|  |  | Combined into CN.01 | CN.03.PM.02 | Equal Employment Opportunity and Minority Business Enterprise
|  |  | Combined into CN.01.20 | CN.03.PM.03 | Public Information Design-Build
|  |  | Combined into CN.01.20 | CN.03.PM.04 | Budget/Schedule Design-Build
|  |  | Combined into CN.01 | CN.03.PM.06 | General Office Functions
|  |  | Combined into CN.01 | CN.03.PM.12 | Other Work for Management and Overhead
|  |  | Combined into CN.01 | CN.03.PM.12.01 | Travel To & From the Office to the Job Site
CN.01.10 | Survey and Base Map | See Survey Manual for description of work http://www.wsdot.wa.gov/Publications/Manuals/M22-97.htm |  | CN.03.SV.10 | Surveying
CN.01.20 | Design-Build Oversight | All work involved in the oversight of work plans, over-the-shoulder reviews, formally submitted reviews, task force meetings, design QV/QC/QA, deviations, and engineering decisions. It also includes work involved in the oversight of the project environmental review and compliance to commitments, permits, and approvals on Design-Build contracts. Does not include work on environmental documents, permits, and approvals done prior to award of the Design-build contract. Utilities oversight involves all work associated with identifying the location of utilities and determining relocation and/or adjustments and protection of facilities. This includes work to prepare and administer utility agreements on Design-Build contracts. Granting permission to the Design-Builder to enter and do work on right-of way owned by WSDOT at the time of entry. Monitoring the Design-Builder’s compliance with all applicable provisions of the contract and further conditions identified in any right-of-way, easements or right of entry onto property and their activities within. Assisting the Design-Builder in obtaining temporary construction easements. Does not include work involved in the review and approval of the right-of-way plan. Construction oversight and management on Design-Build contracts, of all project construction activities, control of materials, audit, inspection and testing, construction safety, and all other construction-related functions. |  | CN.03.PM.05 | Reporting Design-Build
CN.01.30 | Inspection | All inspection necessary to ensure conformance of workmanship, methods, and procedures. For Inspection description see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm Inspection: General, Earthwork, Drainage, Surface and Paving, Structures, Environmental and Scale Operations. |  | CN.03.IN | Inspection
|  |  | Combined into CN.01.20 | CN.03.IN.01 | Right-of-Way Design-Build
|  |  | Combined into CN.01.30 | CN.03.IN.02 | Inspection (Earthwork, Drainage, Surface and Paving)
|  |  | Combined into CN.01.30 | CN.03.IN.03 | Inspection (Structures)
|  |  | Combined into CN.01.30 | CN.03.IN.04 | Inspection (General)
|  |  | Combined into CN.01.30 | CN.03.IN.05 | Environmental (Inspection and Surveying)
|  |  | Combined into CN.01.30 | CN.03.IN.06 | Inspection and Surveying of Wetland Mitigation Sites
|  |  | Combined into CN.01.30 | CN.03.IN.07 | Environmental Oversight Design-Build
|  |  | Combined into CN.01.30 | CN.03.IN.08 | Utilities Design-Build
|  |  | Combined into CN.01.30 | CN.03.IN.09 | Construction Oversight Design-Build
|  |  | Combined into CN.01.30 | CN.03.IN.10 | Weighting, Dispatching, Receiving
CN.01.40 | Testing | For material Testing see Construction Manual for requirements and frequency http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm (Structures, Earthwork, Surface and Paving, Drainage, Miscellaneous) and Materials Manual for test procedures http://www.wsdot.wa.gov/Publications/Manuals/M46-01.htm --Stormwater BMP Maintenance Plan --Earthwork, Surface and Paving, Drainage, Miscellaneous --Structures |  | CN.03.MT | Testing
|  |  | Combined into CN.01.40 | CN.03.MT.01 | Testing (Earthwork, Surface and Paving, Drainage, Miscellaneous)
|  |  | Combined into CN.01.40 | CN.03.MT.02 | Testing (Structures)
CN.01.50 | Contract Administration & Documentation | For Contract Administration and Documentation, see Construction Manual http://www.wsdot.wa.gov/Publications/Manuals/M41-01.htm Contract Administration and Documentation includes these items at a minimum. --Working Drawings, Plan Checking, Data Preparation --Progress and Final Estimates and Records --Preparation of Change Order --Field Measurement - Progress and Final Estimates and Records --Equal Employment Opportunity and Minority Business Enterprise --Force Account Documentation --Agreements Management --Materials Approval and Acceptance |  | CN.03.CA | Contract Administration & Documentation
|  |  | Combined into CN.01.50 | CN.03.CA.01 | Working Drawings, Plan Checking, Data Preparation
|  |  | Combined into CN.01.50 | CN.03.CA.02 | Progress and Final Estimates and Records
|  |  | Combined into CN.01.50 | CN.03.CA.03 | Preparation of Change Orders
|  |  | Combined into CN.01.20 | CN.03.CA.04 | Change Orders Design-Build
|  |  | Combined into CN.01.20 | CN.03.CA.05 | Document Control Oversight Design-Build
|  |  | Combined into CN.01.20 | CN.03.CA.06 | Design, Oversight Design-Build
|  |  | Combined into CN.01.50 | CN.03.CA.07 | Field Measurement - Progress and Final Estimates and Records
|  |  | Combined into CN.01.50 | CN.03.CA.08 | Force Account Documentation
|  |  | Combined into CN.01.50 | CN.03.AG | Agreements Management
|  |  | Combined into CN.01.50 | CN.03.AG.01 | Consultant Agreements Administration - Construction Engineering
|  |  | Combined into CN.01.20 | CN.03.AG.02 | Partnerships/ Agreement Design-Build
|  |  | Combined into CN.01.50 | CN-06 | Utilities
|  |  | Combined into CN.01.50 | CN-06.01 | Utility Services/Agreements
|  |  | Combined into CN.01.50 | CN-06.02 | Utility Relocations
|  |  | Combined into CN.01.50 | CN.04 | State Force Construction
|  |  | Combined into CN.01.50 | CN.04.01 | Construction - State Forces
|  |  | Combined into CN.01.50 | CN.04.02 | Training - State Force
|  |  | Combined into PM.01 | CN.04.03 | Redistributed Project Management and Overhead (HQ & Region)
CN.02 | Construction Milestones | Milestones for Construction phase of the project, for Project Control and Reporting, for the Construction Contract Information System (CCIS), and other purposes. Other project specific milestones can be added per project needs. |  | CN.10 | Construction Milestones
CN.02.10 | Contract Execution | Milestone - Project Control & Reporting (PC&R) Milestone, CPMS, and CCIS milestone. This is the date when the Department signs the actual contract with the contractor. This typically occurs within 21 days following contract award. See 1-03.3 of the Standard Specifications for further detail. |  | CN.10.01 | Contract Execution
|  |  | Deleted | CN.10.02 | Statement of Intent to Pay Wages
|  |  | Deleted | CN.10.03 | Contractor and Subcontractor/Agent Cert. for F.A. Projects
|  |  | Deleted | CN.10.04 | Affidavit of Wages Paid - Prime
|  |  | Deleted | CN.10.05 | Pre-Construction Meeting Minutes
|  |  | Deleted | CN.10.06 | Ground-Breaking
|  |  | Deleted | CN.10.07 | Contract Time Start
CN.02.20 | Construction Work Start | Milestone - This is the date when work actually starts on building the project and activity might be seen on the site. See 1-08.5 of the Standard Specifications and contract special provisions for further details. |  | CN.10.08 | Construction Work Start
|  |  | Deleted | CN.10.09 | Original Progress Schedule Approved
|  |  | Deleted | CN.10.10 | Last Supplemental Progress Schedule Approved
|  |  | Deleted | CN.10.11 | Ribbon-Cutting
CN.02.30 | Operationally Complete | PERFORMANCE REPORTING MAJOR MILESTONE- This is the date when the public has free and unobstructed use of the facility. In some cases, the facility will be open, but minor work items may remain to be completed. See Section 1-01.3 of the Standard Specifications for further details on substantial completion. For example, a paving project would be considered Operationally Complete when the final lift is laid and the final striping is applied. Judgment must be used in determining the date the Milestone is accomplished, such as when a formal ribbon cutting celebration occurs or the delay of minor work items prevent the actual substantial completion, but the public actually has use of the completed roadway. |  | CN.10.12 | Operationally Complete
CN.02.40 | Substantial Completion | Milestone - CCIS milestone. The Substantial Completion date is the day the Engineer determines the Contracting Agency has full and unrestricted use and benefit of the facilities, both from the operational and safety standpoint, all the initial plantings are completed and only minor incidental work, replacement of temporary substitute facilities, plant establishment periods, or correction or repair remains for the Physical Completion of the total Contract. See 1-08.5 and 1-08.9 of the Standard Specifications for further detail. |  | CN.10.13 | Substantial Completion
CN.02.50 | Physical Completion | Milestone - CCIS milestone. The Physical Completion date is the day all of the Work is physically completed on the project. All documentation required by the Contract and required by law does not necessarily need to be furnished by the Contractor by this date. See 1-08.5 of the Standard Specifications for further detail. |  | CN.10.14 | Physical Completion
|  |  | Deleted | CN.10.15 | Final Estimate to Contractor
|  |  | Deleted | CN.10.16 | Final Estimate to Headquarters
CN.02.60 | Completion | Milestone - Project Control & Reporting (PC&R) Milestone, CPMS, and CCIS milestone. The Completion date is the day all the Work specified in the Contract is completed and all the obligations of the Contractor under the Contract are fulfilled by the Contractor. All documentation required by the Contract and required by law must be furnished by the Contractor before establishment of this date. See 1-08.5 of the Standard Specifications for further detail. |  | CN.10.17 | Completion
|  |  | Deleted | CN.10.18 | Materials Certification
|  |  | Deleted | CN.10.19 | Acceptance
|  |  | Deleted | CN.10.20 | Stewardship Acceptance:
CN.02.70 | CN Phase End | Milestone - All CN costs are finished and the work order is closed in TRAINS |  | CN.10.21 | CN Phase End
|  |  | Deleted | CN.01 | Contractor Activities
|  |  | Deleted | CN.01.01 | Significant Construction Traffic Closure/ Switching/ Opening/ Reopening
|  |  | Combined into CN.01.05 | CN.02 | Payable Agreements
|  |  | Combined into CN.01.05 | CN.02.01 | Agreements / Partnership
|  |  | Combined into CN.01.05 | CN.02.02 | Auditing services
|  |  | Combined into CN.01.05 | CN.02.03 | Legal services
|  |  | Deleted | CN.12 | Vessel Contractor Activities/Shipyard Period
|  |  | Deleted | CN.12.01 | Shipyard Period (Project Mgmt. & Inspection)
|  |  | Deleted | CN.12.02 | Working Drawings, Plan Checking, Data Preparation
|  |  | Deleted | CN.12.03 | AS Built Drawings - Mechanical
|  |  | Deleted | CN.12.04 | AS Built Drawings - Hull
|  |  | Deleted | CN.12.05 | AS Built Drawings - Electrical
|  |  | Deleted | CN.12.06 | Statement of Intent to Pay Wages
|  |  | Deleted | CN.12.07 | Affidavit of Wages Paid - Prime
|  |  | Deleted | CN.12.08 | Pre-Construction Meeting Minutes
|  |  | Deleted | CN.12.09 | Substantial Completion/return to service
|  |  | Deleted | CN.12.10 | Physical Completion
|  |  | Deleted | CN.12.11 | Acceptance
Note on B139: Parker, Julie: This activity has been added at the request of the NWR Design Guidance Team. An investigation of completed projects with large earthwork quantities that revealed that many of them have penny bids with CRIPS that contractor used native soil instead of specified import. This activity is to ensure the native soil investigation is done during the design phase of the project.
Note on C139: 610.04(6)(a) Project Definition The designer contacts and meets with the RME (and the HQ Geotechnical Office as needed) at the project site to conduct a field review to help identify the geotechnical issues for the project. In general, if soil/rock conditions are poor and/or large cuts or fills are anticipated, the RME requests that the HQ Geotechnical Office participate in the field review and reporting efforts. The designer provides a description and location of the proposed earthwork to the RME as follows: • For widening of existing facilities, the anticipated width, length, and location of the widening, relative to the current facility, are provided. • For realignments, the approximate new location proposed for the facility is provided. • Locations in terms of length can be by milepost or stations. A brief conceptual-level report that summarizes the results of the investigation is provided to the designer.