## QL RMP g
Project Name | [11 empty] | Project Identification Number (PIN) |  |  |  | Date:
Project Manager | [14 empty] | Name of Risk Owner:
|  | QUALITATIVE ANALYSIS | [13 empty] | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | [10 empty] | 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | RISK TRIGGER: | [10 empty] | 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | change likelihood
[12 empty] | 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | Description of Risk Event | [10 empty] | 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | share
[12 empty] | 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | [11 empty] | 5 | [6 empty] | PSP | 60
[12 empty] | 4 | [6 empty] | ROW | 70
Project Phase | [11 empty] | 3 | Low | [5 empty] | RR | 80
[12 empty] | 2 | [6 empty] | STG | 90
Date | [11 empty] | 1 | Very Low | [5 empty] | UTL | 900
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 1
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 1: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 1: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 1: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 1: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 1: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 1: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 1: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 1: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 1: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 1
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 2
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 2: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 2: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 2: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 2: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 2: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 2: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 2: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 2: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 2: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 2
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 3
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 3: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 3: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 3: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 3: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 3: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 3: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 3: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 3: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 3: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 3
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 4
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 4: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 4: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 4: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 4: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 4: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 4: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 4: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 4: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 4: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 4
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 5
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 5: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 5: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 5: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 5: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 5: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 5: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 5: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 5: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 5: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 5
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 6
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 6: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 6: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 6: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 6: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 6: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 6: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 6: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 6: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 6: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 6
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 7
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 7: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 7: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 7: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 7: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 7: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 7: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 7: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 7: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 7: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 7
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 8
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 8: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 8: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 8: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 8: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 8: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 8: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 8: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 8: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 8: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 8
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 9
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 9: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 9: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 9: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 9: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 9: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 9: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 9: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 9: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 9: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 9
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 10
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 10: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 10: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 10: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 10: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 10: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 10: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 10: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 10: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 10: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 10
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 11
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
| RISK EVENT NAME: | 1 RISK 11: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | Avoid
Status | RISK TRIGGER: | 1 RISK 11: 9 | [5 empty] | Item of Interest | CTR | 20 | Right-of-way | Transfer
|  | 1 RISK 11: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | Mitigate
RBS Category | Description of Risk Event | 1 RISK 11: 7 |  |  |  | TO BE TAKEN |  | THREAT | ENV | 40 |  | Exploit
|  | 1 RISK 11: 6 | Medium |  |  |  |  | OPPORTUNITY | MGT | 50 |  | Share
Risk Number |  | 1 RISK 11: 5 | [6 empty] | PSP | 60 |  | Enhance
|  | 1 RISK 11: 4 | [6 empty] | ROW | 70 |  | Accept
Project Phase |  | 1 RISK 11: 3 | Low | [5 empty] | RR | 80
|  | 1 RISK 11: 2 | [6 empty] | STG | 90
Date | [12 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 11
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 12
Risk Owner |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è

## User's Guide
Project Name | EXAMPLE PROJECT CANOE | [12 empty] | Project Identification Number (PIN) | 01234 |  |  | Date: |  | February 31, 2929
Project Manager | Miss Manager | [15 empty] | Name of Risk Owner:
|  |  |  | QUALITATIVE ANALYSIS | [13 empty] | RISK RESPONSE |  | MONITOR and CONTROL
|  |  | RISK EVENT NAME: | [10 empty] | 10 | Very High | probability è |  | STRATEGY |  | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Active Risk |  | RISK TRIGGER: | [10 empty] | 9 | [6 empty] | Item of Interest | CTR | 20 | Right-of-way | change likelihood
[14 empty] | 8 | High |  |  | ACTION |  |  |  | DES | 30 | Construction | change impact
RBS Category | ENV |  | Description of Risk Event | [10 empty] | 7 |  |  |  | TO BE TAKEN |  |  | THREAT | ENV | 40 |  | share
[14 empty] | 6 | Medium | [5 empty] | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 900 | [12 empty] | 5 | [7 empty] | PSP | 60
[14 empty] | 4 | [7 empty] | ROW | 70
Project Phase | Design | [12 empty] | 3 | Low | [6 empty] | RR | 80
[14 empty] | 2 | [7 empty] | STG | 90
Date | Feb 31, 2929 | [12 empty] | 1 | Very Low | [6 empty] | UTL | 900
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK #
Risk Owner | Dude Responsible |  |  | Very Lo to Lo |  |  |  | some |  | Hi to Very Hi
Impact è
é |  | é |  |  |  |  | é | [9 empty] | é |  | é |  |  | 40
40.1
40.2
40.3
40.4
50
50.1
50.2
50.3
50.4
60
60.1
60.2
60.3
60.4
70
70.1
70.2
70.3
RISK IDENTIFICATION INFORMATION
STATUS  ACTIVE or ITEM OF INTEREST
(this is a drop-down menu to identify the event as an active risk or item of interest to keep an eye on)
RBS CATEGORY  INDICATE TYPE OF RISK
(drop-down menu of standard risk categories, RBS = Risk Breakdown Structure)
RISK NUMBER  NUMBER under the Risk Category
(drop-down menu to more specifically identify the event with a number from the RBS)
PROJECT PHASE  DESIGN, RIGHT-OF-WAY or CONSTRUCTION
(drop-down menu to identify the phase the risk event will impact)
Date Risk Identified  Enter the date the risk was identified
NAME OF RISK OWNER  Enter the name of the person responsible for the risk
RISK ANALYSIS - QUALITATIVE
DISCUSS THE RISK
How likely is it to occur?
If it were to occur what is the impact?
Copy and plot the "X" as appropriate for each risk
RBS CATEGORY  INDICATE TYPE OF RISK
(drop-down menu of risk categories, RBS = Risk Breakdown Structure)
RESPONSE
Identify the response strategy to be used for the risk.
Design specific actions to implement strategy, determine who owns the risk.
This matrix is easily adapted to a 2 X 2 matrix as shown.
Low High
High
Low
MONITOR and CONTROL
Insure response actions are followed through. Record the risk review dates and status of the risk. Project risks changes as the project matures, new risks develop, or anticipated risks disappear. The project manager schedules regular project risk reviews, and ensures that project risk is an agenda item at all Project Team meetings. Risk ratings and prioritization commonly change during the project lifecycle.
If an unanticipated risk emerges, or a risk’s impact is greater than expected, the planned response strategy and actions may not be adequate. The project manager and the Project Team must perform additional response strategies and actions to control the risk.
Risk Control Involves: 1) choosing an alternative response; 2) implement a contingency plan; 3) taking corrective actions; 4) re-planning the project (recovery plan).
General Project Info

X
X

## RBS List (hidden)
CNS
CTR
DES
ENV
MGT
PSP
ROW
RR
STG
UTL

## example
| Project Name | [12 empty] | Project Identification Number (PIN) |  |  |  | Date:
| Project Manager | [15 empty] | Name of Risk Owner:
|  |  |  | QUALITATIVE ANALYSIS | [13 empty] | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | unknown utilities | [10 empty] | 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Active Risk | RISK TRIGGER: | discovery | [10 empty] | 9 |  |  |  | avoid |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT | [11 empty] | 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | UTL | Areas outside of R/W have not been investigated for conflicts. Additional work is required for sewer/storm, water, gas, power, communications. Triggers include: utilities found late in design or during construction. | [11 empty] | 7 |  |  |  | TO BE TAKEN | update at the next Quarterly Project Report (QPR) meeting | THREAT | ENV | 40 |  | share
[14 empty] | 6 | Medium |  |  | subsurface utility investigations immediately; assign team member to this full time. |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 20 | [12 empty] | 5 | [6 empty] | PSP | 60
[14 empty] | 4 | [6 empty] | ROW | 70
Project Phase | Design | [12 empty] | 3 | Low | [5 empty] | RR | 80
[11 empty] | X |  |  | 2 | [6 empty] | STG | 90
Date | May 32, 2929 | [12 empty] | 1 | Very Low | [5 empty] | UTL | 900
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 1
Risk Owner | M. Example |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  |  |  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | noise wall | 1 RISK 1: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Active Risk | RISK TRIGGER: | analysis results | 1 RISK 1: 9 |  |  |  | avoid |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT |  | 9: X; 1 RISK 1: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | ENV | possibility that a noise wall will have to be added to the project - pending results of the type 1 analysis; this is a high impact high probability threat |  | 1 RISK 1: 7 |  |  |  | TO BE TAKEN | analysis due August 39th. | THREAT | ENV | 40 |  | share
|  |  |  | 1 RISK 1: 6 | Medium |  |  | press for noise analysis ASAP |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 90 |  |  | 1 RISK 1: 5 | [6 empty] | PSP | 60
|  |  |  | 1 RISK 1: 4 | [6 empty] | ROW | 70
Project Phase | Design |  |  | 1 RISK 1: 3 | Low | [5 empty] | RR | 80
|  |  |  | 1 RISK 1: 2 | [6 empty] | STG | 90
Date | May 32, 2929 | [13 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 1
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 2
Risk Owner | Green Jeans |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
Name of Risk Owner:
|  |  |  | 1: QUALITATIVE ANALYSIS |  |  |  | RISK RESPONSE | MONITOR and CONTROL
|  | RISK EVENT NAME: | cultural resources | 1 RISK 2: 10 | Very High | probability è |  | STRATEGY | Date, Status and review comments | Active Risk | CNS | 10 | Design | avoid
Status | Item of Interest | RISK TRIGGER: | discovery | 1 RISK 2: 9 |  |  |  | accept |  | Item of Interest | CTR | 20 | Right-of-way | change likelihood
|  | THREAT |  | 1 RISK 2: 8 | High |  |  | ACTION |  |  | DES | 30 | Construction | change impact
RBS Category | ENV | discovery of artifact; triggered during design if field investigation results in discovery; also trigger if discovered during construction ¦ deemed low probability - this area has been investigated previously and very little new ground is being disturbed. |  | 1 RISK 2: 7 |  |  |  | TO BE TAKEN | supplemental field investigation report due November 31. | THREAT | ENV | 40 |  | share
|  |  |  | 1 RISK 2: 6 | Medium |  |  | monitor |  | OPPORTUNITY | MGT | 50 |  | accept
Risk Number | 40 |  |  | 1 RISK 2: 5 | [6 empty] | PSP | 60
|  |  |  | 1 RISK 2: 4 | [6 empty] | ROW | 70
Project Phase | Design |  |  | 2: X; 1 RISK 2: 3 | Low | [5 empty] | RR | 80
|  |  |  | 1 RISK 2: 2 | [6 empty] | STG | 90
Date | May 33, 2929 | [13 empty] | Very Low | [5 empty] | UTL | 900 | bar: 1 RISK 2
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | RISK 3
Risk Owner | Green Jeans |  |  | 1: Very Lo to Lo; 5: some; 7: Hi to Very Hi
Impact è
X
X
X

## old QL rmp
Project Title
Project PIN #
Date
| Project Mngr |  | Name | Telephone Number | (xxx) xxx-xxxx
Priority | PROJECT RISK MANAGEMENT PLAN
| Risk Identification | [7 empty] | Qualitative Analysis | [6 empty] | Risk-Response Strategy |  | Monitoring and Control
| Status | ID # | Date Identified Project Phase | Risk Event (threat/opportunity) | SMART Column | Risk Trigger | Impact Area | Affected MDL/WBS Level 2 process | Probability | Impact | Risk Matrix |  |  |  | Risk Owner | Strategy | ACTION TO BE TAKEN (include advantages and disadvantages) | Status Interval or Milestone Check | Date, Status and Review Comments
| Active |  | Scoping |  |  |  | Scope | [8 empty] | Avoidance
| Dormant |  | Design/PS&E |  |  |  | Schedule |  | High | High | [5 empty] | Transference
| Retired |  | Construction |  |  |  | Budget | [8 empty] | Mitigation
[9 empty] | Low | Low | [5 empty] | Acceptance
(1) | (2) | (3) | (4) | (5) | (6) | (7) | (8) | (9) | (10) | (11) | (12) |  |  |  | (13) | (14) | (15) | (16) | (17)
Instructions | Active=actively monitored & controlled Dormant = not a high priority; may become active in the future. Retired = no longer a threat to project objectives. | E1 | For example: 6/30/99 Scoping | Risk is an uncertain event or condition that, if it occurs, has a positive (opportunity) or negative (threat) on a project. For example; Wetland Mitigation requires additional R/W. | Detailed description of the risk. Includes information on the risk that is Specific, Measureable, Attributable, Relevant and Timebound. Describe the consequences of the risk to scope, schedule, budget or quality. | Triggers are indications that a risk has occurred or is about to occur. Used to determine when to implement the Risk Response Strategy. For example: Wetland impact is greater than 1/2 acre. | Is the primary impact to the scope, schedule, or budget? | Which WBS element will be modified as part of the response strategy? For example: PC-19 Environmental Permits | Assessment of the likelihood of occurrence. Valid entries are Low or High. | The severity of the risk's effect on the projects objectives. Valid entries are Low or High. | High: Substantial impact on cost, schedule, or technical. Substantial action required to alleviate issue. Low: Minimal impact on cost, schedule, or technical. Normal management oversight is sufficient. |  |  |  | Name of the person or office responsible for managing the risk event. | Avoid, Transfer, Mitigate, Acceptance, Exploit, Share, Enhance (See the Risk Management Guide for strategy definitions.) | Develop options and determine actions to be taken in response to the risk event. Immediate action may be required at the time of identification. Estimate value of risk and estimate cost to respond. | For example: Completion of wetland delineation expected: 2/28/00 | For example: Last status update 4/30/00. Wetland delineation completed 3/15/00. Over 1 acre of wetland was delineated, action is being taken to expedite meetings with regulatory agencies & expedite the effort to provide appropriate wetland mitigation & attain project permits.
[8 empty] | WBS 165 Perform Environmental Studies and Prepare Draft Environmental Document (DED) |  |  | Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact
Probability
H
L
[13 empty] | L | H
Impact

## old users guide
old risk management plan (RMP) – old user guide
The RMP describes how risk management will be structured and performed on the project. It becomes a subset of the project management plan. See the Project Management Online Guide for more information, http://www.wsdot.wa.gov/Projects/ProjectMgmt/ Also, review "A Policy for Cost Risk Assessment" (http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/) to determine the appropriate level of detailed risk analysis to be performed on the project.
The RMP comprises four main sections of risk assessment:
1. Risk Identification
2. Risk Analysis (Qualitative & Quantitative)
3. Risk Response Strategy
4. Risk Monitoring and Control
Risk Identification determines which risk might affect the project and documents their characteristics. Risk identification is an iterative process because new risks may become known as the project progresses thought its life. The frequency of iterations and who participates in each cycle will vary from case to case. The project team is involved in this process to develop and maintain a sense of ownership of, and responsibility for, risks and associated risk response strategy. The Risk Identification process leads to one of the two main segments of the Risk Analysis section.
The Risk Identification section includes:
(1) Priority, this is the ranking of the risks by priority and occurs subsequent to the risk analysis.
(2) Risk Status defines the status of the risk event. The user has three status scenarios to choose from such as:
· Active, when the risk is being actively monitored and controlled
· Dormant, when the risk is low priority but may become high priority in the future
· Retired, when the risk is demised for any reason.
(3) Risk Identification number is a unique number assigned to the risk for tracking purpose.
(4) Date Identified and Project Phase, represents the date when the risk was first identified and the phase of the project when the risk was first identified. Valid entries for the project phase are: Scoping, Design/PS&E and Construction.
(5) Risk Event (threat/opportunity), present a summary definition of the risk. It clarifies the risk outcome:
· If the risk outcome provides negative impact to the project (higher cost and/or longer duration) the risk is named a Threat, which should be minimized.
· If the risk outcome provides positive impact to the project (lower cost and/or shorter duration) the risk is named an Opportunity, which should be maximized.
(6) SMART Column provides a detailed description of the risk. Including information on the risk that is Specific, Measurable, Attributable, Relevant and Time bound. It describes the consequences of the risk to scope, schedule, budget or quality.
(7) Risk Trigger presents symptoms and warning signs that indicate whether each risk is likely to occur. This information is used the determine when to implement the Risk Response Strategies.
(8) Impact Area identifies the primary impact to the scope, schedule, budget, or quality.
(9) Affected MDL/WBS Level 2 process identifies which WBS element(s) will be modified as part of the response strategy.
Qualitative Risk Analysis includes methods for prioritizing the identified risks for further action, such as Quantitative Risk Analysis (See A Policy for Cost Risk Assessment) or Risk Response Planning. Qualitative Risk Analysis assesses the priority of risks by using their probability of occurring, corresponding impact on project objectives if the risks do occur, as well as other factors such as the time frame and risk tolerance of the project constraints of scope, schedule, budget, and quality. Time critical risk related actions may magnify the importance of a risk. Qualitative Risk Analysis is a method for establishing priorities for Risk Response Planning and may lead into Quantitative Risk Analysis, when required. See the Project Managment Online Guide for more information about quantitative risk analysis.
(10-12) The Probability and Impact Matrix is a common way to determine whether a risk is considered low or high by combining the two dimensions of a risk; it probability of occurrence, and its impact on objectives if it occurs. High risks that have a negative impact (threat) on objectives may require priority action and aggressive response strategies. Low risk Threats may not require proactive management action beyond being placed on a watch list. Similarly, high risk opportunities that can be obtained most easily and offer the greatest benefit should, therefore, be targeted first. Low risk opportunities should be monitored.
Risk Owner (13) is the name of the person or office responsible for managing the risk event.
Risk Response Planning (strategy) is the process of developing options, and determining actions to be taken to enhance opportunities and reduce threats to the projects objectives. Planned risk responses must be appropriate to the significance of the risk, cost effective, timely, realistic within the project context, agreed upon by all parties involved, and owned by a responsible person.
(14-15) The Project Manager and Team agree upon the appropriate response strategy and design specific actions to implement that strategy for each risk. These strategies and actions include:
· Avoidance: The team changes the project plan to eliminate the risk or to protect the project objectives from its impact. The team might achieve this by changing scope, adding time, or adding resources (thus relaxing the so-called “triple constraint”). These changes may require upper management approval. Some risks that arise early in the project can be avoided by clarifying requirements, obtaining information, improving communication, or acquiring expertise.
· Transference: Risk transference shifts the ownership and responsibility for its management to a third party; it does not eliminate it. Transferring liability for risk is most effective in dealing with financial risk exposure.
· Mitigation: The team seeks to reduce the probability or consequences of a risk event to an acceptable threshold. Taking early action to reduce the probability and/or impact of a risk occurring on the project is often more effective than trying to repair the damage after the risk has occurred. Mitigation costs should be appropriate, given the probability of the risk and its consequences.
· Acceptance: The Project Manager and team decide not to change the project plan to deal with a risk, or cannot identify a suitable response action. A contingency plan may be developed or no action may be taken, leaving the project team to deal with the risk as it occurs.
Risk Monitoring and Control tracks identified risks, monitors residual risks, and identifies new risks, ensuring the execution of risk plans, and evaluating their effectiveness in reducing risk. Risk Monitoring and Control is an ongoing process for the life of the project. The list of project risks changes as the project matures, new risks develop, or anticipated risks disappear. Periodic project risk reviews repeat the tasks of identification, analysis, and response strategies. The project manager regularly schedules project risk reviews, and ensures that project risk is an agenda item at all Project Team meetings. Risk ratings and prioritization commonly change during the project lifecycle.
(16-17) Insert any comments that would be helpful for risk tracking and control.
If an unanticipated risk emerges, or a risk’s impact is greater than expected, the planned response strategy and actions may not be adequate. The project manager and the Project Team must perform additional response Strategies and actions to control the risk.
Risk control involves:
• Choosing alternative response strategies
• Implementing a contingency plan
• Taking corrective actions
• Re-planning the project
The task manager assigned to each risk reports periodically to the project manager on the effectiveness of the plan, any unanticipated effects, and any mid-course correction that the Project Team must take to mitigate the risk.
GENERAL NOTE:
The RMP also serves as a nice project performance measurement tool.