## RECAP Hrs
Agreement Number Project Name ESTIMATED HOURS RECAP
Prime Consultant and subs
Work Elem. |  |  | Sub Elem. | Description | Parsons | Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | [12 empty] | Total Hours
WE-01 | Project Management | [23 empty] | 1779
| 1.1 | Project Management |  |  | 252 | 0 | 0 | 0 | 12 | 0 | 0 | 0 | [12 empty] | 264
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 1.2 | Project Management Plan |  |  | 86 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 86
| 1.3 | Quality Management Plan |  |  | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 30
| 1.4 | Project Meetings |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.4.1 |  | STATE Team Meetings | 64 | 28 | 0 | 4 | 4 | 4 | 4 | 4 | [12 empty] | 112
|  | 1.4.2 |  | Consultant Team Meetings | 30 | 27 | 0 | 36 | 12 | 13 | 16 | 8 | [12 empty] | 142
| 1.5 | Consultant Co-location Plan |  |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 4
| 1.6 | Monthly Progress Reporting and Invoicing |  |  | 240 | 24 | 36 | 24 | 44 | 24 | 11 | 12 | [12 empty] | 415
| 1.7 | Document Management |  |  | 80 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 80
| 1.8 | Team Direction and Oversight |  |  | 646 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 646
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 1290
| 2.1 | Community Engagement Plan (CEP) |  |  | 8 | 38 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 46
| 2.2 | Community meetings and Events |  |  | 80 | 213 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 293
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.3 | Open Houses |  |  | 46 | 302 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 348
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.4 | Community Database |  |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 48
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops |  |  | 90 | 182 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 272
| 2.6 | Community Briefings |  |  | 35 | 133 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 168
| 2.7 | Websites and Social Media |  |  | 12 | 103 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 115
WE-03 | Practical Design Assessment | [23 empty] | 1313
| 3.1 | Baseline and Contextual Need Statement |  |  | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 43
| 3.2 | Design Control Selection |  |  | 218 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 218
| 3.3 | Performance Metrics and Targets |  |  | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 310
| 3.4 | Contributing Factors Analysis |  |  | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 310
| 3.5 | Alternatives Development and Evaluation |  |  | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 432
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 2893
| 4.1 | Data Collection |  |  | 44 | 0 | 273 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 317
| 4.2 | Existing Conditions 2016 Analysis |  |  | 52 | 0 | 528 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 580
| 4.3 | Future Forecasts |  |  | 90 | 0 | 442 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 532
| 4.4 | Alternatives Analysis |  |  | 96 | 0 | 1368 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 1464
WE-05 | Survey | [23 empty] | 1016
| 5.1 | Existing Mapping |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.1.1 |  | Control and Datum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172 | [12 empty] | 172
|  | 5.1.2 |  | Topography | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 564 | [12 empty] | 564
|  | 5.1.3 |  | Utilities Survey | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 264 | [12 empty] | 280
WE-06 | Environmental | [23 empty] | 387
| 6.1 | Environmental Management and Support |  |  | 12 | 0 | 0 | 50 | 0 | 24 | 0 | 0 | [12 empty] | 86
| 6.2 | Environmental Analysis and Summary Memorandum |  |  | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | [12 empty] | 24
|  | 6.2.1 |  | Cultural Resources Study | 3 | 0 | 0 | 20 | 0 | 0 | 0 | 0 | [12 empty] | 23
|  | 6.2.2 |  | Wetland and Stream Assessment | 3 | 0 | 0 | 50 | 0 | 0 | 0 | 0 | [12 empty] | 53
|  | 6.2.3 |  | Biological Assessment | 3 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | [12 empty] | 27
|  | 6.2.4 |  | Land Use Analysis | 3 | 25 | 0 | 2 | 0 | 0 | 0 | 0 | [12 empty] | 30
|  | 6.2.5 |  | Air Quality Analysis | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | [12 empty] | 2
|  | 6.2.6 |  | Noise Analysis | 51 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | [12 empty] | 53
|  | 6.2.7 |  | Environmental Justice Analysis | 3 | 39 | 0 | 2 | 0 | 0 | 0 | 0 | [12 empty] | 44
|  | 6.2.8 |  | Hazardous Materials Analysis | 3 | 0 | 0 | 2 | 0 | 0 | 40 | 0 | [12 empty] | 45
WE-07 | Geotechnical Services | [23 empty] | 57
| 7.1 | Data Collection and Summary |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | [12 empty] | 31
| 7.2 | Geologic Hazards Screening |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | [12 empty] | 11
| 7.3 | Conceptual Foundation Recommendations |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | [12 empty] | 15
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 2362
| 8.1 | Preliminary Utility Coordination |  |  | 176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 176
| 8.2 | Civil Preliminary Engineering |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | 8.2.1 |  | Data Collection and Review | 176 | 0 | 0 | 0 | 32 | 40 | 0 | 0 | [12 empty] | 248
|  | 8.2.2 |  | Civil Design Criteria | 189 | 0 | 0 | 0 | 80 | 9 | 0 | 0 | [12 empty] | 278
|  | 8.2.3 |  | Basis of Design | 132 | 0 | 0 | 0 | 54 | 20 | 0 | 0 | [12 empty] | 206
|  | 8.2.4 |  | Cost Estimating | 182 | 0 | 0 | 0 | 120 | 70 | 0 | 0 | [12 empty] | 372
| 8.3 | Preliminary Alternative Design |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | 438 | 0 | 0 | 0 | 290 | 100 | 0 | 0 | [12 empty] | 828
|  | 8.3.2 |  | Internal Team Coordination | 64 | 0 | 0 | 0 | 36 | 10 | 0 | 0 | [12 empty] | 110
|  | 8.3.3 |  | CAD Support for WE 2.8 | 88 | 0 | 0 | 0 | 56 | 0 | 0 | 0 | [12 empty] | 144
|  |  |  | Total | 4843 | 1162 | 2647 | 242 | 740 | 314 | 125 | 1024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11097
[5 empty] | 43.64% | 10.47% | 23.85% | 2.181% | 6.668% | 2.83% | 1.126% | 9.228%
Note on Z25: P007755A: Agreed

## RECAP Fee
Agreement Number Project Name ESTIMATED FEE RECAP
Prime Consultant and subs
Work Elem. |  |  | Sub Elem. | Description | Parsons | Sub 1 | Sub 2 | Sub 3 | Sub 4 | Sub 5 | Sub 6 | Sub 7 | [12 empty] | Total Hours
WE-01 | Project Management |  |  |  | 253237 | 14705 | 4799 | 10457 | 12507 | 5856 | 5431 | 3482 | [12 empty] | 310474
| 1.1 | Project Management |  |  | 43931 | 0 | 0 | 0 | 2575 | 0 | 0 | 0 | [12 empty] | 46506
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 1.2 | Project Management Plan |  |  | 14783 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 14783
| 1.3 | Quality Management Plan |  |  | 4663 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 4663
| 1.4 | Project Meetings |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 1.4.1 |  | STATE Team Meetings | 12263 | 4110 | 0 | 816 | 773 | 669 | 833 | 635 | [12 empty] | 20099
|  | 1.4.2 |  | Consultant Team Meetings | 5742 | 6273 | 0 | 5957 | 2319 | 2175 | 3332 | 1326 | [12 empty] | 27124
| 1.5 | Consultant Co-location Plan |  |  | 779 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 779
| 1.6 | Monthly Progress Reporting and Invoicing |  |  | 34978 | 4322 | 4799 | 3684 | 6840 | 3012 | 1266 | 1521 | [12 empty] | 60422
| 1.7 | Document Management |  |  | 10332 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 10332
| 1.8 | Team Direction and Oversight |  |  | 125766 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 125766
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
WE-02 | Public and Community Outreach and Engagement |  |  |  | 54419 | 120301 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 174720
| 2.1 | Community Engagement Plan (CEP) |  |  | 1361 | 6777 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 8138
| 2.2 | Community meetings and Events |  |  | 15356 | 20971 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 36327
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.3 | Open Houses |  |  | 8846 | 31821 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 40667
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.4 | Community Database |  |  | 0 | 5030 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 5030
[5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops |  |  | 19706 | 24998 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 44704
| 2.6 | Community Briefings |  |  | 6814 | 16912 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 23726
| 2.7 | Websites and Social Media |  |  | 2336 | 13792 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 16128
WE-03 | Practical Design Assessment |  |  |  | 273324 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 273324
| 3.1 | Baseline and Contextual Need Statement |  |  | 9176 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 9176
| 3.2 | Design Control Selection |  |  | 41368 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 41368
| 3.3 | Performance Metrics and Targets |  |  | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 67137
| 3.4 | Contributing Factors Analysis |  |  | 67137 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 67137
| 3.5 | Alternatives Development and Evaluation |  |  | 88506 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 88506
WE-04 | Traffic Analysis and Data Collection |  |  |  | 53172 | 0 | 369359 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 422531
| 4.1 | Data Collection |  |  | 7984 | 0 | 33606 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 41590
| 4.2 | Existing Conditions 2016 Analysis |  |  | 9604 | 0 | 73521 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 83125
| 4.3 | Future Forecasts |  |  | 17298 | 0 | 65370 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 82668
| 4.4 | Alternatives Analysis |  |  | 18286 | 0 | 196862 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 215148
WE-05 | Survey |  |  |  | 2722 | 0 | 0 | 0 | 0 | 0 | 0 | 104274 | [12 empty] | 106996
| 5.1 | Existing Mapping |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.1.1 |  | Control and Datum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18579 | [12 empty] | 18579
|  | 5.1.2 |  | Topography | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 57364 | [12 empty] | 57364
|  | 5.1.3 |  | Utilities Survey | 2722 | 0 | 0 | 0 | 0 | 0 | 0 | 28331 | [12 empty] | 31053
WE-06 | Environmental |  |  |  | 18674 | 9688 | 0 | 27961 | 0 | 2978 | 4376 | 0 | [12 empty] | 63677
| 6.1 | Environmental Management and Support |  |  | 2336 | 0 | 0 | 10204 | 0 | 2978 | 0 | 0 | [12 empty] | 15518
| 6.2 | Environmental Analysis and Summary Memorandum |  |  | 0 | 0 | 0 | 3226 | 0 | 0 | 0 | 0 | [12 empty] | 3226
|  | 6.2.1 |  | Cultural Resources Study | 535 | 0 | 0 | 2976 | 0 | 0 | 0 | 0 | [12 empty] | 3511
|  | 6.2.2 |  | Wetland and Stream Assessment | 535 | 0 | 0 | 6429 | 0 | 0 | 0 | 0 | [12 empty] | 6964
|  | 6.2.3 |  | Biological Assessment | 535 | 0 | 0 | 3086 | 0 | 0 | 0 | 0 | [12 empty] | 3621
|  | 6.2.4 |  | Land Use Analysis | 535 | 3894 | 0 | 408 | 0 | 0 | 0 | 0 | [12 empty] | 4837
|  | 6.2.5 |  | Air Quality Analysis | 0 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | [12 empty] | 408
|  | 6.2.6 |  | Noise Analysis | 13128 | 0 | 0 | 408 | 0 | 0 | 0 | 0 | [12 empty] | 13536
|  | 6.2.7 |  | Environmental Justice Analysis | 535 | 5794 | 0 | 408 | 0 | 0 | 0 | 0 | [12 empty] | 6737
|  | 6.2.8 |  | Hazardous Materials Analysis | 535 | 0 | 0 | 408 | 0 | 0 | 4376 | 0 | [12 empty] | 5319
WE-07 | Geotechnical Services |  |  |  | 585 | 0 | 0 | 0 | 0 | 0 | 7805 | 0 | [12 empty] | 8390
| 7.1 | Data Collection and Summary |  |  | 195 | 0 | 0 | 0 | 0 | 0 | 4319 | 0 | [12 empty] | 4514
| 7.2 | Geologic Hazards Screening |  |  | 195 | 0 | 0 | 0 | 0 | 0 | 1506 | 0 | [12 empty] | 1701
| 7.3 | Conceptual Foundation Recommendations |  |  | 195 | 0 | 0 | 0 | 0 | 0 | 1980 | 0 | [12 empty] | 2175
WE-08 | Preliminary Engineering/Alternatives Analysis |  |  |  | 185986 | 0 | 0 | 0 | 85590 | 31186 | 0 | 0 | [12 empty] | 302762
| 8.1 | Preliminary Utility Coordination |  |  | 21476 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 21476
| 8.2 | Civil Preliminary Engineering |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.2.1 |  | Data Collection and Review | 24779 | 0 | 0 | 0 | 4108 | 5196 | 0 | 0 | [12 empty] | 34083
|  | 8.2.2 |  | Civil Design Criteria | 24939 | 0 | 0 | 0 | 11148 | 1160 | 0 | 0 | [12 empty] | 37247
|  | 8.2.3 |  | Basis of Design | 19998 | 0 | 0 | 0 | 8200 | 2654 | 0 | 0 | [12 empty] | 30852
|  | 8.2.4 |  | Cost Estimating | 23308 | 0 | 0 | 0 | 13503 | 9117 | 0 | 0 | [12 empty] | 45928
| 8.3 | Preliminary Alternative Design |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | 51638 | 0 | 0 | 0 | 35689 | 11818 | 0 | 0 | [12 empty] | 99145
|  | 8.3.2 |  | Internal Team Coordination | 9310 | 0 | 0 | 0 | 5778 | 1241 | 0 | 0 | [12 empty] | 16329
|  | 8.3.3 |  | CAD Support for WE 2.8 | 10538 | 0 | 0 | 0 | 7164 | 0 | 0 | 0 | [12 empty] | 17702
|  |  |  | Total Labor | 842119 | 144694 | 374158 | 38418 | 98097 | 40020 | 17612 | 107756 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1662874
|  |  |  | Other Direct Costs | 20950.3 | 6380 | 562.4 | 367.36 | 4205.6 | 319 | 885 | 14260 | [12 empty] | 47929.66
|  |  |  | Total Estimate | 863069.3 | 151074 | 374720.4 | 38785.36 | 102302.6 | 40339 | 18497 | 122016 | [12 empty] | 1710803.66
[5 empty] | 50.45% | 8.831% | 21.9% | 2.267% | 5.98% | 2.358% | 1.081% | 7.132%

## EST HRS (Prime-)
Agreement Number Project Name PRIME ESTIMATED HOURS
Prime Consultant -
[5 empty] | 287.3688 | 194.6838 | 188.0959 | 202.4833 | 145.6153 | 145.6153 | 175.955 | 116.1338 | 137.0081 | 119.5919 | 135.7713 | 119.7433 | 47.9579 | 259.7046 | 162.4511 | 105.9617 | 262.355 | 140.3652 | 101.065 | 84.936
Work Elem. |  |  | Sub Elem. | Description | Sr Program Director | Sr Proj Mgr | Sr Proj Mgr | Pr Planner | Pr Proj Controls | Pr Proj Manager | Project Manager | Sr Engineer | Sr Project Engineer | Sr Engineer | Supervising Engineer | Pr Designer | Cad | Vice President | Se Construction Engineer | Engineer II | Program Director | Sr Member Tech Staff | Sr IT Analyst | Sr Admin Asst | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 1432 | 253237
| 1.1 | Project Management |  |  | 32 | 64 |  | 20 | 80 |  | 20 | [12 empty] | 36 | 252 | 43931
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan |  |  |  | 4 | 60 |  |  | 2 | 8 | [12 empty] | 12 | 86 | 14783
| 1.3 | Quality Management Plan |  |  |  | 6 |  |  |  | 24 | [14 empty] | 30 | 4663
| 1.4 | Project Meetings | [23 empty] | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 28 |  | 18 |  |  | 18 | [13 empty] | 64 | 12263
|  | 1.4.2 |  | Consultant Team Meetings |  | 12 |  | 9 |  |  | 9 | [13 empty] | 30 | 5742
| 1.5 | Consultant Co-location Plan |  |  |  | 4 | [18 empty] | 4 | 779
| 1.6 | Monthly Progress Reporting and Invoicing |  |  |  | 36 | [15 empty] | 192 |  | 12 | 240 | 34978
| 1.7 | Document Management |  |  |  | 24 | [16 empty] | 56 |  | 80 | 10332
| 1.8 | Team Direction and Oversight |  |  |  | 646 | [18 empty] | 646 | 125766
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 271 | 54419
| 2.1 | Community Engagement Plan (CEP) |  |  |  | 4 |  |  |  | 4 | [14 empty] | 8 | 1361
| 2.2 | Community meetings and Events |  |  |  | 40 |  | 20 |  |  | 20 | [13 empty] | 80 | 15356
[25 empty] | 0 | 0
| 2.3 | Open Houses |  |  |  | 26 |  | 10 |  |  | 10 | [13 empty] | 46 | 8846
[25 empty] | 0 | 0
| 2.4 | Community Database |  |  |  | 0 | [18 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops |  |  |  | 30 |  | 30 | [9 empty] | 30 | [6 empty] | 90 | 19706
| 2.6 | Community Briefings |  |  |  | 35 | [18 empty] | 35 | 6814
| 2.7 | Websites and Social Media |  |  |  | 12 | [18 empty] | 12 | 2336
WE-03 | Practical Design Assessment | [23 empty] | 1313 | 273324
| 3.1 | Baseline and Contextual Need Statement |  |  |  | 6 |  | 22 |  | 3 | [7 empty] | 12 | [6 empty] | 43 | 9176
| 3.2 | Design Control Selection |  |  |  | 36 |  | 42 |  | 2 | 106 | [6 empty] | 24 | [5 empty] | 8 | 218 | 41368
| 3.3 | Performance Metrics and Targets |  |  |  | 36 |  | 138 |  | 2 | 18 | [6 empty] | 108 | [5 empty] | 8 | 310 | 67137
| 3.4 | Contributing Factors Analysis |  |  |  | 36 |  | 138 |  | 2 | 18 | [6 empty] | 108 | [5 empty] | 8 | 310 | 67137
| 3.5 | Alternatives Development and Evaluation |  |  |  | 48 |  | 162 |  | 6 | 110 | [6 empty] | 98 | [5 empty] | 8 | 432 | 88506
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 282 | 53172
| 4.1 | Data Collection | [5 empty] | 32 |  | 8 | [13 empty] | 4 | 44 | 7984
| 4.2 | Existing Conditions 2016 Analysis | [5 empty] | 40 |  | 8 | [13 empty] | 4 | 52 | 9604
| 4.3 | Future Forecasts | [5 empty] | 78 |  | 8 | [13 empty] | 4 | 90 | 17298
| 4.4 | Alternatives Analysis | [5 empty] | 80 |  | 12 | [13 empty] | 4 | 96 | 18286
WE-05 | Survey | [23 empty] | 16 | 2722
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey |  | 8 |  |  |  | 8 | [14 empty] | 16 | 2722
WE-06 | Environmental | [23 empty] | 81 | 18674
| 6.1 | Environmental Management and Support |  |  |  | 12 | [18 empty] | 12 | 2336
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
|  | 6.2.2 |  | Wetland and Stream Assessment |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
|  | 6.2.3 |  | Biological Assessment |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
|  | 6.2.4 |  | Land Use Analysis |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis |  | 2 |  |  |  | 1 | [10 empty] | 48 |  |  |  | 51 | 13128
|  | 6.2.7 |  | Environmental Justice Analysis |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
|  | 6.2.8 |  | Hazardous Materials Analysis |  | 2 |  |  |  | 1 | [14 empty] | 3 | 535
WE-07 | Geotechnical Services | [23 empty] | 3 | 585
| 7.1 | Data Collection and Summary |  |  |  | 1 | [18 empty] | 1 | 195
| 7.2 | Geologic Hazards Screening |  |  |  | 1 | [18 empty] | 1 | 195
| 7.3 | Conceptual Foundation Recommendations |  |  |  | 1 | [18 empty] | 1 | 195
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 1445 | 185986
| 8.1 | Preliminary Utility Coordination |  |  | 0 | 0 | 0 | 0 | 0 | 2 | 14 | 40 | 0 | 96 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 176 | 21476
| 8.2 | Civil Preliminary Engineering
|  | 8.2.1 |  | Data Collection and Review |  |  | 16 | 30 | 0 | 0 | 16 | 40 | 0 | 30 | 0 | 8 | 0 | 0 | 0 | 30 | 0 | 0 | 0 | 6 | 176 | 24779
|  | 8.2.2 |  | Civil Design Criteria |  |  | 20 | 0 | 0 | 4 | 32 | 96 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 32 | 0 | 0 | 0 | 5 | 189 | 24939
|  | 8.2.3 |  | Basis of Design |  |  | 24 | 0 | 0 | 4 | 52 | 32 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | 0 | 0 | 4 | 132 | 19998
|  | 8.2.4 |  | Cost Estimating |  |  | 24 | 0 | 0 | 6 | 6 | 96 | 0 | 0 | 8 | 16 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 2 | 182 | 23308
| 8.3 | Preliminary Alternative Design
|  | 8.3.1 |  | Conceptual (5%) Plans |  |  | 6 | 0 | 0 | 6 | 24 | 82 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 156 | 0 | 0 | 0 | 8 | 438 | 51638
|  | 8.3.2 |  | Internal Team Coordination |  |  | 8 | 8 | 0 | 0 | 8 | 8 | 0 | 8 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 64 | 9310
|  | 8.3.3 |  | CAD Support for WE 2.8 |  |  | 0 | 0 | 0 | 0 | 11 | 16 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 28 | 0 | 0 | 0 | 5 | 88 | 10538
|  |  |  | Total | 32 | 1170 | 158 | 877 | 80 | 118 | 500 | 410 | 0 | 134 | 16 | 232 | 0 | 380 | 0 | 294 | 48 | 192 | 56 | 146 | 4843 | 842119

## EST COST (Prime-)
Agreement Number
Project Name
Prime Consultant
Cost Worksheet
| Firm Name: | PRIME CONSULTANT
Class | Classification | Role | Staff | Hours | x | Rate | = | Cost |  |  | Raw | OH | Fee | Burdened
26 | Sr Program Director | Principal in Charge |  | 32 |  | 113.85 |  | 3643.2 |  | 2.6667 | 113.85 | 138.7945 | 34.7242 | 287.3688 | 1.667%
23 | Sr Proj Mgr | Project Manager |  | 1170 |  | 77.13 |  | 90242.1 |  | 97.5 | 77.13 | 94.0292 | 23.5246 | 194.6838 | 60.94%
23 | Sr Proj Mgr | Cost Estimator |  | 158 |  | 74.52 |  | 11774.16 |  | 13.1667 | 74.52 | 90.8473 | 22.7286 | 188.0959 | 8.229%
22 | Pr Planner | Tranportation Mgr |  | 877 |  | 80.22 |  | 70352.94 |  | 73.0833 | 80.22 | 97.7962 | 24.4671 | 202.4833 | 45.68%
20 | Pr Proj Controls | Project Contoller |  | 80 |  | 57.69 |  | 4615.2 |  | 6.6667 | 57.69 | 70.3299 | 17.5954 | 145.6153 | 4.167%
23 | Pr Proj Manager | Quality Mgr |  | 118 |  | 57.69 |  | 6807.42 |  | 9.8333 | 57.69 | 70.3299 | 17.5954 | 145.6153 | 6.146%
22 | Project Manager | Design Mgr |  | 500 |  | 69.71 |  | 34855 |  | 41.6667 | 69.71 | 84.9835 | 21.2615 | 175.955 | 26.04%
19 | Sr Engineer | Desisgner |  | 410 |  | 46.01 |  | 18864.1 |  | 34.1667 | 46.01 | 56.0908 | 14.033 | 116.1338 | 21.35%
21 | Sr Project Engineer | Drainage Eng |  | 0 |  | 54.28 |  | 0 |  | 0 | 54.28 | 66.1727 | 16.5554 | 137.0081 | 0%
19 | Sr Engineer | Drainage Eng |  | 134 |  | 47.38 |  | 6348.92 |  | 11.1667 | 47.38 | 57.761 | 14.4509 | 119.5919 | 6.979%
22 | Supervising Engineer | Structural Design |  | 16 |  | 53.79 |  | 860.64 |  | 1.3333 | 53.79 | 65.5754 | 16.406 | 135.7713 | 0.8333%
19 | Pr Designer | CAD Mgr |  | 232 |  | 47.44 |  | 11006.08 |  | 19.3333 | 47.44 | 57.8341 | 14.4692 | 119.7433 | 12.08%
13 | Cad | CAD Tech |  | 0 |  | 19 |  | 0 |  | 0 | 19 | 23.1629 | 5.795 | 47.9579 | 0%
26 | Vice President | Vice Pres |  | 380 |  | 102.89 |  | 39098.2 |  | 31.6667 | 102.89 | 125.4332 | 31.3815 | 259.7046 | 19.79%
21 | Se Construction Engineer | Engineer |  | 0 |  | 64.36 |  | 0 |  | 0 | 64.36 | 78.4613 | 19.6298 | 162.4511 | 0%
18 | Engineer II | Engineer II |  | 294 |  | 41.98 |  | 12342.12 |  | 24.5 | 41.98 | 51.1778 | 12.8039 | 105.9617 | 15.31%
25 | Program Director | Program Director |  | 48 |  | 103.94 |  | 4989.12 |  | 4 | 103.94 | 126.7133 | 31.7017 | 262.355 | 2.5%
21 | Sr Member Tech Staff | Sr Member Tech |  | 192 |  | 55.61 |  | 10677.12 |  | 16 | 55.61 | 67.7942 | 16.9611 | 140.3652 | 10%
18 | Sr IT Analyst | Sr IT Analyst |  | 56 |  | 40.04 |  | 2242.24 |  | 4.6667 | 40.04 | 48.8128 | 12.2122 | 101.065 | 2.917%
16 | Sr Admin Asst | Sr Admin Asst |  | 146 |  | 33.65 |  | 4912.9 |  | 12.1667 | 33.65 | 41.0227 | 10.2632 | 84.936 | 7.604%
|  |  | Total Hours | 4843
[7 empty] | Total Direct Labor | 333631.46
Overhead & Fee
| Overhead Cost @ | 121.9% | of Direct Labor |  |  |  |  | 406730.1129
| Fee @ | 30.5% | Direct Labor |  |  |  |  | 101757.5953
| Total Direct Labor, Overhead and Fee | [6 empty] | 842119.1682
| Direct Non-Salary Costs | [6 empty] | Cost
| Automobile |  | 8120 | 0.54 |  |  |  | 4384.8
|  |  | Miles | $/Mi
| Flight |  | 12 | 300 |  |  |  | 3600
| Rental Car |  | 12 | 150 |  |  |  | 1800 | 2 day rental @ $75/day = $150
| Fuel |  | 90 | 2.75 |  |  |  | 247.5
| Parking |  | 24 | 12 |  |  |  | 288
| Hotel |  | 6 | 202 |  |  |  | 1212
|  |  | 6 | 157 |  |  |  | 942
| Meals |  | 24 | 74 |  |  |  | 1776
| Photocopies |  | 1000 | 0.1 |  |  |  | 100
|  |  | Copies | $/copy
| Traffic Counts | [6 empty] | 6400
Advance Traffic Control
| Postage / Delivery (allowance) |  | Est. |  |  |  |  | 150
| Parking |  | 5 | 10 |  |  |  | 50
|  |  | Events | $/event
[7 empty] | Direct Non-Salary Costs Total | 20950.3
[6 empty] | Prime Subtotal |  | 863069.4682
Subconsultant Expenses
| Subconsultant 1 | [6 empty] | 151073
| Subconsultant 2 | [6 empty] | 374719
| Subconsultant 3 | [6 empty] | 38786
| Subconsultant 4 | [6 empty] | 102302
| Subconsultant 5 | [6 empty] | 40340
| Subconsultant 6 | [6 empty] | 18496
| Subconsultant 7 | [6 empty] | 122017.3662
| Total Subconsultant Expense | [6 empty] | 847733.3662
[6 empty] | Total |  | 1710802.8344
| Agreement Agreement Number Total Cost: |  |  |  |  | Rounded |  | 1710803

## EST HRS (Sub-1)
Agreement Number Project Name SUBCONSULTANT 1 ESTIMATED HOURS
SUBCONSULTANT 1 - Public Affairs
Labor Estimate |  |  |  |  | 346.7477 | 146.7682 | 69.2542 | 116.8109
Work Elem. |  |  | Sub Elem. | Description | Co-Pres | Sr Acct Mgr | Sr Project Coord | Designer | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
[5 empty] | Communications Strategy | Project Mgr | Proj Assist | Design
WE-01 | Project Management | [23 empty] | 79 | 14705
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [23 empty] | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 28 | [18 empty] | 28 | 4110
|  | 1.4.2 |  | Consultant Team Meetings | 12 | 12 | 0 | 3 | [16 empty] | 27 | 6273
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  | 4 | 20 | 0 | 0 | [16 empty] | 24 | 4322
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 1019 | 120301
| 2.1 | Community Engagement Plan (CEP) |  |  | 6 | 32 | 0 | 0 | [16 empty] | 38 | 6777
| 2.2 | Community meetings and Events |  |  | 0 | 60 | 120 | 33 | [16 empty] | 213 | 20971
[5 empty] | 0 |  | 0 | [17 empty] | 0 | 0
| 2.3 | Open Houses |  |  | 10 | 73 | 167 | 52 | [16 empty] | 302 | 31821
[25 empty] | 0 | 0
| 2.4 | Community Database |  |  | 0 | 22 | 26 | 0 | [16 empty] | 48 | 5030
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops |  |  | 6 | 120 | 26 | 30 | [16 empty] | 182 | 24998
| 2.6 | Community Briefings |  |  | 7 | 70 | 49 | 7 | [16 empty] | 133 | 16912
| 2.7 | Websites and Social Media |  |  | 8 | 45 | 30 | 20 | [16 empty] | 103 | 13792
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 64 | 9688
| 6.1 | Environmental Management and Support | [22 empty] | 0 | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | 5 | 10 | 10 | 0 | [16 empty] | 25 | 3894
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | 5 | 22 | 12 | 0 | [16 empty] | 39 | 5794
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0 | 0
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0 | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0 | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0 | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0 | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0 | 0
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | [20 empty] | 0 | 0
|  | 8.3.2 |  | Internal Team Coordination | [20 empty] | 0 | 0
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
|  |  |  | Total | 63 | 514 | 440 | 145 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1162 | 144694

## EST COST (Sub-1)
Agreement Number
Project Name
SUBCONSULTANT 1 -- PUBLIC AFFAIRS
Cost Worksheet
Firm Name: SUB 1
Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
Co-President | Communications Strategy |  | 63 |  | 109.15 |  | 6876.45 | 109.15 | 206.49 | 31.1077 | 346.7477
Sr Acct Manager | Project Manager |  | 514 |  | 46.2 |  | 23746.8 | 46.2 | 87.4012 | 13.167 | 146.7682
Sr Project Coord | Project Coord |  | 440 |  | 21.8 |  | 9592 | 21.8 | 41.2412 | 6.213 | 69.2542
Designer | Designer |  | 145 |  | 36.77 |  | 5331.65 | 36.77 | 69.5615 | 10.4794 | 116.8109
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
|  | Total Hours | 1162 |  |  | Total Direct Labor | 45546.9
Overhead & Fee
Overhead Cost @ | 189.2% | of Direct Labor |  |  |  |  | 86165.6254
Fee @ | 28.5% | Direct Labor |  |  |  |  | 12980.8665
Total Direct Labor, Overhead and Fee | [6 empty] | 144693.3919
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 2000 | 0.54 |  |  |  | 1080
|  | Miles | $/Mi
Photocopies |  | 1000 | 0.1 |  |  |  | 100
|  | Copies | $/copy
Postage / Delivery (allowance) |  | Est. based on two mailings x 2,000 ea at $.40/ea |  |  |  |  | 1600
|  | Open House display boards & handouts + doorhangers |  |  |  |  | 3500
Parking |  | 10 | 10 |  |  |  | 100
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 6380
[5 empty] | Total |  | 151073.3919
SUBCONSULTANT 1 -- PUBLIC AFFAIRS Total Cost: |  |  |  |  | Rounded |  | 151073

## EST HRS (Sub-2)
Agreement Number Project Name SUBCONSULTANT 2 ESTIMATED HOURS
SUBCONSULTANT 2 - Traffic
[5 empty] | 272.4359 | 205.0734 | 203.611 | 172.8393 | 168.452 | 124.5186 | 98.1342 | 98.1342 | 117.1761 | 98.1342
Work Elem. |  |  | Sub Elem. | Description | Principal | Principal II | Sr Associate I | Associate I | Sr Engineer Planner IV | Sr Engineer Planner III | Entineer Planner III | Engineer Planner II | Sr Engineer Tech III | Sr Admin Assist III | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 36 | 4799
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [23 empty] | 0
|  | 1.4.1 |  | STATE Team Meetings | [20 empty] | 0 | 0
|  | 1.4.2 |  | Consultant Team Meetings | [20 empty] | 0 | 0
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  |  |  | 12 | [6 empty] | 24 | [10 empty] | 36 | 4799
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 2611 | 369359
| 4.1 | Data Collection |  |  |  | 6 | 31 |  | 8 | 18 | 112 |  | 98 | [11 empty] | 273 | 33606
| 4.2 | Existing Conditions 2016 Analysis |  |  | 8 | 26 | 68 | 90 | 0 | 132 | 196 | 0 | 8 | [11 empty] | 528 | 73521
| 4.3 | Future Forecasts |  |  | 0 | 40 | 56 | 0 | 86 | 204 | 36 | 0 | 20 | [11 empty] | 442 | 65370
| 4.4 | Alternatives Analysis |  |  | 8 | 92 | 214 | 142 | 0 | 622 | 196 | 0 | 94 | [11 empty] | 1368 | 196862
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 0 | 0
| 6.1 | Environmental Management and Support | [22 empty] | 0 | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0 | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0 | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0 | 0
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0 | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0 | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0 | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0 | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0 | 0
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | [20 empty] | 0 | 0
|  | 8.3.2 |  | Internal Team Coordination | [20 empty] | 0 | 0
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
|  |  |  | Total | 16 | 164 | 381 | 232 | 94 | 976 | 540 | 0 | 220 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2647 | 374158

## EST COST (Sub-2)
Agreement Number
Project Name
SUBCONSULTANT 2 -- Traffic
Cost Worksheet
Firm Name: SUB 2
Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
Principal | Principal-in-Charge |  | 16 |  | 89.42 |  | 1430.72 | 89.42 | 157.5312 | 25.4847 | 272.4359
Principal II | Technical Principal |  | 164 |  | 67.31 |  | 11038.84 | 67.31 | 118.58 | 19.1833 | 205.0734
Senior Associate I | Project Manager |  | 381 |  | 66.83 |  | 25462.23 | 66.83 | 117.7344 | 19.0465 | 203.611
Associate I | Sr. Operations Modeler |  | 232 |  | 56.73 |  | 13161.36 | 56.73 | 99.9412 | 16.168 | 172.8393
Sr. Engineer/Planner IV | Sr. Travel Demand Modeler |  | 94 |  | 55.29 |  | 5197.26 | 55.29 | 97.4044 | 15.7576 | 168.452
Sr. Engineer/Planner III | Sr. Transportation Analyst |  | 976 |  | 40.87 |  | 39889.12 | 40.87 | 72.0007 | 11.6479 | 124.5186
Engineer/Planner III | Analyst |  | 540 |  | 32.21 |  | 17393.4 | 32.21 | 56.7444 | 9.1799 | 98.1342
Engineer/Planner II | Analyst |  | 0 |  | 32.21 |  | 0 | 32.21 | 56.7444 | 9.1799 | 98.1342
Sr. Engineering Technician III | Visual Communcations |  | 220 |  | 38.46 |  | 8461.2 | 38.46 | 67.755 | 10.9611 | 117.1761
Sr. Administrative Assistant III | Administrative |  | 24 |  | 32.21 |  | 773.04 | 32.21 | 56.7444 | 9.1799 | 98.1342
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
[8 empty] | 0 | 0 | 0 | 0
|  | Total Hours | 2647 |  |  | Total Direct Labor | 122807.17
Overhead & Fee
Overhead Cost @ | 176.2% | of Direct Labor |  |  |  |  | 216349.3914
Fee @ | 28.5% | Direct Labor |  |  |  |  | 35000.0434
Total Direct Labor, Overhead and Fee | [6 empty] | 374156.6048
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 560 | 0.54 |  |  |  | 302.4
|  | Miles | $/Mi
Photocopies |  | 2600 | 0.1 |  |  |  | 260
|  | Copies | $/copy
Est.
Parking |  | 0 | 10 |  |  |  | 0
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 562.4
[5 empty] | Total |  | 374719.0048
SUBCONSULTANT 2 -- Traffic Total Cost: |  |  |  |  | Rounded |  | 374719

## EST HRS (Sub-3)
Agreement Number Project Name SUBCONSULTANT 3 ESTIMATED HOURS
SUBCONSULTANT 3-- Environmental
Labor Estimate |  |  |  |  | 204.0736 | 204.0736 | 133.6549 | 88.2663 | 63.6414 | 102.9278 | 73.6047 | 135.005
Work Elem. |  |  | Sub Elem. | Description | Principal | Principal | Sr Scientist | Proj Scientist | Staff Scientist | Accting | Admin | Sr Historian | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 64 | 10457
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [23 empty] | 0
|  | 1.4.1 |  | STATE Team Meetings | 4 | [19 empty] | 4 | 816
|  | 1.4.2 |  | Consultant Team Meetings | 24 |  |  | 12 | [16 empty] | 36 | 5957
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  | 12 |  |  |  |  | 12 | [14 empty] | 24 | 3684
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 178 | 27961
| 6.1 | Environmental Management and Support |  |  | 50 | [19 empty] | 50 | 10204
| 6.2 | Environmental Analysis and Summary Memorandum |  |  | 8 |  | 4 | 12 | [16 empty] | 24 | 3226
|  | 6.2.1 |  | Cultural Resources Study | 4 | [6 empty] | 16 | [12 empty] | 20 | 2976
|  | 6.2.2 |  | Wetland and Stream Assessment | 8 |  | 24 | 18 | [16 empty] | 50 | 6429
|  | 6.2.3 |  | Biological Assessment | 2 | 4 | 6 | 12 | [16 empty] | 24 | 3086
|  | 6.2.4 |  | Land Use Analysis | 2 | [19 empty] | 2 | 408
|  | 6.2.5 |  | Air Quality Analysis | 2 | [19 empty] | 2 | 408
|  | 6.2.6 |  | Noise Analysis | 2 | [19 empty] | 2 | 408
|  | 6.2.7 |  | Environmental Justice Analysis | 2 | [19 empty] | 2 | 408
|  | 6.2.8 |  | Hazardous Materials Analysis | 2 | [19 empty] | 2 | 408
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0 | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0 | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0 | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0 | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0 | 0
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | [20 empty] | 0 | 0
|  | 8.3.2 |  | Internal Team Coordination | [20 empty] | 0 | 0
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
|  |  |  | Total | 122 | 4 | 34 | 54 | 0 | 12 | 0 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 242 | 38418

## EST COST (Sub 3)
Agreement Number
Project Name
SUBCONSULTANT 3 -- Environmental
Cost Worksheet
Firm Name: SUB 3
Class | Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
| Principal | Permitting/ESA |  | 122 |  | 75.58 |  | 9220.76 | 75.58 | 106.9533 | 21.5403 | 204.0736
| Principal | Environmental Pr Mgr |  | 4 |  | 75.58 |  | 302.32 | 75.58 | 106.9533 | 21.5403 | 204.0736
| Sr Scientist | Permittint/wetland/ESA |  | 34 |  | 49.5 |  | 1683 | 49.5 | 70.0474 | 14.1075 | 133.6549
| Project Scientist | Permitting/wetland/ESA |  | 54 |  | 32.69 |  | 1765.26 | 32.69 | 46.2596 | 9.3166 | 88.2663
| Staff Scientist | Wetlands/SEPA/NEPT |  | 0 |  | 23.57 |  | 0 | 23.57 | 33.3539 | 6.7174 | 63.6414
| Accounting |  |  | 12 |  | 38.12 |  | 457.44 | 38.12 | 53.9436 | 10.8642 | 102.9278
| Administrative |  |  | 0 |  | 27.26 |  | 0 | 27.26 | 38.5756 | 7.7691 | 73.6047
| Senior Historian |  |  | 16 |  | 50 |  | 800 | 50 | 70.755 | 14.25 | 135.005
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
[9 empty] | 0 | 0 | 0 | 0
|  |  | Total Hours | 242 |  |  | Total Direct Labor | 14228.78
Overhead & Fee
| Overhead Cost @ | 141.5% | of Direct Labor |  |  |  |  | 20135.1466
| Fee @ | 28.5% | Direct Labor |  |  |  |  | 4055.2023
| Total Direct Labor, Overhead and Fee | [6 empty] | 38419.1289
| Direct Non-Salary Costs | [6 empty] | Cost
| Automobile |  | 384 | 0.54 |  |  |  | 207.36
|  |  | Miles | $/Mi
| Photocopies |  | 100 | 0.1 |  |  |  | 10
|  |  | Copies | $/copy
| Postage / Delivery (allowance) |  | Est. |  |  |  |  | 0
| Parking |  | 15 | 10 |  |  |  | 150
|  |  | Events | $/event
[7 empty] | Direct Non-Salary Costs Total | 367.36
[6 empty] | Total |  | 38786.4889
| SUBCONSULTANT 3 -- Environmental Total Cost: |  |  |  |  | Rounded |  | 38786

## EST HRS (Sub-4)
Agreement Number Project Name SUBCONSULTANT 4 ESTIMATED HOURS
SUBCONSULTANT 4 - Civil Cost Estimating
[5 empty] | 235.9974 | 193.2106 | 127.7683 | 95.0471 | 128.1423 | 158.1522 | 98.1634 | 71.6749
Work Elem. |  |  | Sub Elem. | Description | Principal | Project Manager | Lead Engineer | Design Engineer | CAD Tech | Contracts Admin | Accountant | Clerical | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 72 | 12507
| 1.1 | Project Management |  |  | 6 | 6 | [18 empty] | 12 | 2575
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [23 empty] | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 4 | [18 empty] | 4 | 773
|  | 1.4.2 |  | Consultant Team Meetings |  | 12 | [18 empty] | 12 | 2319
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  |  | 24 |  |  |  | 4 | 16 | [13 empty] | 44 | 6840
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 0 | 0
| 6.1 | Environmental Management and Support | [22 empty] | 0 | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0 | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0 | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0 | 0
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 668 | 85590
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review |  | 8 | 8 | 12 | 2 | 0 | 0 | 2 | [12 empty] | 32 | 4108
|  | 8.2.2 |  | Civil Design Criteria | 2 | 24 | 32 | 16 | 0 | 0 | 0 | 6 | [12 empty] | 80 | 11148
|  | 8.2.3 |  | Basis of Design | 2 | 24 | 16 | 8 | 0 | 0 | 0 | 4 | [12 empty] | 54 | 8200
|  | 8.2.4 |  | Cost Estimating | 0 | 8 | 32 | 72 | 8 | 0 | 0 | 0 | [12 empty] | 120 | 13503
| 8.3 | Preliminary Alternative Design |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | 10 | 16 | 48 | 108 | 108 | 0 | 0 | 0 | [12 empty] | 290 | 35689
|  | 8.3.2 |  | Internal Team Coordination | 0 | 18 | 18 | 0 | 0 | 0 | 0 | 0 | [12 empty] | 36 | 5778
|  | 8.3.3 |  | CAD Support for WE 2.8 | 0 | 8 | 8 | 16 | 24 | 0 | 0 | 0 | [12 empty] | 56 | 7164
|  |  |  | Total | 20 | 152 | 162 | 232 | 142 | 4 | 16 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 740 | 98097

## EST COST (Sub-4)
Agreement Number
Project Name
SUBCONSULTANT 4 -- CIVIL COST ESTIMATING
Cost Worksheet
Firm Name: SUB 4
Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
Principal | Director of Design |  | 20 |  | 75.73 |  | 1514.6 | 75.73 | 138.6843 | 21.5831 | 235.9974
Project Manager | Sr Associate |  | 152 |  | 62 |  | 9424 | 62 | 113.5406 | 17.67 | 193.2106
Project Manager | Lead Engineer |  | 162 |  | 41 |  | 6642 | 41 | 75.0833 | 11.685 | 127.7683
Engineer II | Design Engineer |  | 232 |  | 30.5 |  | 7076 | 30.5 | 55.8546 | 8.6925 | 95.0471
CAD Manager | CAD Tech |  | 142 |  | 41.12 |  | 5839.04 | 41.12 | 75.3031 | 11.7192 | 128.1423
Contracts Admin | Human Resources |  | 4 |  | 50.75 |  | 203 | 50.75 | 92.9385 | 14.4637 | 158.1522
Sr Accountant | Accounting |  | 16 |  | 31.5 |  | 504 | 31.5 | 57.6859 | 8.9775 | 98.1634
Admin Assist | Clerical |  | 12 |  | 23 |  | 276 | 23 | 42.1199 | 6.555 | 71.6749
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Hours | 740 |  |  | Total Direct Labor | 31478.64
Overhead & Fee
Overhead Cost @ | 183.1% | of Direct Labor |  |  |  |  | 57646.8334
Fee @ | 28.5% | Direct Labor |  |  |  |  | 8971.4124
Total Direct Labor, Overhead and Fee | [6 empty] | 98096.8858
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 640 | 0.54 |  |  |  | 345.6
|  | Miles | $/Mi
CAD/Computer |  | 348 | 10 |  |  |  | 3480
|  | Hours | $/hour
Photocopies |  | 1000 | 0.1 |  |  |  | 100
|  | Copies | $/copy
Postage / Delivery (allowance) |  | Est. |  |  |  |  | 200
Parking |  | 4 | 20 |  |  |  | 80
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 4205.6
[5 empty] | Total |  | 102302.4858
SUBCONSULTANT 4 -- CIVIL COST ESTIMATING Total Cost: |  |  |  |  | Rounded |  | 102302

## EST HRS (Sub-5)
Agreement Number Project Name SUBCONSULTANT 5 ESTIMATED HOURS
SUBCONSULTANT 5 - Alternatives Analysis
[5 empty] | 167.3416 | 167.3416 | 158.686 | 124.0636 | 139.2109 | 92.3264 | 83.6708
Work Elem. |  |  | Sub Elem. | Description | Principal | Sr Engineer | Sr Civil Engineer | Project Design Engineer | CADD Manager | CAD/GIS Tech | Admin | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 41 | 5856
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [22 empty] | 0 | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 4 | [18 empty] | 4 | 669
|  | 1.4.2 |  | Consultant Team Meetings | 1 | 12 | [18 empty] | 13 | 2175
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  |  | 12 |  |  |  |  | 12 | [13 empty] | 24 | 3012
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 24 | 2978
| 6.1 | Environmental Management and Support | [5 empty] | 24 | [16 empty] | 24 | 2978
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0 | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0 | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0 | 0
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 249 | 31186
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review |  | 4 |  | 32 | 4 | [15 empty] | 40 | 5196
|  | 8.2.2 |  | Civil Design Criteria |  | 1 |  | 8 | [16 empty] | 9 | 1160
|  | 8.2.3 |  | Basis of Design |  | 4 |  | 16 | [16 empty] | 20 | 2654
|  | 8.2.4 |  | Cost Estimating |  | 10 |  | 60 | [16 empty] | 70 | 9117
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans |  | 4 |  | 72 |  | 24 | [14 empty] | 100 | 11818
|  | 8.3.2 |  | Internal Team Coordination |  |  |  | 10 | [16 empty] | 10 | 1241
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
WE-09 | Initial Quality Control | [23 empty] | 0 | 0
| 9.1 | Quality Control Reviews | [22 empty] | 0 | 0
|  |  |  | Total | 1 | 51 | 0 | 222 | 4 | 24 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 314 | 40020

## EST COST (Sub-5)
Agreement Number
Project Name
SUBCONSULTANT 5-- Engineering Alternatives Analysis
Cost Worksheet
Firm Name: SUB 5
Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
Principal | Pr Technical |  | 1 |  | 58 |  | 58 | 58 | 92.8116 | 16.53 | 167.3416
Proj Eng/Sr Eng | Proj Mgr |  | 51 |  | 58 |  | 2958 | 58 | 92.8116 | 16.53 | 167.3416
Senior Civil Engineer | Sr Drainage Eng |  | 0 |  | 55 |  | 0 | 55 | 88.011 | 15.675 | 158.686
Proj/Design Eng | Drainage Design |  | 222 |  | 43 |  | 9546 | 43 | 68.8086 | 12.255 | 124.0636
Sr CAD Drafter | CADD Manager |  | 4 |  | 48.25 |  | 193 | 48.25 | 77.2096 | 13.7512 | 139.2109
CAD Drafter | CAD/GIS Tech |  | 24 |  | 32 |  | 768 | 32 | 51.2064 | 9.12 | 92.3264
Administration | Admin/Tech Editor |  | 12 |  | 29 |  | 348 | 29 | 46.4058 | 8.265 | 83.6708
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Hours | 314 |  |  | Total Direct Labor | 13871
Overhead & Fee
Overhead Cost @ | 160% | of Direct Labor |  |  |  |  | 22196.3742
Fee @ | 28.5% | Direct Labor |  |  |  |  | 3953.235
Total Direct Labor, Overhead and Fee | [6 empty] | 40020.6092
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 350 | 0.54 |  |  |  | 189
|  | Miles | $/Mi
Photocopies |  | 100 | 0.1 |  |  |  | 10
|  | Copies | $/copy
Postage / Delivery (allowance) |  | Est. |  |  |  |  | 0
Parking |  | 12 | 10 |  |  |  | 120
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 319
[5 empty] | Total |  | 40339.6092
SUBCONSULTANT 5-- Engineering Alternatives Analysis Total Cost: |  |  |  |  | Rounded |  | 40340

## EST HRS (Sub-6)
Agreement Number Project Name SUBCONSULTANT 6 - ESTIMATED HOURS
SUBCONSULTANT 6 - GEOTECHNICAL
[5 empty] | 208.247 | 208.247 | 144.171 | 144.171 | 128.152 | 128.152 | 80.095 | 108.9292 | 96.114 | 108.9292
Work Elem. |  |  | Sub Elem. | Description | Hazard Analysis Lead | Geotech Lead | Geotech Engineer | Geotech Engineer | Hazard Analysis Engineer | Geotech Engineer | Hazard Analysis Engineer | Sr CADD | Word Processing | Reproduction | [10 empty] | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 31 | 5431
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [22 empty] | 0 | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 4 | [18 empty] | 4 | 833
|  | 1.4.2 |  | Consultant Team Meetings |  | 16 | [18 empty] | 16 | 3332
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  |  | 1 | 2 | [5 empty] | 8 | [11 empty] | 11 | 1266
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 0 | 0
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0 | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0 | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0 | 0
WE-06 | Environmental | [23 empty] | 40 | 4376
| 6.1 | Environmental Management and Support | [22 empty] | 0 | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0 | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0 | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | 2 |  |  |  | 16 |  | 16 | 2 | 2 | 2 | [10 empty] | 40 | 4376
WE-07 | Geotechnical Services | [23 empty] | 54 | 7805
| 7.1 | Data Collection and Summary |  |  |  | 4 | 16 |  |  | 6 |  | 2 | 2 | [11 empty] | 30 | 4319
| 7.2 | Geologic Hazards Screening |  |  |  | 2 | 4 |  |  | 4 | [14 empty] | 10 | 1506
| 7.3 | Conceptual Foundation Recommendations |  |  |  | 2 | 8 |  |  |  |  | 2 | 2 | [11 empty] | 14 | 1980
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0 | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [22 empty] | 0 | 0
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0 | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0 | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0 | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0 | 0
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | [20 empty] | 0 | 0
|  | 8.3.2 |  | Internal Team Coordination | [20 empty] | 0 | 0
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
|  |  |  | Total | 2 | 29 | 30 | 0 | 16 | 10 | 16 | 6 | 14 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 17612

## EST COST (Sub-6)
Agreement Number
Project Name
SUBCONSULTANT 6 -- GEOTECHNICAL
Cost Worksheet
Firm Name: SUB 6
Class | Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
25 | Vice President | Hazard Analysis Lead |  | 2 |  | 65 |  | 130 | 65 | 124.722 | 18.525 | 208.247
25 | Vice President | Proj Mgr/Geotechnical Lead |  | 29 |  | 65 |  | 1885 | 65 | 124.722 | 18.525 | 208.247
20 | Sr Professional III | Geotechnical Engineer |  | 30 |  | 45 |  | 1350 | 45 | 86.346 | 12.825 | 144.171
20 | Sr Professional III | Geotechnical Engineer |  | 0 |  | 45 |  | 0 | 45 | 86.346 | 12.825 | 144.171
19 | Sr Professional II | Hazard Analysis Engineer |  | 16 |  | 40 |  | 640 | 40 | 76.752 | 11.4 | 128.152
19 | Sr Professional II | Geotechnical Engineer |  | 10 |  | 40 |  | 400 | 40 | 76.752 | 11.4 | 128.152
15 | Professional II | Hazard Analysis Engineer |  | 16 |  | 25 |  | 400 | 25 | 47.97 | 7.125 | 80.095
17 | Sr Drafter | Sr CADD |  | 6 |  | 34 |  | 204 | 34 | 65.2392 | 9.69 | 108.9292
17 | Administration | Word Processing |  | 14 |  | 30 |  | 420 | 30 | 57.564 | 8.55 | 96.114
17 | Administration | Reproduction |  | 2 |  | 34 |  | 68 | 34 | 65.2392 | 9.69 | 108.9292
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | Total Hours | 125 |  |  | Total Direct Labor | 5497
Overhead & Fee
| Overhead Cost @ | 191.9% | of Direct Labor |  |  |  |  | 10547.6436
| Fee @ | 28.5% | Direct Labor |  |  |  |  | 1566.645
| Total Direct Labor, Overhead and Fee | [6 empty] | 17611.2886
| Direct Non-Salary Costs | [6 empty] | Cost
| Automobile |  | 250 | 0.54 |  |  |  | 135
|  |  | Miles | $/Mi
| Photocopies |  | 500 | 0.1 |  |  |  | 50
|  |  | Copies | $/copy
| Airphoto Review | [6 empty] | 350
| EDR Radius Map Report | [6 empty] | 300
| Parking |  | 5 | 10 |  |  |  | 50
|  |  | Events | $/event
[7 empty] | Direct Non-Salary Costs Total | 885
[6 empty] | Total |  | 18496.2886
| SUBCONSULTANT 6 -- GEOTECHNICAL Total Cost: |  |  |  |  | Rounded |  | 18496

## EST HRS (Sub-7)
Agreement Number Project Name SUBCONSULTANT 7 ESTIMATED HOURS
SUBCONSULTANT 7 - SURVEY
[5 empty] | 172.7506 | 158.8191 | 128.1698 | 117.0246 | 103.0931 | 94.7342 | 103.0931 | 80.8027
Work Elem. |  |  | Sub Elem. | Description | Project Principal | Survey Proj Mgr | Prof Land Surveyor | Project Engineer | Jr Engineer | Surveyor | Survey Tech / Drafter | Admin / Accounting | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours | Fee
WE-01 | Project Management | [23 empty] | 24 | 3482
| 1.1 | Project Management | [22 empty] | 0 | 0
[25 empty] | 0 | 0
[25 empty] | 0 | 0
| 1.2 | Project Management Plan | [22 empty] | 0 | 0
| 1.3 | Quality Management Plan | [22 empty] | 0 | 0
| 1.4 | Project Meetings | [22 empty] | 0 | 0
|  | 1.4.1 |  | STATE Team Meetings |  | 4 | [18 empty] | 4 | 635
|  | 1.4.2 |  | Consultant Team Meetings | 4 | 4 | [18 empty] | 8 | 1326
| 1.5 | Consultant Co-location Plan | [22 empty] | 0 | 0
| 1.6 | Monthly Progress Reporting and Invoicing |  |  | 6 | [6 empty] | 6 | [12 empty] | 12 | 1521
| 1.7 | Document Management | [22 empty] | 0 | 0
| 1.8 | Team Direction and Oversight | [22 empty] | 0 | 0
[25 empty] | 0 | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0 | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0 | 0
| 2.2 | Community meetings and Events | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.3 | Open Houses | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.4 | Community Database | [22 empty] | 0 | 0
[25 empty] | 0 | 0
| 2.5 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0 | 0
| 2.6 | Community Briefings | [22 empty] | 0 | 0
| 2.7 | Websites and Social Media | [22 empty] | 0 | 0
WE-03 | Practical Design Assessment | [23 empty] | 0 | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0 | 0
| 3.2 | Design Control Selection | [22 empty] | 0 | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0 | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0 | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0 | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0 | 0
| 4.1 | Data Collection | [22 empty] | 0 | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0 | 0
| 4.3 | Future Forecasts | [22 empty] | 0 | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0 | 0
WE-05 | Survey | [23 empty] | 1000 | 104274
| 5.1 | Existing Mapping | [23 empty] | 0
|  | 5.1.1 |  | Control and Datum |  | 4 | 16 | 40 | 12 | 40 | 60 | [13 empty] | 172 | 18579
|  | 5.1.2 |  | Topography |  | 4 | 60 |  | 80 | 300 | 120 | [13 empty] | 564 | 57364
|  | 5.1.3 |  | Utilities Survey |  | 4 | 40 | 40 | 60 | 80 | 40 | [13 empty] | 264 | 28331
WE-06 | Environmental | [23 empty] | 0 | 0
| 6.1 | Environmental Management and Support | [22 empty] | 0 | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0 | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0 | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0 | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0 | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0 | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0 | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0 | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0 | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0 | 0
WE-07 | Geotechnical Services | [23 empty] | 0 | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0 | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0 | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0 | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0 | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0 | 0
| 8.2 | Civil Preliminary Engineering | [23 empty] | 0
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0 | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0 | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0 | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0 | 0
| 8.3 | Preliminary Alternative Design | [22 empty] | 0 | 0
|  | 8.3.1 |  | Conceptual (5%) Plans | [20 empty] | 0 | 0
|  | 8.3.2 |  | Internal Team Coordination | [20 empty] | 0 | 0
|  | 8.3.3 |  | CAD Support for WE 2.8 | [20 empty] | 0 | 0
|  |  |  | Total | 10 | 20 | 116 | 80 | 152 | 420 | 220 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1024 | 107756

## EST COST (Sub-7)
Agreement Number
Project Name
SUBCONSULTANT 7 -- SURVEYING
Cost Worksheet
Firm Name: SUB 7
Classification | Role | Staff | Hours | x | Rate | = | Cost | Raw | OH | Fee | Burdened
Project Principal | Project Manager |  | 10 |  | 62 |  | 620 | 62 | 93.0806 | 17.67 | 172.7506
Survey Project Manager | Survey Review |  | 20 |  | 57 |  | 1140 | 57 | 85.5741 | 16.245 | 158.8191
Professional Land Surveyor | St Survey Lead |  | 116 |  | 46 |  | 5336 | 46 | 69.0598 | 13.11 | 128.1698
Project Engineer |  |  | 80 |  | 42 |  | 3360 | 42 | 63.0546 | 11.97 | 117.0246
Junior Engineer | Basemapping |  | 152 |  | 37 |  | 5624 | 37 | 55.5481 | 10.545 | 103.0931
Surveyor | Surveyor |  | 420 |  | 34 |  | 14280 | 34 | 51.0442 | 9.69 | 94.7342
Survey Technician / Drafter | Drafter |  | 220 |  | 37 |  | 8140 | 37 | 55.5481 | 10.545 | 103.0931
Admin / Accounting | Clerical |  | 6 |  | 29 |  | 174 | 29 | 43.5377 | 8.265 | 80.8027
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0
|  | Total Hours | 1024 |  |  | Total Direct Labor | 38674
Overhead & Fee
Overhead Cost @ | 150.1% | of Direct Labor |  |  |  |  | 58061.2762
Fee @ | 28.5% | Direct Labor |  |  |  |  | 11022.09
Total Direct Labor, Overhead and Fee | [6 empty] | 107757.3662
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 4000 | 0.54 |  |  |  | 2160
|  | Miles | $/Mi
Photocopies |  | 1000 | 0.1 |  |  |  | 100
|  | Copies | $/copy
Traffic control (TMA trucks, etc.) |  | Est. |  |  |  |  | 2400
3D Laser Scanner Usage |  | 12 | 800 |  |  |  | 9600
|  | Day | $/day
Parking |  | 0 | 10 |  |  |  | 0
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 14260
[5 empty] | Total |  | 122017.3662
SUBCONSULTANT 7 -- SURVEYING Total Cost: |  |  |  |  | Rounded |  | 122017

## EST HRS (Sub-Traffic Data) (hidden)
Y-11834 SR 9 /SR 204 PRIME ESTIMATED HOURS
SUBCONSULTANT - Data Traffic Gathering
Labor Estimate
Classification
Work Elem. |  |  | Sub Elem. | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | Total Hours
WE-01 | Project Management | [23 empty] | 0
| 1.1 | Scope Management | [22 empty] | 0
| 1.2 | Schedule Management | [22 empty] | 0
| 1.3 | Budget Management | [22 empty] | 0
| 1.4 | Communication Plan Development | [22 empty] | 0
| 1.5 | Quality Management Plan | [22 empty] | 0
| 1.6 | Project Meetings
|  | 1.6.1 |  | STATE Team Meetings | [20 empty] | 0
|  | 1.6.2 |  | Consultant Team Meetings | [20 empty] | 0
| 1.7 | Consultant Co-location Plan | [22 empty] | 0
| 1.8 | Monthly Progress Reporting and Invoicing | [22 empty] | 0
| 1.9 | Document Management | [22 empty] | 0
| 1.1 | Team Direction and Oversight | [22 empty] | 0
| 1.11 | Subconsultant Management | [22 empty] | 0
WE-02 | Public and Community Outreach and Engagement | [23 empty] | 0
| 2.1 | Community Engagement Plan (CEP) | [22 empty] | 0
| 2.2 | Community meetings and Events | [22 empty] | 0
| 2.3 | Graphic Support | [22 empty] | 0
| 2.4 | Open Houses | [22 empty] | 0
| 2.5 | Door to Door Outreach | [22 empty] | 0
| 2.6 | Community Database | [22 empty] | 0
| 2.7 | Mailings | [22 empty] | 0
| 2.8 | Multi Agency Interdisciplinary Stakeholder Advisory (MAISA) Workshops | [22 empty] | 0
| 2.9 | Elected Official Briefings | [22 empty] | 0
| 2.1 | Websites and Social Media | [22 empty] | 0
WE-03 | Practical Design Assessment | [23 empty] | 0
| 3.1 | Baseline and Contextual Need Statement | [22 empty] | 0
| 3.2 | Design Control Selection | [22 empty] | 0
| 3.3 | Performance Metrics and Targets | [22 empty] | 0
| 3.4 | Contributing Factors Analysis | [22 empty] | 0
| 3.5 | Alternatives Development and Evaluation | [22 empty] | 0
WE-04 | Traffic Analysis and Data Collection | [23 empty] | 0
| 4.1 | Data Collection | [22 empty] | 0
| 4.2 | Existing Conditions 2016 Analysis | [22 empty] | 0
| 4.3 | Future Forecasts | [22 empty] | 0
| 4.4 | Alternatives Analysis | [22 empty] | 0
WE-05 | Survey | [23 empty] | 0
| 5.1 | Existing Mapping
|  | 5.1.1 |  | Control and Datum | [20 empty] | 0
|  | 5.1.2 |  | Topography | [20 empty] | 0
|  | 5.1.3 |  | Utilities Survey | [20 empty] | 0
WE-06 | Environmental | [23 empty] | 0
| 6.1 | Environmental Management and Support | [22 empty] | 0
| 6.2 | Environmental Analysis and Summary Memorandum | [22 empty] | 0
|  | 6.2.1 |  | Cultural Resources Study | [20 empty] | 0
|  | 6.2.2 |  | Wetland and Stream Assessment | [20 empty] | 0
|  | 6.2.3 |  | Biological Assessment | [20 empty] | 0
|  | 6.2.4 |  | Land Use Analysis | [20 empty] | 0
|  | 6.2.5 |  | Air Quality Analysis | [20 empty] | 0
|  | 6.2.6 |  | Noise Analysis | [20 empty] | 0
|  | 6.2.7 |  | Environmental Justice Analysis | [20 empty] | 0
|  | 6.2.8 |  | Hazardous Materials Analysis | [20 empty] | 0
WE-07 | Geotechnical Services | [23 empty] | 0
| 7.1 | Data Collection and Summary | [22 empty] | 0
| 7.2 | Geologic Hazards Screening | [22 empty] | 0
| 7.3 | Conceptual Foundation Recommendations | [22 empty] | 0
WE-08 | Preliminary Engineering/Alternatives Analysis | [23 empty] | 0
| 8.1 | Preliminary Utility Coordination | [22 empty] | 0
| 8.2 | Civil Preliminary Engineering
|  | 8.2.1 |  | Data Collection and Review | [20 empty] | 0
|  | 8.2.2 |  | Civil Design Criteria | [20 empty] | 0
|  | 8.2.3 |  | Basis of Design | [20 empty] | 0
|  | 8.2.4 |  | Cost Estimating | [20 empty] | 0
WE-09 | Initial Quality Control | [23 empty] | 0
| 9.1 | Quality Control Reviews | [22 empty] | 0
|  |  |  | Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## EST COST (Traffic Data) (hidden)
Y-11834
SR 9 /SR 204
SUBCONSULTANT
Cost Worksheet
Firm Name: DATA TRAFFIC GATHERING
Classification |  |  | Hours | x | Rate | = | Cost
1 |  |  | 0 |  | 10 |  | 0
2 |  |  | 0 |  | 10 |  | 0
3 |  |  | 0 |  | 10 |  | 0
4 |  |  | 0 |  | 10 |  | 0
5 |  |  | 0 |  | 10 |  | 0
6 |  |  | 0 |  | 10 |  | 0
7 |  |  | 0 |  | 10 |  | 0
8 |  |  | 0 |  | 10 |  | 0
9 |  |  | 0 |  | 10 |  | 0
10 |  |  | 0 |  | 10 |  | 0
11 |  |  | 0 |  | 10 |  | 0
12 |  |  | 0 |  | 10 |  | 0
13 |  |  | 0 |  | 10 |  | 0
14 |  |  | 0 |  | 10 |  | 0
15 |  |  | 0 |  | 10 |  | 0
16 |  |  | 0 |  | 10 |  | 0
17 |  |  | 0 |  | 10 |  | 0
18 |  |  | 0 |  | 10 |  | 0
19 |  |  | 0 |  | 10 |  | 0
20 |  |  | 0 |  | 10 |  | 0
|  | Total Hours | 0 |  |  | Total Direct Labor | 0
Overhead & Fee
Overhead Cost @ | 100% | of Direct Labor |  |  |  |  | 0
Fee @ | 10% | Direct Labor |  |  |  |  | 0
Total Direct Labor, Overhead and Fee | [6 empty] | 0
Direct Non-Salary Costs | [6 empty] | Cost
Automobile |  | 0 | 0.54 |  |  |  | 0
|  | Miles | $/Mi
Photocopies |  | 0 | 0.1 |  |  |  | 0
|  | Copies | $/copy
Postage / Delivery (allowance) |  | Est. |  |  |  |  | 0
Parking |  | 0 | 10 |  |  |  | 0
|  | Events | $/event
[6 empty] | Direct Non-Salary Costs Total | 0
[5 empty] | Total |  | 0
SUBCONSULTANT Total Cost: |  |  |  |  | Rounded |  | 0