## Lessons Learned
Quality Office Lessions Learned Database for PS&E
Use the Table below to find issues that occurred and Lesson Learned
Region | Date | Project Title | Project Type | Project Size | Category | Issue | What we did right | What we did Wrong | Actions for Improvement
Northwest | 2019-01-25 | SR 000 EXAMPLE Project | Intersection | >$5,000,000 and <$10,000,000 | Traffic Control | Vehicular Traffic turning into Pedestrian Path from RAB | Installed Bollards | During construction we did not clearly identify path | During consturction evaluate the signage to ensure drivers understand

## DATA (hidden)
Region | Size | Type | Category
Northwest | < $100,000 | Drainage | Traffic Control
North Central | >$100,000 and <$500,000 | Interchange | Earthwork
Olympic | >$500,000 and <$1,000,000 | Intersection | Schedule
Southwest | >$1,000,000 and <$5,000,000 | Paving
South Central | >$5,000,000 and <$10,000,000 | Structures
Eastern | >$10,000,000 and <$20,000,000 | Widening
WSF | >$20,000,000 and <$50,000,000
>$50,000,000 and <$100,000,000
>$100,000,000