## RBS List (hidden)
CNS
CTR
DES
ENV
MGT
PSP
ROW
RR
STG
UTL

## Risk Mgmt Plan
|  |  | Project Title: |  |  | Project Manager: | [6 empty] | Project Base Cost (Current Year $M): | 100
|  |  | Project PIN #: |  |  | Project Manager's Phone: | [6 empty] | Estimate Reference Date:
|  |  | Last Update Date: | [9 empty] | Projected Completion Date: | 2029-12-31
- PROJECT RISK MANAGEMENT PLAN
Risk Identification | [8 empty] | Qualitative Analysis |  |  | Risk-Response Strategy |  |  |  |  | Monitoring and Control
[9 empty] | Probability | High Cost | None |  | High | Active | Avoid
[9 empty] | Threshold | Threshold | HighProbabilityLowImpact |  | Medium | Dormant | Transfer
[9 empty] | 50% | 2% | HighProbabilityHighImpact |  | Low | Retired | Mitigate
[11 empty] | LowProbabilityLowImpact |  |  |  | Accept
[10 empty] | High Time | LowProbabilityHighImpact |  |  |  | Exploit
[10 empty] | Threshold |  |  |  |  | Share
[10 empty] | 6 | X |  |  |  | Enhance
X
X
X
(3) |  | (4) | (5) | (6) | (7) |  |  |  | (10) | (11) | (12) | (13) | (1) | (2) | (14) | (15) | (16) | (17)
Refer to RBS categories and numbering | Date risk identified | Risk Discipline Category | RBS Level 2 | Detailed description of the risk. Includes information on the risk that is Specific, Measurable, Attributable, Relevant and Timebound. Describe the consequences of the risk to scope, schedule, budget or quality. | Notes may include specific trigger(s), justification for potential impact quantification, etc. |  |  |  | Assessment of the likelihood of occurrence. Valid entries are Low or High. Based on most likely impact values if quantitatively assessed. | The severity of the risk's effect on the projects objectives. Valid entries are Low or High. Based on probability if quantitatively assessed. | High: Substantial impact on cost, schedule, or technical. Substantial action required to alleviate issue. Low: Minimal to moderate impact on cost, schedule, or technical. Normal management oversight is sufficient. | Name of the person or office responsible for managing the risk event. | Instructions | Active=actively monitored & controlled Dormant = not a high priority; may become active in the future. Retired = no longer a threat to project objectives. | Avoid, Transfer, Mitigate, Acceptance, Exploit, Share, Enhance (See the Risk Management Guide for strategy definitions.) | Develop options and determine actions to be taken in response to the risk event. Immediate action may be required at the time of identification. Estimate value of risk and estimate cost to respond. | For example: Completion of wetland delineation expected: 2/28/00 | For example: Last status update 4/30/00. Wetland delineation completed 3/15/00. Over 1 acre of wetland was delineated, action is being taken to expedite meetings with regulatory agencies & expedite the effort to provide appropriate wetland mitigation & attain project permits.
[6 empty] | Direct Cost | Schedule | Likelihood
ID # | Date Identified | Discipline Category | Risk Breakdown Structure Level 2 | Risk Description | Additional Notes | Impact ($M) | Impact (months) | of Impact Occurring | Probability | Impact | Chart | Risk Owner | Priority | Status | Strategy | Actions to be Taken | Interval or Milestone | Date, Status and Review Comments
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
.
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
H
L
L H
Probability
Impact
Note on Q21: Strategy Avoid - You can change your plans to avoid the risk. This is a good strategy for when a risk has a potentially large impact on your project. Transfer – Transfer is a risk management strategy in projects where there are several parties. Essentially, you transfer the impact and management of the risk to someone else best capable of managing the risk. Mitigate - You limit the impact of a risk, so that if it does occur, the issue it creates is smaller and easier to manage. Accept - Accepting the risk means that while you have identified it and logged it in your risk management plan, you take no action. You simply accept that it might happen and decide to deal with it if it does. This is a good strategy to use for very small risks – risks that won’t have much of an impact on your project if they happen and could be easily dealt with if or when they arise. It could take a lot of time to put together an alternative risk management strategy or take action to deal with the risk, so it’s often a better use of your resources to do nothing for small risks. Exploit - Eliminate the uncertainty associated with the risk to ensure it occurs. Share – Allocating some or all of the ownership of the opportunity to a third party. Enhance – Increase the probability or the positive impacts of an opportunity.

## Risk Breakdown Structure
| RISK BREAKDOWN STRUCTURE | [10 empty] | Level1 | Level2
| Major Project Risks | [10 empty] | ENV - Environmental | ENV 10 - NEPA/SEPA – documentation completion, Section 4f/6f, challenges | ENV - Environmental | ENV 10 - NEPA/SEPA – documentation completion, Section 4f/6f, challenges | ENV 20 - ESA Issues – consultation, Biologic Assessments / Biological Opinions, Fish Passage | ENV 30 - Environmental Permitting – delays, appeals, unanticipated conditions | ENV 40 - Discoveries – cultural resources (Section 106), historic property impacts & mitigation | ENV 50 - Hazardous Matls - soil/ groundwater contamination, building / structure abatement/ lead paint | ENV 60 - Habitat Mitigation Issues – wetlands/ stream/ floodplain | ENV 70 - Environmental Justice (disadvantaged communities) – traffic mgmt, access, temp construction impacts | ENV 80 - Construction Impacts – water quality, TESC | ENV 90 - Noise (permanent mitigation) |  | ENV 900 - Other ENV Issues
[12 empty] | ENV - Environmental | ENV 20 - ESA Issues – consultation, Biologic Assessments / Biological Opinions, Fish Passage | STG - Structures & Geotechnical
Level 1 | ENV - Environmental | STG - Structures & Geotechnical | DES - Design / PS&E Roadway, Hydraulics, etc. | ROW - Right-of-Way Acquisition & Access | UTL - Utilities | RR - Railroad | PSP - Partnerships & Stakeholders | MGT - Management / Funding | CTR - Contracting & Procurement | CNS - Construction | Using the Risk Breakdown Structure (RBS) Each project is unique and has a specific project risk profile. Examples provided are an aid to identify risk types and are not to be considered complete or exclusive. Develop project risk registers by identifying and assessing risks for the project under review. The RBS provides several functions and benefits, including: 1) Consistent risk organization, approach and taxonomy (wording). 2) Common standard categories. 3) Allows for identification of trends (risk event categories, types and characteristics). 4) Offers a basis for initiating risk identification and elicitation. 5) Eases the ability to conduct risk surveys for those unable to attend workshops For more information regarding the RBS, see the Project Risk Management Guide. Note: decision-makers may have other enterprise level considerations that are difficult to quantify, such as: trust, credibility, safety, and reputation of the organization. | ENV - Environmental | ENV 30 - Environmental Permitting – delays, appeals, unanticipated conditions | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 10 - Roadway Design Change – vertical / horizontal alignment, earthwork, pavement | DES 20 - Roadway Design Criteria Change – Design Manual, design analysis approval, practical design considerations | DES 30 - Aesthetic Design Changes – Architectural, CSS, Landscaping | DES 40 - Hydraulic Design Changes – flow control, water quality, criteria changes | DES 50 - Traffic Design Changes – ITS, Illumination, Signals, intersections | DES 60 - WSDOT Initiated Changes – maintenance request, change to purpose and need | DES 70 - Tolling Design Changes – infrastructure requirements, toll collection, back-office | DES 80 - External Initiated Changes (contractor or other party) – innovation, ATC | DES 90 - ADA – curb ramp modifications require R/W, MEF approval |  | DES 900 - Other DES Issues
[12 empty] | ENV - Environmental | ENV 40 - Discoveries – cultural resources (Section 106), historic property impacts & mitigation | ROW - Right-of-Way Acquisition & Access
Level 2 | ENV 10 - NEPA/SEPA – documentation completion, Section 4f/6f, challenges | STG 10 - Structure Design Change – bridge superstructure, retaining walls | DES 10 - Roadway Design Change – vertical / horizontal alignment, earthwork, pavement | ROW 10 - Plan Development Issues – easements: temporary construction/subterranean, FHWA approval | UTL 10 - Plan Development Issues – design coordination, agreements | RR 10 - Plan Development Issues – design coordination, agreements, right-of-entry | PSP 10 - Tribal Issues | MGT 10 - Project Management Issues – change in managers / other key leadership | CTR 10 - Project Delivery Method – changes or issues | CNS 10 - Traffic Control & Staging – MOT / WZTC, multimodal traffic management |  | ENV - Environmental | ENV 50 - Hazardous Matls - soil/ groundwater contamination, building / structure abatement/ lead paint | UTL - Utilities | UTL 10 - Plan Development Issues – design coordination, agreements | UTL 20 - Practical Issues (in the field) – relocation, conflicts, discoveries |  | UTL 900 - Other UTL Issues
| ENV 20 - ESA Issues – consultation, Biologic Assessments / Biological Opinions, Fish Passage | STG 20 - Geotechnical Design Change – foundations, ground improvements, unsuitable materials | DES 20 - Roadway Design Criteria Change – Design Manual, design analysis approval, practical design considerations | ROW 20 - Project ROW Cost Change – change in land use/zoning, urbanization, market conditions | UTL 20 - Practical Issues (in the field) – relocation, conflicts, discoveries | RR 20 - Construction Coordination Issues – flagging, work restrictions / windows, right-of-entry requirements | PSP 20 - Public Involvement Issues | MGT 20 - Delay – indecision, submittal review | CTR 20 - Contract Language Issues – contract packaging, warranties, liquidated damages, DBE, insurance/bonding | CNS 20 - Construction Permitting – work restrictions |  | ENV - Environmental | ENV 60 - Habitat Mitigation Issues – wetlands/ stream/ floodplain | RR - Railroad | RR 10 - Plan Development Issues – design coordination, agreements, right-of-entry | RR 20 - Construction Coordination Issues – flagging, work restrictions / windows, right-of-entry requirements | RR 30 - Property Rights Issues – challenges in acquiring from RR, considerations for delivery method (DB vs DBB) |  | RR 900 - Other RR Issues
| ENV 30 - Environmental Permitting – delays, appeals, unanticipated conditions | STG 30 - Structural Design Criteria Change – seismic, hydraulic, geometric, building codes | DES 30 - Aesthetic Design Changes – Architectural, CSS, Landscaping | ROW 30 - Limited Access Issues – Access Revision Report (ARR), access hearing, permanent construction easement |  | RR 30 - Property Rights Issues – challenges in acquiring from RR, considerations for delivery method (DB vs DBB) | PSP 30 - Scope / Design Changes – artwork, shared-use pathways, arterial/intersection improvements | MGT 30 - Funding – availability, cash flow restrictions | CTR 30 - Contract Procurement Process Issues – addenda / extensions, protests | CNS 30 - Work Window Coordination – weather, in/over-water |  | ENV - Environmental | ENV 70 - Environmental Justice (disadvantaged communities) – traffic mgmt, access, temp construction impacts | PSP - Partnerships & Stakeholders | PSP 10 - Tribal Issues | PSP 20 - Public Involvement Issues | PSP 30 - Scope / Design Changes – artwork, shared-use pathways, arterial/intersection improvements | PSP 40 - Interagency Issues (Sound Transit, USFS, cities, counties, etc.) – design coordination, agreements | PSP 50 - Multimodal Considerations – design coordination, agreements, bicycle, pedestrians, transit |  | PSP 900 - Other PSP Issues
| ENV 40 - Discoveries – cultural resources (Section 106), historic property impacts & mitigation | STG 40 - Geotechnical Design Criteria Change – soil stabilization, hydraulic, codes | DES 40 - Hydraulic Design Changes – flow control, water quality, criteria changes | ROW 40 - Managed Access Issues – appeal hearing |  |  | PSP 40 - Interagency Issues (Sound Transit, USFS, cities, counties, etc.) – design coordination, agreements | MGT 40 - Political / Policy Changes | CTR 40 - Market Conditions – non-competitive bidding environment, lack of qualified bidders, bids exceed upset price or budget | CNS 40 - Schedule Uncertainty (general) |  | ENV - Environmental | ENV 80 - Construction Impacts – water quality, TESC | MGT - Management / Funding | MGT 10 - Project Management Issues – change in managers / other key leadership | MGT 20 - Delay – indecision, submittal review | MGT 30 - Funding – availability, cash flow restrictions | MGT 40 - Political / Policy Changes | MGT 50 - State Workforce Limitations | MGT 60 - Project Phasing / Packaging Changes | MGT 70 - Inadequate Quality Verification – VECP, ATC, review error |  | MGT 900 - Other MGT Issues
| ENV 50 - Hazardous Matls - soil/ groundwater contamination, building / structure abatement/ lead paint |  | DES 50 - Traffic Design Changes – ITS, Illumination, Signals, intersections | ROW 50 - Acquisition Issues – appraisals, condemnation, relocations, demolitions |  |  | PSP 50 - Multimodal Considerations – design coordination, agreements, bicycle, pedestrians, transit | MGT 50 - State Workforce Limitations | CTR 50 - Procurement Delays & Premiums – specialty materials/ equipment, "Buy America" | CNS 50 - Marine / Over-Water | ATC Alternative Technical Concept CSS Context Sensitive Solution DB Design - Build DBB Design - Bid - Build DBE Disadvantaged Business Enterprise ESA Endangered Species Act ITS Intelligent Transportation System MEF Maximum Extent Feasible MOT Maintenance of Traffic NEPA National Environmental Policy Act SEPA State Environmental Policy Act TESC Temporary Erosion & Sediment Control VECP Value Engineering Change Proposal WZTC Work Zone Traffic Control | ENV - Environmental | ENV 90 - Noise (permanent mitigation) | CTR - Contracting & Procurement | CTR 10 - Project Delivery Method – changes or issues | CTR 20 - Contract Language Issues – contract packaging, warranties, liquidated damages, DBE, insurance/bonding | CTR 30 - Contract Procurement Process Issues – addenda / extensions, protests | CTR 40 - Market Conditions – non-competitive bidding environment, lack of qualified bidders, bids exceed upset price or budget | CTR 50 - Procurement Delays & Premiums – specialty materials/ equipment, "Buy America" | CTR 60 - Contractor Performance Issues – productivity, quality | CTR 70 - Labor Issues – availability of specialty labor, labor / productivity disruptions | CTR 80 - Schedule Uncertainty – timing of award |  | CTR 900 - Other CTR Issues
| ENV 60 - Habitat Mitigation Issues – wetlands/ stream/ floodplain |  | DES 60 - WSDOT Initiated Changes – maintenance request, change to purpose and need |  |  |  |  | MGT 60 - Project Phasing / Packaging Changes | CTR 60 - Contractor Performance Issues – productivity, quality | CNS 60 - Constructability (non-geotech or marine) – site access, staging/ material handling, differing site conditions, etc. |  | ENV - Environmental |  | CNS - Construction | CNS 10 - Traffic Control & Staging – MOT / WZTC, multimodal traffic management | CNS 20 - Construction Permitting – work restrictions | CNS 30 - Work Window Coordination – weather, in/over-water | CNS 40 - Schedule Uncertainty (general) | CNS 50 - Marine / Over-Water | CNS 60 - Constructability (non-geotech or marine) – site access, staging/ material handling, differing site conditions, etc. | CNS 70 - Material Handling / Earthwork Issues – re-use, haul, disposal; hazardous mtls, lead paint | CNS 80 - Adjacent Projects – coordination among contractors, limited staging, sequencing | CNS 90 - Site Security – vandalism, encampments, damage | CNS 100 - Construction Accidents | CNS 900 - Other CNS Issues – change orders, disputes, claims
| ENV 70 - Environmental Justice (disadvantaged communities) – traffic mgmt, access, temp construction impacts |  | DES 70 - Tolling Design Changes – infrastructure requirements, toll collection, back-office |  |  |  |  | MGT 70 - Inadequate Quality Verification – VECP, ATC, review error | CTR 70 - Labor Issues – availability of specialty labor, labor / productivity disruptions | CNS 70 - Material Handling / Earthwork Issues – re-use, haul, disposal; hazardous mtls, lead paint |  | ENV - Environmental | ENV 900 - Other ENV Issues
| ENV 80 - Construction Impacts – water quality, TESC |  | DES 80 - External Initiated Changes (contractor or other party) – innovation, ATC | [5 empty] | CTR 80 - Schedule Uncertainty – timing of award | CNS 80 - Adjacent Projects – coordination among contractors, limited staging, sequencing |  | STG - Structures & Geotechnical | STG 10 - Structure Design Change – bridge superstructure, retaining walls
| ENV 90 - Noise (permanent mitigation) |  | DES 90 - ADA – curb ramp modifications require R/W, MEF approval | [6 empty] | CNS 90 - Site Security – vandalism, encampments, damage |  | STG - Structures & Geotechnical | STG 20 - Geotechnical Design Change – foundations, ground improvements, unsuitable materials
[10 empty] | CNS 100 - Construction Accidents |  | STG - Structures & Geotechnical | STG 30 - Structural Design Criteria Change – seismic, hydraulic, geometric, building codes
| ENV 900 - Other ENV Issues | STG 900 - Other STG Issues | DES 900 - Other DES Issues | ROW 900 - Other ROW Issues | UTL 900 - Other UTL Issues | RR 900 - Other RR Issues | PSP 900 - Other PSP Issues | MGT 900 - Other MGT Issues | CTR 900 - Other CTR Issues | CNS 900 - Other CNS Issues – change orders, disputes, claims |  | STG - Structures & Geotechnical | STG 40 - Geotechnical Design Criteria Change – soil stabilization, hydraulic, codes
STG - Structures & Geotechnical
STG - Structures & Geotechnical
STG - Structures & Geotechnical
STG - Structures & Geotechnical
STG - Structures & Geotechnical
STG - Structures & Geotechnical
[12 empty] | STG - Structures & Geotechnical | STG 900 - Other STG Issues
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 10 - Roadway Design Change – vertical / horizontal alignment, earthwork, pavement
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 20 - Roadway Design Criteria Change – Design Manual, design analysis approval, practical design considerations
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 30 - Aesthetic Design Changes – Architectural, CSS, Landscaping
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 40 - Hydraulic Design Changes – flow control, water quality, criteria changes
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 50 - Traffic Design Changes – ITS, Illumination, Signals, intersections
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 60 - WSDOT Initiated Changes – maintenance request, change to purpose and need
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 70 - Tolling Design Changes – infrastructure requirements, toll collection, back-office
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 80 - External Initiated Changes (contractor or other party) – innovation, ATC
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 90 - ADA – curb ramp modifications require R/W, MEF approval
DES - Design / PS&E Roadway, Hydraulics, etc.
[12 empty] | DES - Design / PS&E Roadway, Hydraulics, etc. | DES 900 - Other DES Issues
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 10 - Plan Development Issues – easements: temporary construction/subterranean, FHWA approval
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 20 - Project ROW Cost Change – change in land use/zoning, urbanization, market conditions
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 30 - Limited Access Issues – Access Revision Report (ARR), access hearing, permanent construction easement
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 40 - Managed Access Issues – appeal hearing
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 50 - Acquisition Issues – appraisals, condemnation, relocations, demolitions
ROW - Right-of-Way Acquisition & Access
ROW - Right-of-Way Acquisition & Access
ROW - Right-of-Way Acquisition & Access
ROW - Right-of-Way Acquisition & Access
ROW - Right-of-Way Acquisition & Access
[12 empty] | ROW - Right-of-Way Acquisition & Access | ROW 900 - Other ROW Issues
[12 empty] | UTL - Utilities | UTL 10 - Plan Development Issues – design coordination, agreements
[12 empty] | UTL - Utilities | UTL 20 - Practical Issues (in the field) – relocation, conflicts, discoveries
UTL - Utilities
UTL - Utilities
UTL - Utilities
UTL - Utilities
UTL - Utilities
UTL - Utilities
UTL - Utilities
UTL - Utilities
[12 empty] | UTL - Utilities | UTL 900 - Other UTL Issues
[12 empty] | RR - Railroad | RR 10 - Plan Development Issues – design coordination, agreements, right-of-entry
[12 empty] | RR - Railroad | RR 20 - Construction Coordination Issues – flagging, work restrictions / windows, right-of-entry requirements
[12 empty] | RR - Railroad | RR 30 - Property Rights Issues – challenges in acquiring from RR, considerations for delivery method (DB vs DBB)
RR - Railroad
RR - Railroad
RR - Railroad
RR - Railroad
RR - Railroad
RR - Railroad
RR - Railroad
[12 empty] | RR - Railroad | RR 900 - Other RR Issues
[12 empty] | PSP - Partnerships & Stakeholders | PSP 10 - Tribal Issues
[12 empty] | PSP - Partnerships & Stakeholders | PSP 20 - Public Involvement Issues
[12 empty] | PSP - Partnerships & Stakeholders | PSP 30 - Scope / Design Changes – artwork, shared-use pathways, arterial/intersection improvements
[12 empty] | PSP - Partnerships & Stakeholders | PSP 40 - Interagency Issues (Sound Transit, USFS, cities, counties, etc.) – design coordination, agreements
[12 empty] | PSP - Partnerships & Stakeholders | PSP 50 - Multimodal Considerations – design coordination, agreements, bicycle, pedestrians, transit
PSP - Partnerships & Stakeholders
PSP - Partnerships & Stakeholders
PSP - Partnerships & Stakeholders
PSP - Partnerships & Stakeholders
PSP - Partnerships & Stakeholders
[12 empty] | PSP - Partnerships & Stakeholders | PSP 900 - Other PSP Issues
[12 empty] | MGT - Management / Funding | MGT 10 - Project Management Issues – change in managers / other key leadership
[12 empty] | MGT - Management / Funding | MGT 20 - Delay – indecision, submittal review
[12 empty] | MGT - Management / Funding | MGT 30 - Funding – availability, cash flow restrictions
[12 empty] | MGT - Management / Funding | MGT 40 - Political / Policy Changes
[12 empty] | MGT - Management / Funding | MGT 50 - State Workforce Limitations
[12 empty] | MGT - Management / Funding | MGT 60 - Project Phasing / Packaging Changes
[12 empty] | MGT - Management / Funding | MGT 70 - Inadequate Quality Verification – VECP, ATC, review error
MGT - Management / Funding
MGT - Management / Funding
MGT - Management / Funding
[12 empty] | MGT - Management / Funding | MGT 900 - Other MGT Issues
[12 empty] | CTR - Contracting & Procurement | CTR 10 - Project Delivery Method – changes or issues
[12 empty] | CTR - Contracting & Procurement | CTR 20 - Contract Language Issues – contract packaging, warranties, liquidated damages, DBE, insurance/bonding
[12 empty] | CTR - Contracting & Procurement | CTR 30 - Contract Procurement Process Issues – addenda / extensions, protests
[12 empty] | CTR - Contracting & Procurement | CTR 40 - Market Conditions – non-competitive bidding environment, lack of qualified bidders, bids exceed upset price or budget
[12 empty] | CTR - Contracting & Procurement | CTR 50 - Procurement Delays & Premiums – specialty materials/ equipment, "Buy America"
[12 empty] | CTR - Contracting & Procurement | CTR 60 - Contractor Performance Issues – productivity, quality
[12 empty] | CTR - Contracting & Procurement | CTR 70 - Labor Issues – availability of specialty labor, labor / productivity disruptions
[12 empty] | CTR - Contracting & Procurement | CTR 80 - Schedule Uncertainty – timing of award
CTR - Contracting & Procurement
CTR - Contracting & Procurement
[12 empty] | CTR - Contracting & Procurement | CTR 900 - Other CTR Issues
[12 empty] | CNS - Construction | CNS 10 - Traffic Control & Staging – MOT / WZTC, multimodal traffic management
[12 empty] | CNS - Construction | CNS 20 - Construction Permitting – work restrictions
[12 empty] | CNS - Construction | CNS 30 - Work Window Coordination – weather, in/over-water
[12 empty] | CNS - Construction | CNS 40 - Schedule Uncertainty (general)
[12 empty] | CNS - Construction | CNS 50 - Marine / Over-Water
[12 empty] | CNS - Construction | CNS 60 - Constructability (non-geotech or marine) – site access, staging/ material handling, differing site conditions, etc.
[12 empty] | CNS - Construction | CNS 70 - Material Handling / Earthwork Issues – re-use, haul, disposal; hazardous mtls, lead paint
[12 empty] | CNS - Construction | CNS 80 - Adjacent Projects – coordination among contractors, limited staging, sequencing
[12 empty] | CNS - Construction | CNS 90 - Site Security – vandalism, encampments, damage
[12 empty] | CNS - Construction | CNS 100 - Construction Accidents
[12 empty] | CNS - Construction | CNS 900 - Other CNS Issues – change orders, disputes, claims

## Users Guide
Risk Management Plan (RMP) – user guide
The RMP describes how risk management will be structured and performed on the project. It becomes a subset of the project management plan. See the Project Management Online Guide for more information, http://www.wsdot.wa.gov/Projects/ProjectMgmt/ Also, review "A Policy for Cost Risk Assessment" (http://www.wsdot.wa.gov/Projects/ProjectMgmt/RiskAssessment/) to determine the appropriate level of detailed risk analysis to be performed on the project.
The RMP comprises four main sections of risk assessment:
1. Risk Identification
2. Risk Analysis (Qualitative & Quantitative)
3. Risk Response Strategy
4. Risk Monitoring and Control
Risk Identification determines which risk might affect the project and documents their characteristics. Risk identification is an iterative process because new risks may become known as the project progresses thought its life. The frequency of iterations and who participates in each cycle will vary from case to case. The project team is involved in this process to develop and maintain a sense of ownership of, and responsibility for, risks and associated risk response strategy. The Risk Identification process leads to one of the two main segments of the Risk Analysis section.
The Risk Identification section includes:
(1) Priority, this is the ranking of the risks by priority and occurs subsequent to the risk analysis.
(2) Risk Status defines the status of the risk event. The user has three status scenarios to choose from such as:
· Active, when the risk is being actively monitored and controlled
· Dormant, when the risk is low priority but may become high priority in the future
· Retired, when the risk is demised for any reason.
(3) Risk Identification number is a unique number assigned to the risk for tracking purpose.
(5) Risk Event (threat/opportunity), present a summary definition of the risk. It clarifies the risk outcome:
· If the risk outcome provides negative impact to the project (higher cost and/or longer duration) the risk is named a Threat, which should be minimized.
· If the risk outcome provides positive impact to the project (lower cost and/or shorter duration) the risk is named an Opportunity, which should be maximized.
(6) SMART Column provides a detailed description of the risk. Including information on the risk that is Specific, Measurable, Attributable, Relevant and Time bound. It describes the consequences of the risk to scope, schedule, budget or quality.
(7) Risk Trigger presents symptoms and warning signs that indicate whether each risk is likely to occur. This information is used the determine when to implement the Risk Response Strategies.
Qualitative Risk Analysis includes methods for prioritizing the identified risks for further action, such as Quantitative Risk Analysis (See A Policy for Cost Risk Assessment) or Risk Response Planning. Qualitative Risk Analysis assesses the priority of risks by using their probability of occurring, corresponding impact on project objectives if the risks do occur, as well as other factors such as the time frame and risk tolerance of the project constraints of scope, schedule, budget, and quality. Time critical risk related actions may magnify the importance of a risk. Qualitative Risk Analysis is a method for establishing priorities for Risk Response Planning and may lead into Quantitative Risk Analysis, when required. See the Project Managment Online Guide for more information about quantitative risk analysis.
(10-12) The Probability and Impact Matrix is a common way to determine whether a risk is considered low or high by combining the two dimensions of a risk; it probability of occurrence, and its impact on objectives if it occurs. High risks that have a negative impact (threat) on objectives may require priority action and aggressive response strategies. Low risk Threats may not require proactive management action beyond being placed on a watch list. Similarly, high risk opportunities that can be obtained most easily and offer the greatest benefit should, therefore, be targeted first. Low risk opportunities should be monitored.
Risk Owner (13) is the name of the person or office responsible for managing the risk event.
Risk Response Planning (strategy) is the process of developing options, and determining actions to be taken to enhance opportunities and reduce threats to the projects objectives. Planned risk responses must be appropriate to the significance of the risk, cost effective, timely, realistic within the project context, agreed upon by all parties involved, and owned by a responsible person.
(14-15) The Project Manager and Team agree upon the appropriate response strategy and design specific actions to implement that strategy for each risk. These strategies and actions include:
· Avoidance: The team changes the project plan to eliminate the risk or to protect the project objectives from its impact. The team might achieve this by changing scope, adding time, or adding resources (thus relaxing the so-called “triple constraint”). These changes may require upper management approval. Some risks that arise early in the project can be avoided by clarifying requirements, obtaining information, improving communication, or acquiring expertise.
· Transference: Risk transference shifts the ownership and responsibility for its management to a third party; it does not eliminate it. Transferring liability for risk is most effective in dealing with financial risk exposure.
· Mitigation: The team seeks to reduce the probability or consequences of a risk event to an acceptable threshold. Taking early action to reduce the probability and/or impact of a risk occurring on the project is often more effective than trying to repair the damage after the risk has occurred. Mitigation costs should be appropriate, given the probability of the risk and its consequences.
· Acceptance: The Project Manager and team decide not to change the project plan to deal with a risk, or cannot identify a suitable response action. A contingency plan may be developed or no action may be taken, leaving the project team to deal with the risk as it occurs.
Risk Monitoring and Control tracks identified risks, monitors residual risks, and identifies new risks, ensuring the execution of risk plans, and evaluating their effectiveness in reducing risk. Risk Monitoring and Control is an ongoing process for the life of the project. The list of project risks changes as the project matures, new risks develop, or anticipated risks disappear. Periodic project risk reviews repeat the tasks of identification, analysis, and response strategies. The project manager regularly schedules project risk reviews, and ensures that project risk is an agenda item at all Project Team meetings. Risk ratings and prioritization commonly change during the project lifecycle.
(16-17) Insert any comments that would be helpful for risk tracking and control.
If an unanticipated risk emerges, or a risk’s impact is greater than expected, the planned response strategy and actions may not be adequate. The project manager and the Project Team must perform additional response Strategies and actions to control the risk.
Risk control involves:
• Choosing alternative response strategies
• Implementing a contingency plan
• Taking corrective actions
• Re-planning the project
The task manager assigned to each risk reports periodically to the project manager on the effectiveness of the plan, any unanticipated effects, and any mid-course correction that the Project Team must take to mitigate the risk.
GENERAL NOTE:
The RMP also serves as a nice project performance measurement tool.

## Sheet1 (hidden)
X | X | X | X | X | X | X | X | X | X
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact
Probability
L H
L H
Impact